## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity 01 | 1 | 5 | 1 | 4 | 25%
Activity 02 | 1 | 6 | 1 | 6 | 100%
Activity 03 | 2 | 4 | 2 | 5 | 35%
Activity 04 | 4 | 8 | 4 | 6 | 10%
Activity 05 | 4 | 2 | 4 | 8 | 85%
Activity 06 | 4 | 3 | 4 | 6 | 85%
Activity 07 | 5 | 4 | 5 | 3 | 50%
Activity 08 | 5 | 2 | 5 | 5 | 60%
Activity 09 | 5 | 2 | 5 | 6 | 75%
Activity 10 | 6 | 5 | 6 | 7 | 100%
Activity 11 | 6 | 1 | 5 | 8 | 60%
Activity 12 | 9 | 3 | 9 | 3 | 0%
Activity 13 | 9 | 6 | 9 | 7 | 50%
Activity 14 | 9 | 3 | 9 | 1 | 0%
Activity 15 | 9 | 4 | 8 | 5 | 1%
Activity 16 | 10 | 5 | 10 | 3 | 80%
Activity 17 | 11 | 2 | 11 | 5 | 0%
Activity 18 | 12 | 6 | 12 | 7 | 0%
Activity 19 | 12 | 1 | 12 | 5 | 0%
Activity 20 | 14 | 5 | 14 | 6 | 0%
Activity 21 | 14 | 8 | 14 | 2 | 44%
Activity 22 | 14 | 7 | 14 | 3 | 0%
Activity 23 | 15 | 4 | 15 | 8 | 12%
Activity 24 | 15 | 5 | 15 | 3 | 5%
Activity 25 | 15 | 8 | 15 | 5 | 0%
Activity 26 | 16 | 28 | 16 | 30 | 50%

## Task 1 - Helicity Generator
Helicity Generator Boards Upgrade
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Fabrication of new boards | 1 | 1 | 1 | 1 | 100%
Firmware update | 1 | 1 | 1 | 1 | 100%
Test | 1 | 1 | 1 | 1 | 100%
Boards to MOLLER Col. | 1 | 1 | 1 | 1 | 70%
Commissioning | 1 | 3 | 1 | 3 | 50%
Install in CEBAF | 9 | 1 | 9 | 1 | 0%

## Task 2 - Helicity Decoder
Helicity Decoder Boards
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Fabrication of two prototypes | 1 | 1 | 1 | 1 | 100%
Firmware | 1 | 1 | 1 | 1 | 100%
Test of prototypes | 1 | 2 | 1 | 2 | 50%
Fabrication of 5 boards | 2 | 1 | 2 | 1 | 0%
Test | 2 | 2 | 2 | 2 | 0%
Fabrication of 15 boards | 4 | 1 | 4 | 1 | 0%
Distribute to Halls | 4 | 9 | 4 | 9 | 0%
Documentation | 9 | 1 | 9 | 1 | 0%

## Task 3 - RTP HV Driver
RTP HV Driver
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Document existing system | 1 | 1 | 1 | 1 | 100%
Requirements | 1 | 1 | 1 | 1 | 100%
System design | 9 | 1 | 9 | 1 | 0%
Driver technology evaluation | 9 | 1 | 9 | 1 | 0%
Test stand development | 9 | 1 | 9 | 1 | 0%
Prototype design & build | 9 | 1 | 9 | 1 | 0%
Production unit design & build | 10 | 1 | 10 | 1 | 0%
Install | 11 | 1 | 11 | 1 | 0%
Commission | 12 | 2 | 12 | 2 | 0%
Documentation | 13 | 1 | 13 | 1 | 0%

## Task 4 - IA HV Driver
IA HV Driver
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Document existing system | 1 | 1 | 1 | 1 | 100%
Requirements | 1 | 1 | 1 | 1 | 100%
System design | 2 | 2 | 2 | 2 | 35%
Isolated ground | 2 | 2 | 2 | 2 | 50%
Test stand development | 1 | 2 | 1 | 2 | 0%
Prototype design & build | 4 | 3 | 4 | 6 | 0%
Production unit design & build | 5 | 4 | 5 | 3 | 0%
Install | 10 | 1 | 10 | 5 | 0%
Commission | 10 | 2 | 10 | 1 | 0%
Documentation | 10 | 1 | 10 | 1 | 0%

## Task 5 - Helicity Magnets
Upgrade Helicity Magnets Control
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Document existing system | 10 | 1 | 10 | 1 | 0%
Requirements | 1 | 1 | 1 | 1 | 100%
System design | 10 | 2 | 10 | 2 | 0%
Isolated ground | 10 | 2 | 10 | 2 | 0%
Test stand development | 10 | 2 | 10 | 2 | 0%
Prototype design & build | 10 | 2 | 10 | 2 | 0%
Production unit design & build | 12 | 2 | 12 | 2 | 0%
Install | 14 | 1 | 14 | 1 | 0%
Commission | 15 | 2 | 15 | 1 | 0%
Documentation | 16 | 1 | 16 | 1 | 0%

## Task 6 - Polarization Feedback
Feedback on Polarization Orientation
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 0%
Study Wiens with small angles | 2 | 2 | 2 | 2 | 0%
System energy feedback | 2 | 2 | 2 | 2 | 0%
Decide method | 4 | 1 | 4 | 1 | 0%
System design | 5 | 3 | 5 | 3 | 0%
Implement feedback | 12 | 2 | 12 | 2 | 0%
Test | 12 | 2 | 12 | 2 | 0%
Install | 12 | 1 | 12 | 1 | 0%
Commission | 12 | 3 | 12 | 3 | 0%
Documentation | 15 | 1 | 15 | 1 | 0%

## Task 7 - Wien Flip
Wien Filters Slow Reversal – Wien Flip
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Beam studies | 1 | 3 | 1 | 3 | 50%
Study Vwiien Flip | 1 | 3 | 1 | 3 | 50%
Study solenoinds flip | 1 | 3 | 1 | 3 | 0%
Stability studies | 1 | 9 | 1 | 9 | 0%
Documentation | 10 | 1 | 10 | 1 | 0%

## Task 8 - Injector Tranasmission
Injector Transmission and Parity-Quality Beam
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Beam studies | 1 | 9 | 1 | 9 | 20%
Study Flip | 1 | 9 | 1 | 9 | 0%
Beam studies | 1 | 9 | 1 | 9 | 0%
Documentation | 10 | 1 | 10 | 1 | 0%

## Task 9 - Matching and Damping
Matching and Adiabatic Damping from 200 keV to Hall A
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Beam studies | 1 | 9 | 1 | 9 | 10%
Study injector matching | 1 | 9 | 1 | 9 | 10%
Study Hall A match | 1 | 9 | 1 | 9 | 0%
Measure damping | 1 | 9 | 1 | 9 | 0%
Documentation | 10 | 1 | 10 | 1 | 0%

## Task 10 - Fast FeedBack
Fast Feedback (FFB) System Resurrection
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Beam studies | 1 | 9 | 1 | 9 | 20%
Maintain system | 1 | 9 | 1 | 9 | 0%
Documentation | 10 | 1 | 10 | 1 | 0%

## Task 11 - Compton Pol
Compton Polarimeter Setup
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 3 | 1 | 3 | 50%
Beam setup | 12 | 1 | 12 | 1 | 0%
Measure halo | 12 | 2 | 12 | 2 | 0%
Documentation | 15 | 1 | 15 | 1 | 0%

## Task 12 - Beam Modulation
Beam Modulation
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Verify operation at 11 GeV | 1 | 1 | 1 | 1 | 100%
Hot checkout | 4 | 1 | 4 | 1 | 0%
Beam test | 4 | 4 | 4 | 4 | 0%
Documentation | 9 | 1 | 9 | 1 | 0%

## Task 13 - Phase Advance
Phase Advance
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Check beamline design | 1 | 9 | 1 | 9 | 0%
Beam studies | 12 | 3 | 12 | 3 | 0%
Documentation | 15 | 1 | 15 | 1 | 0%

## Task 14 - KLF Co-operation
Study Co-operation of MOLLER with K-long Experiment in Hall D
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Install low-rep laser | 1 | 1 | 1 | 1 | 100%
Injector setup | 1 | 1 | 1 | 1 | 0%
Photocathode effects | 2 | 6 | 2 | 6 | 0%
Model beam loading | 1 | 3 | 1 | 3 | 20%
Study beam loading | 4 | 4 | 4 | 4 | 0%
Beam studies | 2 | 6 | 2 | 6 | 0%
Report to Physics Division | 9 | 1 | 9 | 1 | 0%
Documentation | 9 | 1 | 9 | 1 | 0%

## Task 15 - Charge Asymmetries
Control of Charge Asymmetry on Halls B, C, and D Beams
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Install Hall D IA | 1 | 3 | 1 | 3 | 0%
Test feedback | 4 | 4 | 4 | 4 | 0%
Hall D parity DAQ | 4 | 4 | 4 | 4 | 0%
Test feedback | 4 | 4 | 4 | 4 | 0%
Documentation | 9 | 1 | 9 | 1 | 0%

## Task 16 - PQB Studies
Parity-Quality Beam (PQB) Studies in Injector and Hall
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 1 | 1 | 1 | 100%
Injector PQB studies | 1 | 9 | 1 | 9 | 30%
Hall A PQB studies | 4 | 12 | 4 | 12 | 0%
Documentation | 16 | 1 | 16 | 1 | 0%

## Task 17 - Halo Monitor
Halo Monitors in Hall A
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 3 | 1 | 3 | 0%
Halo target and detectors | 1 | 3 | 1 | 3 | 0%
Install | 9 | 3 | 9 | 3 | 0%
Test FSD | 9 | 3 | 9 | 3 | 0%
Controls | 9 | 3 | 9 | 3 | 0%
Test | 12 | 2 | 12 | 2 | 0%
Halo MCC readback | 12 | 2 | 12 | 2 | 0%
Measure halo | 12 | 2 | 12 | 2 | 0%
Documentation | 15 | 1 | 15 | 1 | 0%

## Task 18 - Apparatus Protection
Robust Beam Mis-steer Protection / Fast Shutdown Detectors in MOLLER Apparatus
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Requirements | 1 | 3 | 1 | 3 | 0%
Evaluate ion chamber | 4 | 4 | 4 | 4 | 0%
System design | 9 | 6 | 9 | 6 | 0%
Test of prototypes | 15 | 2 | 15 | 2 | 0%
System implementation | 24 | 1 | 24 | 1 | 0%
Documentation | 25 | 1 | 25 | 1 | 0%

## Task 19 - Hall A BPMs
New BPM Digital Receivers in Hall A line – instead of Sample/Hold cards
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| Requirements | 1 | 1 | 1 | 1 | 0%
| I&C test receiver | 1 | 3 | 1 | 3 | 0%
| Beam test | 1 | 9 | 1 | 9 | 0%
| Controls | 4 | 4 | 4 | 4 | 0%
| Commissioning | 4 | 4 | 4 | 4 | 0%
| Documentation | 9 | 1 | 9 | 1 | 0%

## Task 20 - Hall A BCMs
New BCMs electronics in Hall A line
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| Requirements | 1 | 3 | 1 | 3 | 0%
| Beam test | 1 | 3 | 1 | 3 | 0%
| Controls | 1 | 3 | 1 | 3 | 0%
| Commissioning | 4 | 4 | 4 | 4 | 0%
| Documentation | 9 | 1 | 9 | 1 | 0%