## Sheet1
BUBBLE CHAMBER SUMMER 2014 INSTALLATION |  |  | LAST UPDATED: April 14, 2014
Job | Task | Responsible | Status | Start | End
Fast Valve | Vacuum install | Heckman | No update |  | 2014-08-01
| FV interlocks | Kortze | ATLIS submitted |  | 2014-08-15
| PSS tie-in | Mahoney | No update |  | 2014-09-01
| Guage | EGG
Magnet | Magnet design | Benesch | Completed |  | 2014-03-15
| Magnet package | Gregory | Final edits |  | 2014-04-01
| Magnet build | Gregory/Grames | Vendor TBD |  | 2014-07-01
| Fixture design | Gregory | Completed |  | 2014-05-01
| Fixture package | Gregory | Completed |  | 2014-07-01
| Fixture build | Gregory/Grames | Vendor TBD |  | 2014-07-01
| Hall probe | Suleiman | Ordered | 2014-04-02 | 2014-05-15
| Hall probe SW | Software | Design Req TBD | 2014-05-15 | 2014-07-01
| Hall probe cable/network | ICN | Work Req TBD | 2014-05-15 | 2014-07-15
| Magnet mapping | MagTest | Plan TBD | 2014-07-01 | 2014-08-01
| Magnet install | S&A | Dates TBD | 2014-08-01 | 2014-09-01
Beamline Layout | Beamline design | Suleiman/Grames | Iterating |  | 2014-04-15
| Beamline package | Gregory | Waiting on final design |  | 2014-04-30
| Modify points | S&A | TBD |  | 2014-06-01
| Modify girders/feet | Install | TBD |  | 2014-06-15
| Vacuum install | EGG | TBD |  | 2014-06-30
| Diagnostics | ICN | TBD |  | 2014-06-30
| Controls | SW | TBD |  | 2014-08-01
| Component align | S&A | TBD |  | 2014-08-01
Radiator | Cooling flange design | ME | Completed |  | 2014-04-01
| Cooling flange fab (2x) | Shop | Completed |  | 2014-04-01
| Cooling flange leak/LCW test | Adderley | In process |  | 2014-05-05
| Radiator design | Meekins | In process |  | 2014-04-16
| Radiator purchase/fab | Meekins | In process |  | 2014-04-30
Photon Collimator | Collimator design | Suleiman | In process |  | 2014-05-01
| Collimator purchase/fab | Suleiman |  |  | 2014-08-01
Photon Dump | Dump design | Suleiman | In process |  | 2014-05-01
| Dump purchase/fab | Suleiman |  |  | 2014-08-01
Safety Review | Laughing Gas (N2O) | Meekins |  | 2014-04-01 | 2014-08-01
| Pressure System | Meekins |  | 2014-04-01 | 2014-08-01
| Mercury | Meekins |  | 2014-04-01 | 2014-08-01
| OSP | Meekins |  | 2014-04-01 | 2014-08-01
COO
ESAD
RSAD