## Specs
Last updated Aug 19, 2015
(#) Function | Type | Specifications | LCW | Hyst | Trim PS | Measured | Design BL | Design I | Status | MMF | Comments
(1) 15 deg bend | DS | DWG# 32709-C-0358 Winding: AWG14 | no | no | 10 A | Tested 2.5 A | 693 keV/c 603 G-cm @ 15 deg | 4.187 A | 8/19 - (1) Spare @ MMF | Test if too hot at 4.2 A | If too hot at 4.2 A build another with large guage wire on same type fixture
(1) Wien filter | WF | DWG: 32893-0001 | no | yes | 10 A | Tested to 10 A | 693 keV/c |  | 8/17 - Assembly @ UITF | Not ready | Waiting on some 8-32 x 3/8" screws to complete assembly; then map field profile @ 10A to cut electrodes
(1) keV spec. | D? | Small red dipole | no | yes |  | ? | 693 keV/c 1634 G-cm @ 45 deg | TBD | 8/17 - (1) @ MMF | HiPot Test to 3.5 A Axis profile By (x=y=0) @ 1.5, 2.5, 3.5 A) B v. I | Found dipole in cabinet, can work at 350keV or just use the DL (next one); it's stronger than necessary but will work.
(1) keV spec. | DL | Designed 2014 | no | yes | 10 A | Measured 2014 Tested to 10 A | 10 MeV/c 14500 G-cm @ 25 deg | TBD | 8/17 -(1) @ MMF | Tested and ready | Ready, see comments above
(2) Chicane | D? | Big red dipole | yes | yes | 10 A | ? | 10 MeV/c 14500 G-cm @ 25 deg | TBD | 8/17 - (2) @ MMF | Check LCW HiPot Test to 5 A (requires 14500 G-cm) Axis profile By (x=y=0) @ 1, 3, 5 A) B v. I | These will be vertical chicane dipoles, should work fine. Need 14.5 kG-cm, MMF will find good max I and map. We'll need fixtures to support, heavy.
(1) Waist Y | FH | DWG# 32709-0319 Spool: SW, AWG14 square, N=742 Steel: L=3.0", ID=2.5", OD=6.875" | no | yes | 10 A | Oct. 1998 Tested 2A 8.62E4 G2-m/A | 693 keV/c F=50cm, 4.3E5 G2-cm Elegant = 4.9E5 G2-cm | 2.22 A 2.39 A | 8/18 - (1) @ MMF | HiPot Test for 3.0 A (V,R) Axis profile Bz (x=y=0) @ (1,2,3 A) B v. I | Mapping at higher current
(1) Waist Wien | FB | DWG#: UI-D-2709-32 Spool: SW, AWG14 square, N=742 Steel: L=3.0", ID=2.0", OD=6.875" | no | yes | 10 A | Jan. 1992 Tested 3.65A 1.0E5 G2-m/A | 693 keV/c F=50cm, 4.3E5 G2-cm Elegant = 7.31E5 G2-cm | 2.07 A 2.71 A | 8/17 - (1) @ MMF | HiPot Test for 3.5 A (V,R) Axis profile Bz (x=y=0) @ (1.5, 2.5, 3.5 A) B v. I | Testing at "old" high current
(1) Waist C2 (1) Waist Bunch | FA | DWG: I0038D01 Spool: CW, AWG18, N=520 Steel: L=2.62", ID=1.5", OD=6.25" Thin central plate | no | yes | 10 A | Tested 2 A B2L=1.11E5 G2-cm/A | 693 keV/c F=50cm, 4.3E5 G2-cm Elegant = 4.89E5 G2-m Elegant = 5.5E5 G2-cm | 1.96 A 2.10 A 2.22 A | 8/17 - (1) FA03 @ UITF 8/17 - (1) FA05 @ MMF | HiPot Test for 2.5 A (V,R) Axis profile Bz (x=y=0) @ (0.5, 1.5, 2.5 A) B v. I | Mapping FA03 at higher current; FA05 is captured on chopper cavity at UITF
(2) Chpping | FD | Steel DWG# Coils DWG#: 39200-D-0067 | no | yes | 10 A | ? | 693 keV/c Elegant = 3.83E5 | 1.64 A | 8/17 - (2) Fab @ shop | Not ready | Shop is fab'ing two solenoids and will resuse spare coils; when done they go to MMF to measure; need 1.6-1.8 A
(1) Waist QCM | FQ | DWG#: 39200-0210 Spool: CW AWG18, N=573 Steel: L=2.75", ID=1.5", OD=6.25" Thick central plate | no | yes | 10 A | Tested March 2000 Tested 2.0 A B2L=1.34E5 G2-cm/A | 693 keV/c F=50cm, 4.3E5 G2-cm Elegant = 4.11E5 G2-cm | 1.78 A 1.75 A | 8/17 - (1) @ MMF | HiPot Test for 2.5 A (V,R) Axis profile Bz (x=y=0) @ (0.5, 1.5, 2.5 A) B v. I | Mapping at higher current
(2) Wien asti. | Q? | Found in locker | no | yes | 10 A | n/a | 693 keV/c | TBD | 8/17 - (2) @ MMF | HiPot Test for 4 A Measure quad strength @ 0.5 or 1 cm | Found two smalls quads for Wien filter; small ID good for 1.5" pipe. MMF is learning how strong they are
(2) Chic. Disp. | QD | MQD drawing package | yes | yes | 10 A | yes | 10 MeV/c 3214 G @ 10 A | <10 A | 8/17 - (2) MMF refurb | Not ready | Two used QD's at MMF can be refurbed to correct dispersion in MeV vertical chicane
(11) Transport | QJ | MQJ drawing package | yes | yes | 10 A | yes | 10 MeV/c 594 G @ 10 A | <10 A | 8/17 - (13) Fabrication | Not ready | New QJ's being fab'd for MeV transport line.