## Sheet1
Quarter Year | Jlab |  |  | UO |  |  | MSU |  |  | AIST
| Tasks | Procure | Labor | Tasks | Procure | Labor | Tasks | Procure | Labor | Tasks | Procure | Labor
Oct-Dec 2016 | Develop theory of ultra-low emittance from dc high voltage photogun |  |  | Develop theory and simulations of the effects of spatial coherence on electron vortex beam production |  |  | Mott : Familiarize with Jlab Mott polarimeter
Jan-Mar 2017 | Develop GPT simulation model of photogun and diagnostic for low emittance beam | $3k - license |  | Simulate vortex beam behavior in beamline optics (quadrupoles, hexapoles, bending magnets, etc) |  | 1 wk @ Jlab | Mott : Develop simulation tool for Mott
Apr-Jun 2017 | Perform GPT multivariate optimization of photogun parameters (photocathode, temperature, E/B fields, laser pulse) |  |  | Develop simulation tools and calculations for nanograting placement relative to cathode Design nanogratings |  |  | Mott : Simulation of parameter space, sensitiity, energy depend.
Jul-Sep 2017 | Integrate low-emittance photogun and vortex grating simulations | $10k - gratings |  | Fabricate gratings |  | 1 wk @ Jlab | Mott : Simulation of proposed exp't conditions Develop S2E experiment simulation, with Mott
Oct-Dec 2017 | Complete design of nanograting, diagnostic chamber, and Mott polarimeter |  | 4 wks designer | Qualify gratings at UO |  |  | Mott : finalize configuration
Jan-Mar 2018 | Fabricate electrode, nanograting/diagnostic chamber, beam line components | $30k |  | Ship gratings to JLab |  |  | Mott : assemble target ladder, detectors, collimators
Apr-Jun 2018 | Modify HV chamber/electrode for cooling Test chamber with HV/cooling Assemble nanograting/diagnostic chamber | $15k |  |  |  | 1 wk @ Jlab | Mott : build DAQ, test
Jul-Sep 2018 | Assemble experiment beam line Make beam from cooled photocathode Commission beam line | $15k | 4 wks eng. Sup. |  |  |  | Mott : integrate to beam line
Oct-Dec 2018 | Measure beam emittance, compare to model
Jan-Mar 2019 | Measure beam OAM, compare to model
Apr-Jun 2019 | Measure Mott scattering, compare to model
Jul-Sep 2019 | Write up results for publication
Note on D5: Microsoft Office User: Eliminate?