## AIPINJ FY19
| Job | When | # | Total | WFO
| Replace Gun2 electrode | Apr-May, 2019 | 2 | 10 | ME 2 wks
| Build two 200keV Wien filters | FY19 | 2 | 50 | ME 8 wks S&A 2 wks
| Wien filter HVPS rack ISB | Aug-Oct, 2019 | 1 | 5 | EES 2 wks Software 2 wks
| Wien filter HV relays | Aug-Oct, 2019 | 10 | 25
| Wien filter 20A PS | Aug-Oct, 2019 | 2 | 10 | DC power 2 wks Software 2 wks
| Build/install PSS kicker 200kV | Apr-May, 2019 | 2 | 50 | S&A 2 wks
Baseline | Activity |  |  | FY19 MUST+SHOULD | FY19 MUST | MSMECH | MSSURV | EESICS | EESDCP | EESSAF
Not in the plan | Replace Gun2 electrode |  |  | 0 |  | 0 | 0
Reach | Build two Wien filters |  |  | 100 | 100 | 4 wks: Danny Machie 4 wks: Shaun Gregory | Kelly Tremblay - 2 hr Chris Gould - 6 hr Steve Hardisty - 3 day Bobby Mares - 3 day
| Install Wien HVPS in rack |  |  | 5 | 5
| HV relays + switch chassis |  |  | 10 | 2.5 |  |  | Designer : 3 dy Tech I : 1 wk
| 200KV Wien PS |  |  | 15 | 15 |  |  |  | Eric Diggs : 1 wk Jim Coleman : 0.5 wk Jason Delk : 1 wk
| (9) Low power solenoids |  |  | 60 | 60
(7) High power solenoids
Vacuum coating
| PSS Kicker |  |  | 20 | 20 |  |  |  |  | TBD
| 200kV chopper amplifiers |  |  | 100 | 0
| Beamline design |  |  | 0 | 0 | 8 wks: Danny Machie 8 wks: Shaun Gregory
| TOTAL |  |  | 310 | 202.5
| Arne Target |  |  | 200 | 200

## AIPINJ TOTAL ETC
COMPLETE
COULD HAPPEN FY19
GUESS/NEED INFO
WILD CARD
System | Item | Comment | Unit Cost | Have |  | Want |  | MUST |  | SHOULD |  | LIKE |  | LABOR
|  |  |  | Qty | Total | Qty | Total | Must | Total | Should | Total | Like | Total | CIS | ME | MS | Facil | S&A | I&C | RF | SRF | MMF | DC | PSS | Software | Req
200KV Gun | Fixed DILO system | Dedicated, no crane operation | 31690 | 0 | 0 | 1 | 31690 |  | 0 | 1 | 31690 |  | 0 | 0.5
200KV Gun | Root pump | Shorten evac 1 shift => hour | 6647 | 0 | 0 | 1 | 6647 |  | 0 | 1 | 6647 | 0 | 0
200KV Gun | R28 Receptacles | Spare | 750 | 0 | 0 | 2 | 1500 |  | 0 | 0 | 0 | 1 | 1500 | 0
200KV Gun | R28 350KV 10' CABLE | Gun cables | 3265 | 4 | 13060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=379220
[9 empty] | 0 |  | 0 |  | 0
Wien Filter Rack | Re-purposed 2 rack from ACE | Installed Jan 2019 | 1000 | 1 | 1000 | [11 empty] | 0.5
200KV Wien Magnet | 20A POWER SUPPLIES | Ordered FY19 | 7000 | 2 | 14000 | 0 | 0 | 0 | 0 | [13 empty] | 0
200KV Wien Magnet | Install 20A power supplies to Wiens | Labor + Cables + Drop | 1000 |  |  | 1 | 1000 | 1 | 1000 | [13 empty] | 2.6
200KV Wien Magnet | Modify steel of CEBAF H/V Wiens | MS labor during 2020 down | 2000 | 0 | 0 | 2 | 4000 | 1 | 4000 |  |  |  |  | 1 | 1 | X |  | 0.5
200KV Wien Magnets | Fabricate 20A coil sets (3 pairs) | 20A coils sets | 2000 | 0 |  | 3 | 2000 | 3 | 6000 |  |  |  |  | 1 | 1
200KV Wien Filter | Build new chamber magnet from scratch | Backup plan | 50000
200KV Wien HV | 40kV Feedthrough | Testing Aug/Sep 19 | 340.4 | 4 | 1361.6 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0.5 | 0.2 |  |  |  | 0 | [6 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=385700
200KV Wien HV | 40kV 8' cable | Testing Aug/Sep 19 | 120.82 | 4 | 483.28 | 0 | 0 |  | 0 |  | 0 |  | 0 | [12 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=385700
200KV Wien HV | 70KV SPDT w/ leads HV Switches | Received | 1017 | 8 | 8136 | 0 | 0 |  | 0 |  | 0 |  | 0 | [12 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=380299
200KV Wien HV | 30KV POS HVPS | At ISB | 5150 | 3 | 15450 | 0 | 0 |  | 0 |  | 0 |  | 0 | [12 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=372468
200KV Wien HV | 30KV NEG HVPS | At ISB | 5150 | 3 | 15450 | 0 | 0 |  | 0 |  | 0 |  | 0 | [12 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=372468
200KV Wien HV | RS-232 interace to optical comm | KC 7/24/19 | 550 | 3 | 1650 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 9 | [5 empty] | 2.5 | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=372468
200KV Wien HV | optical interface to PS | KC 7/24/19 | 645 | 3 | 1935 | 0 | 0 |  | 0 |  | 0 |  | 0 | [12 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=372468
200KV Wien HV | port server | KC 7/24/19 | 1500 | 0 | 0 | 1 | 1500 | 1 | 1500 |  | 0 |  | 0
200KV Wien HV | HV connectors | KC 7/24/19 | 4000 |  |  | 1 | 4000 | 1 | 4000 |  | 0 |  | 0
200KV Wien HV | HV Switch chassis | KC 7/24/19 | 1666.6667 | 0 | 0 | 1 | 1666.6667 | 3 | 5000 |  | 0 |  | 0 | [12 empty] | https://misportal.jlab.org/reqs/pr/viewPr.do?prNum=386699P
200KV Wien HV | Communications chassis | KC 7/24/19 | 1000 | 0 | 0 | 3 | 3000 | 1 | 3000 |  | 0 |  | 0
200KV Wien HV | HV Cables | Order placed already | 1490 | 1 | 1490 | 2 | 2980 |  | 0 |  | 0 |  | 0 | [12 empty] | https://misportal.jlab.org/reqs/pr/viewPrItems.do?prNum=386402
[9 empty] | 0 |  | 0 |  | 0
Magnets | New 15 deg dipole on 3" pipe | Jay/Reza design | 5000 |  |  | 2 | 10000 | 1 | 10000 |  | 0 |  | 0 | 0 | 2 | x | 0 | 0.4 | 0.2 | 0 | 0 | 0.4 | 0.4 | 0 | 0.1
Magnets | (7) keV beam line solenoids | Meyers/Christopher SOW | 10000 | 0 | 0 | 7 | 70000 |  | 0 | 1 | 70000 |  | 0 | 4 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Field map
Magnets | (2) spare coils | Meyers/Christopher SOW | 5000 | 0 | 0 | 2 | 10000 |  | 0 | 1 | 10000 |  | 0
Magnets | (2) keV chopper solenoids | Meyers/Christopher SOW | 10000 | 0 | 0 | 2 | 20000 |  | 0 |  |  | 1 | 20000 | [11 empty] | 0.2
Magnets | Wien quads | TBD | 2000 | 0 | 0 | 4 | 8000 | 1 | 8000
Magnets | Haimsons replace MAD style + fixtures | See PR# 383631 | 540 | 0 | 0 | 10 | 5400 | 0.5 | 2700 | 0.5 | 2700 |  | 0 | 0.2 | 0 | X | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.2 | 0 | 0.1
Magnets | Earth correcting coils | New supports + coil | 1000 | 0 | 0 | 3 | 3000 | 1 | 3000 |  | 0 |  | 0
[9 empty] | 0 |  | 0 |  | 0
PSS | Upgrade + spare 200kV kicker | Test existing Sep 2019 | 20000 | 0 | 0 | 1 | 20000 | 1 | 20000 |  | 0 |  | 0 | 2 | 2 | ? | [7 empty] | 2
PSS | Increase 500keV dipole chamber gap | Gap magnet | 5000 | 0 | 0 | 1 | 5000 |  |  | 1 | 5000 |  | 0 | 1 | 1 | X | [5 empty] | 0.5 |  | 2
[9 empty] | 0 |  | 0 |  | 0
Vacuum | New Y-chamber | Lesker | 5000 | 1 | 5000 | 0 | 0 | [5 empty] | 0 | 1
Vacuum | Replace DP getters (Y, DP, DP) | 7/17/19 quote Marcy/SAES | 7650 | 0 | 0 | 6 | 45900 | 0.33 | 15147 | 0.33 | 15147 | 0.33 | 15147
Vacuum | Replace DP IP's | Must=1I01,1I05, Should=1I07 | 4000 |  |  | 3 | 12000 | 0.66 | 7920 |  |  | 0.33 | 3960
Vacuum | Bellows | Expect 20% leaky | 395 |  |  | 2 | 790 | 1 | 790
Vacuum | Valves | (1) New, (1) leaky | 2770 |  |  | 2 | 5540 | 1 | 5540
Vacuum | Bakeouts | heater, insul, pwr boxes, controls | 1500 |  |  | 1 | 1500 | 1 | 1500
Vacuum | NEG coating | power supply, materials | 5000 |  |  | 1 | 5000 |  | 0 | 1 | 5000
Vacuum | Reworking the beam line | Nipples, gaskets, nuts/bolts | 2000 |  |  | 1 | 2000 | 1 | 2000
[9 empty] | 0 |  | 0 |  | 0
Instrumentation | 2nd Decarad (replace broken Radmon) | 7/17/19 quote Keith Cole | 4000 | 1 | 4000 | 1 | 4000 |  | 0 | 1 | 4000 |  | 0 | 2 | 2 |  |  |  | 2
Instrumentation | Remotely movable A1/A2 apertures |  | 2000 | 0 | 0 | 2 | 4000 |  | 0 |  |  | 1 | 4000 | 2 | 2 | x |  |  | 1 | [5 empty] | 1
Instrumentation | Repurpose stripline cavities | Waiting on # from Phil/Chris |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
Instrumentation | Reworking the beam line | Cables, connectors, etc | 1000 |  |  | 1 | 1000 | 1 | 1000
[9 empty] | 0 |  | 0 |  | 0
Warm RF | Prebuncher jobs | Test Aug 2019 | [6 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0.2 | 1 | 0 | 0 | 0.2 | 1 | 0.4
Warm RF | Chopper | Test Aug 2019
Warm RF | Buncher | Test Aug 2019
Warm RF | Capture | Remove 2020
[9 empty] | 0 |  | 0 |  | 0
Booster | Cryo jobs | [7 empty] | 0 |  | 0 |  | 0
Booster | LLRF hardware/controls jobs | [7 empty] | 0 |  | 0 |  | 0
Booster | SRF hardware/controls jobs | [7 empty] | 0 |  | 0 |  | 0
Booster | Install jobs | [7 empty] | 0 |  | 0 |  | 0
|  |  | TOTALS |  | 83015.88 |  | 293113.6667 |  | 102097 |  | 150184 |  | 44607 | 15.2 | 13.2 | 0 | 0.5 | 1.9 | 12.9 | 1 | 0 | 1.9 | 4.4 | 5 | 4.3
|  |  |  | Completed |  | M+S+L |  | MUST |  | SHOULD |  | LIKE |  | 15.2 | 40.8 | [9 empty] | 4.3
|  |  |  | 83015.88 |  | 293113.6667 |  | 296888 | [5 empty] | CIS | ME | MS | Facil | S&A | I&C | RF | SRF | MMF | DC | PSS | Software
|  |  | Est. purchases | [5 empty] | 41000 |  | 136000 |  | 20000
|  |  | FY19 BUDGET (200k) |  | 60000 | [9 empty] | 9 wks out of 22 wks

## Marcy's vacuum
Parts list CEBAF upgrade
|  |  | number | subtotal
bellows for viewers (2x) | 395 | each | 2 | 790 | REQ 306988
replacement ion pumps for DP cans (3x) | 4000 | each | 3 | 12000
replacement NEG pumps for DP cans (10x) | 7650 |  | 4 | 30600
valve VBV 1I07 replacement - vat o ring | 2770 | each | 1 | 2770 | REQ 281693
hardware: strap nuts, bolts, gaskets | 1500 |  | 1 | 1500
gaskets: 100x 2.75 silver, 50x 4.5" silver, |  |  |  | 0
0
replace ion pumps VIP0I05, 6, 6A, 7, VIP1Kxx: they are all 11 L/s old pumps?? | 2800 |  | 4 | 11200
"---- check for field emission on VIP0I07, replace if needed | 2800 |  | 1 | 2800
0
Valves for beamline: VBV0I06, 0I07, 1Dxx | 2770 |  | 1 | 2770
0
3 more short heaters | 53 |  | 3 | 159
pink insulation | 100 |  | 1 | 100
double output heater boxes | 100 |  | 2 | 200
several more NI thermouple readers (3x) | 115 |  | 3 | 345
2x USB 6008 readers | 315 |  | 2 | 630
gamma ion pump power supplies for bakeouts | 1448 |  | 2 | 2896
gaskets: 100x 2.75 silver, 50x 4.5" silver, |  |  |  | 0
|  |  | estimate | 68760
WP module replacement
| WP1250 | 560 | L/s | ZAO UHV | 1400 | L/s
y chamber | 4x | 2240 |  | 2 | 2800
narrow DP can | 2x | 1120 |  | 1 | 1400

## Keith's Wien controls
Task Name | Procurements | EE | CS | AC/TA | Tech | SS
Wein HV Filter System |  | 2 | 2 | 2 | 4 | 5
HV Switch Chassis X3 | 5
Communications Chassis X3 | 3
Port Server | 1.5
System Installation
Connectors/ field cabling | 4
System testing |  | 0.5 | 0.5 |  | 0.5
1
Material costs total / $K | 13.5
Labor in manweeks total |  | 2.5 | 2.5 | 2 | 4.5 | 6