## Sheet1
LAST UPDATED: June 19, 2014 (Grames)
ME Drawings | Dwg Status | In-Hand | Lead | JLAB MACHINE SHOP JOBS |  |  |  | ADDITIONAL PROCUREMENTS or PARTS
|  |  |  | Submitted | Shop No. | Requested | Needed | More Parts? | What? | Status | Vendor
JL0008724 COLLIMATOR TABLE PLATE.pdf | Released | No | EGG | 2014-06-19 | 325178 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0011888 SPOOL 1.50 DIA 2.75 NR X 2.75 NR.pdf | Released | No | EGG | 2014-06-19 | 325181 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0014290 BUBBLE CHAMBER GIRDER SUB-ASSY.pdf | Released | No | EGG | n/a | n/a | n/a | n/a | Yes | JL0014290
JL0014294 COLLIMATOR TABLE PEDESTAL WELDMENT.pdf | Released | No | EGG | 2014-06-19 | 325176 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0014306 BUBBLE CHAMBER GIRDER CHASSIS.pdf | Released | No | EGG | 2014-06-19 | 325175 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0014312 BUBBLE CHAMBER GIRDER ASSEMBLY.pdf | Released | No | EGG | n/a | n/a | n/a | n/a | Yes | JL0014312
JL0014369 GIRDER 2 ARR - INSTALL.pdf | Released | No | EGG | n/a | n/a | n/a | n/a | Yes | JL0014369
JL0014371 QD SPACER PLATE.pdf | Released | No | EGG | 2014-06-19 | 325179 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0015095 CU COLLIMATOR MOUNTING ASSEMBLY.pdf | Released | No | EGG | 2014-06-19 | 325177 | 2014-08-01 | 2014-08-08 | No | n/a | n/a | n/a
JL0015109 BUBBLE CHAMBER 2ND PEDESTAL WELDMENT.pdf | Released | No | EGG | 2014-06-19 | 325174 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0015130 COLLIMATOR TABLE ASSEMBLY.pdf | Released | No | EGG | n/a | n/a | n/a | n/a | Yes | JL0015130
JL0015132 ADD ON PLATE.pdf | Released | No | EGG | 6.19 | 325180 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0015733 CU RADIATOR WINDOW ASSY.pdf | Released | No | MEEKINS | - | - | - | - | - | - | - | -
JL0015777 CU COLLIMATOR.pdf | Released | No | ANL/MEEKINS | - | - | - | - | - | - | - | -
JL0016546 SPOOL 1.50 DIA 2.75 NR X 2.75 NR.pdf | Released | No | EGG | 2014-06-19 | 325181 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
JL0009386 ALUMINUM PHOTON BEAM DUMP.pdf | Released | No | EGG | 2014-06-19 | 325182 | 2014-07-25 | 2014-08-01 | No | n/a | n/a | n/a
Fixture drawing for Aluminum dump | Waiting | No | EGG |  |  |  |  | No | n/a | n/a | n/a
Points drawing for survey/alignment group | Waiting | No | EGG | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Template drawing for dipole installation | Waiting | No | EGG | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a