## Slide 1: Bubble Chamber Schedule – 2017
February 9, 2017

## Slide 2
1st Pass at Injector Summer SAD 2017 Calendar
# | Week | CEBAF | Float | 4-LLRF | Bubble | Parity Beam | Upgrade Gun
0 | 20-Mar | Spring Run |  |  |  |  | 
1 | 27-Mar |  |  | 4-LLRF Installation | Installation |  | 
2 | 3-Apr |  |  | 4-LLRF Beam | Installation |  | 
3 | 10-Apr |  |  |  | Bubble Run |  | 
4 | 17-Apr |  | Float |  |  |  | 
5 | 24-Apr |  |  |  |  | Beam #1 Spot Size | 
6 | 1-May |  |  |  |  |  | Gun 2 v. ITS
7 | 8-May |  |  |  |  |  | Gun 2 v. 200kV
8 | 15-May |  | Float |  |  |  | 
9 | 22-May |  |  |  |  | Laser opportunity | Modify Gun2/Gun3
10 | 29-May |  |  |  |  | Laser opportunity | Bake
11 | 5-Jun |  |  |  |  |  | Prep/HV Commision
12 | 12-Jun |  |  |  |  |  | Beam Commission
13 | 19-Jun |  |  |  |  |  | 200kV Commission
14 | 26-Jun |  |  |  |  | Laser opportunity | Backout Point
15 | 4-Jul |  |  |  |  | Laser opportunity | 
16 | 11-Jul |  | Float |  |  |  | 
17 | 18-Jul |  |  |  |  | PQB Laser | 
18 | 25-Jul |  |  |  |  | Beam #2 RTP | 
19 | 7-Aug |  |  |  | Bubble Run |  | 
20 | 14-Aug |  |  |  | Bubble Run |  | 
21 | 21-Aug |  | Float |  |  |  | 
22 | 28-Aug | INJ/NL HCO |  |  |  |  | 
23 | 4-Sep | 4-Beam Setup |  |  |  |  | 
24 | 11-Sep | Restore CEBAF |  |  |  |  | 

## Slide 3: Bubble Chamber Experiment
Chamber has been modified to use only one liquid as both active and buffer – no more mercury
Testing has started and plan to be ready by end of March
Chamber is expected at JLab in April 2017
April run plan:
  1 week to install and 1 week of beam (day + swing)
  Active liquid is C2F6 (very similar operating parameters as N2O)
  Beam energy: 4 – 6 MeV
  Beam current: 1 nA – 100 µA
  Prefer to run with RF at 2K but willing to try 4K
Keep chamber installed at 5D line
Plan to run again C2F6 in August: 2 weeks of beam (day + swing)

## Slide 4
Bubble Chamber Tasks:
Implement 5 MeV dipole precision DCCT current readback
Measure beam position on radiator – use x-ray fluorescent screen
Approved to run 10 μA CW and total energy of 10 MeV – needs approval to run at 100 μA
Calibrate BCM and measure nA beam currents
Re-isolate radiator to measure beam current
Survey 5D line (radiator and collimator)
Replace lead shielding with copper and iron bricks
Test the bubble chamber Gumby laser shutter