## Summary Sheet (2)
[7 empty] | FY14 G&A | FY15 G&A | FY16 G&A
[7 empty] | 1.4538 | 1.49 | 1.513
DIRECT $
FY2014: |  |  | Direct |  |  |  | with G&A (loaded) |  |  | Notes
Org | System | FTEs | Labor | Proc | Total |  | Labor | Proc | Total
|  | 1.22 | 160.322 | 189.48 | 349.802 |  | 233.0817 | 274.2927 | 507.3744 | Actuals from PSR
FY2015:
Org | System | FTEs | Labor | Proc | Total |  | Labor | Proc | Total | Notes
MSSURV | Survey/Alignment | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
EESICS | Inst & Control | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
EESRFS | EESRFS | 4.0364 | 468.245 | 252.5 | 720.745 |  | 697.6851 | 373.5374 | 1071.2224 | only 1 >$50K known at this time - power supplies purchased in FY15
EESDCP | DC Power | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
EESSAF | PSS | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
EESSAF | MPS | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
EESSAF | ODH | 0.30455 | 26.962 | 10.6665 | 37.6285 |  | 40.1734 | 15.8931 | 56.0665
MSCRYO | Cryo | 1.965 | 142.334 | 48 | 190.334 |  | 212.0777 | 71.52 | 283.5977 | Waiting for an update from J. Creel concerning heat exchanger
MSMECH | Mech Design | 1.5 | 194.913 | 0 | 194.913 |  | 290.4204 | 0 | 290.4204
OPSSFT | Software & Control | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
SRFOPS | SRF Support | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
ACCCIS | Gun Group | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | Currently not charging any labor to the project - AWP has actuals
FM | Facilities | 0.772 | 104.911 | 300 | 404.911 |  | 156.3174 | 447 | 603.3174 | Still waiting for estimates from vendors
| Total | 8.5779 | 937.365 | 611.1665 | 1548.5315 |  | 1396.6738 | 907.9504 | 2304.6243
FY2016: | 1.75% raises for FY16 is included
Org | System | FTEs | Labor | Proc | Total |  | Labor | Proc | Total | Notes
MSSURV | Survey/Alignment | 0.50341 | 69.2001 | 0 | 69.2001 |  | 104.6997 | 0 | 104.6997
EESICS | Inst & Control | 2.1773 | 209.814 | 219.5 | 429.314 |  | 317.4486 | 332.1035 | 649.5521
EESRFS | EESRFS
EESDCP | DC Power | 0.33182 | 32.21 | 144.5 | 176.71 |  | 48.7337 | 218.6285 | 267.3622
EESSAF | PSS | 1.5489 | 153.8638 | 35 | 188.8638 |  | 232.7959 | 52.955 | 285.7509 | Still awaiting final est
EESSAF | MPS | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | Still awaiting final est
EESSAF | ODH
MSCRYO | Cryo | 0.5 | 62.4161 | 42.5 | 104.9161 |  | 94.4356 | 64.3025 | 158.7381
MSMECH | Mech Design
OPSSFT | Software & Control | 1.2227 | 174.9579 | 58 | 232.9579 |  | 264.7113 | 87.754 | 352.4653
SRFOPS | SRF Support | 0.091 | 11.2047 | 0 | 11.2047 |  | 16.9527 | 0 | 16.9527
ACCCIS | Gun Group | 1.5455 | 226.7194 | 381.834 | 608.5534 |  | 343.0264 | 577.7148 | 920.7412
FM | Facilities
| Total | 7.9205 | 940.3859 | 881.334 | 1821.7199 |  | 1422.8038 | 1333.4583 | 2756.2622
Original Est. by Hari Areti |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total
on 2-7-2014 | FY14 | 3.67 | 462.537 | 478.951 | 941.488 |  | 682.705 | 671.232 | 1353.937
| FY15 | 2.5 | 312.08 | 557.097 | 869.177 |  | 465 | 830.074 | 1295.074
| FY16 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Total | 6.17 | 774.617 | 1036.048 | 1810.665 |  | 1333.4583 | 1501.306 | 2649.011
Revised Est. |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total
by Matt Poelker | FY14 | 1.22 | 160.322 | 189.48 | 349.802 |  | 233.0817 | 274.2927 | 507.3744 | 47.6%
on 5-13-2015 | FY15 | 8.5779 | 937.365 | 611.1665 | 1548.5315 |  | 1396.6738 | 907.9504 | 2304.6243 | 49%
| FY16 | 7.9205 | 940.3859 | 881.334 | 1821.7199 |  | 1422.8038 | 1333.4583 | 2756.2622 | 51.3%
| Total | 17.7185 | 2038.0729 | 1681.9805 | 3720.0534 |  | 3052.5594 | 2515.7015 | 5568.2608
Dfference from original estimate |  | -11.5485 | -1263.4559 | -645.9325 | -1909.3884 | 0 | -1719.101 | -1014.3955 | -2919.2498
FY14 Spent
FY15 YTD Spent
Legend
Waiting on finalized estimate
Completed estimate
2334.9489
227.66
2107.2889
Note on B27: Kelly Hanifan: use 1.75% for raises in FY16: - 3% divided by 12 months times 7 - raises start in March (7 mos thru Sep) - 0.03 divided by 12 = 0.0025 times 7 = 0.0175
Note on I46: Kelly Hanifan: HV Gun - only >$50K ($125 total for the gun)

## MSSURV
MSSURV
Tasks |  |  | Labor - Hours
| Total Hrs | PW | SR STAFF | ADMIN | SCIENTIST | COMP SCI | MECH ENG - PW | MECH ENG | ELEC DES | MECH DES | ELEC TECH | MECH TECH - PW | MECH TECH | SKLLD TRADE
Network: ~20 stations (10 existing)
Layout | 28 | 0.7 |  |  |  |  | 0.4 | 16 |  |  |  | 0.3 | 12
Drilling / setting new monuments | 32 | 0.8 |  |  |  |  | 0.8 | 32 |  |  |  | 0 | 0
Tracker Obs | 84 | 2.1 |  |  |  |  | 1.2 | 48 |  |  |  | 0.9 | 36
Levels | 28 | 0.7 |  |  |  |  | 0.4 | 16 |  |  |  | 0.3 | 12
0
Pase I / section 1: 160kev (Up to A1 / A2) | 0
Support layout | 12 | 0.3 |  |  |  |  | 0.2 | 8 |  |  |  | 0.1 | 4
Support alignment | 36 | 0.9 |  |  |  |  | 0.6 | 24 |  |  |  | 0.3 | 12
Component alignment (3 girders, 2 guns) | 120 | 3 |  |  |  |  | 2 | 80 |  |  |  | 1 | 40
0
Pase I / section 2: 500kev (Master slit, chopper, bnchr, dump) | 0
Support layout | 24 | 0.6 |  |  |  |  | 0.4 | 16 |  |  |  | 0.2 | 8
Support alignment | 48 | 1.2 |  |  |  |  | 0.8 | 32 |  |  |  | 0.4 | 16
Component alignment (2 girders, cavities,dump etc.) | 192 | 4.8 |  |  |  |  | 3.2 | 128 |  |  |  | 1.6 | 64
0
Pase I / section 3: SRF | 0
Support layout / alignment | 20 | 0.5 |  |  |  |  | 0.4 | 16 |  |  |  | 0.1 | 4
1/4 cryomodule fiduc | 24 | 0.6 |  |  |  |  | 0.4 | 16 |  |  |  | 0.2 | 8
1/4 cryomodule align | 48 | 1.2 |  |  |  |  | 0.8 | 32 |  |  |  | 0.4 | 16
0
Pase I / section 4: HD-Ice | 0
Support layout | 10 | 0.25 |  |  |  |  | 0.2 | 8 |  |  |  | 0.05 | 2
Support alignment | 36 | 0.9 |  |  |  |  | 0.6 | 24 |  |  |  | 0.3 | 12
Component alignment (2 quads, harp, 2 BPMs, Fy cup) | 96 | 2.4 |  |  |  |  | 1.6 | 64 |  |  |  | 0.8 | 32
Target alignment | 48 | 1.2 |  |  |  |  | 0.8 | 32 |  |  |  | 0.4 | 16
Total Hrs | 886 | 22.15
FTE | 0.50341 | [5 empty] | 14.8 | 592 |  |  |  | 7.35 | 294
FY16 Raise rate | 1.0175
FY15 Labor: | [6 empty] | 53.353 |  |  |  |  | 14.757
1 PW of Mech Eng III | 3.605 | 14.8 | 53.353
1 PW of Mech Tech III | 1.994 | 7.35 | 14.757
68.11
Procurements |  |  | 0
FY15 Total Direct |  |  | 68.11
FY16 Labor:
1 PW of Mech Eng III | 3.6681 | 14.8 | 54.2877
1 PW of Mech Tech III | 2.0289 | 7.35 | 14.9124
69.2001
Procurements |  |  | 0
FY16 Total Direct |  |  | 69.2001
Note on H36: Kelly Hanifan: used Mech Eng III
Note on M36: Kelly Hanifan: Used Mech Tech III

## EESICS rev1
X | EESIC System Instrumentation ONLY
|  | UNITS on HAND | NEW UNITS | Total Units | Labor (MW)
| System |  |  |  | EE | ET | AC | CS | EF | EL | Total Labor | Materials | Misc Exp |  | Start | Finish | Notes
X | Valve Instrumentation | 5 | 5 | 10 | 0.1 | 3 | 1 | 1 | 2 |  |  | 12000
| Viewer Instrumentation + New Assemblies | 8 | 6 | 14 | 1 | 7 | 2 | 2 | 3 |  |  | 60000
| Ion Pump | 20 |  | 20
| Ion Pump Supplies * (JH Versions) | ? | ? | 20 |  | 2 |  |  | 3
X | **DP Stations | 2 |  | 2 | 0.2 | 0.5 | 0.5 | 0.5 |  |  |  | 2000
X | Convectron Guages | 0 | 4 | 4 | 0.5 | 1 | 0.2 | 0.2 | 0.5 |  |  | 1500
X | Dump Instrumentation | 2 | 1 | 3 | 0.2 | 2 | 1 | 1 | 1 |  |  | 4000
X | Insertable Cup Instrumentation | 2 | 1 | 3 | 0.2 | 2 | 1 | 1 | 1 |  |  | 4000
X | Aperture Instrumentation | 5 | 0 | 5 |  |  |  |  | 2 |  |  | 2000
X | Picometers with Swiching System | 4 | 2 | 6 |  | 2 | 2 | 2 |  |  |  | 10000
X | I to V's | ? | ? | ?
| Stripline BPMs | 0 | 17 | 17 | 4 | 8 | 3 | 2 | 17 |  |  | 102000
| Harps | 1 | 1 | 2 |  | 2 | 1 | 1 | 1 |  |  | 14000
| Yao cavity | ? | ? | 1
X | BCM cavity | ? | ? | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 8000
IOCs
Network (Support Network Cameras?)
60 Hz timing system (SCAM?)
BLMs (is this SSGs territory?)
| Instrumentation Racks | [5 empty] | 0.2 |  |  | 2
FTEs
| Total Labor (weeks) |  |  |  | 7.2 | 30.5 | 12.9 | 11.7 | 31.5 | 2 | 2.1773
| FY15 AWP weekly rate w/ fringe |  |  |  | 3144 | 1999 | 2156 | 3023 | 1895 | 1668
| Weekly rate w/ fringe |  |  |  | 2768.8 | 1690 | 2210.4 | 2768.8 | 1690 | 1690
| Hourly rate w/fringe* |  |  |  | 69.22 | 42.25 | 55.26 | 69.22 | 42.25 | 42.25
| Labor w/fringe (w/o overhead) & Materials |  |  |  | 19935.36 | 51545 | 28514.16 | 32394.96 | 53235 | 3380 |  | 219.5 | 0 | 0 |  |  | 189223.98
| Labor w/fringe (w/o overhead) & Materials |  |  |  | 22639 | 60978 | 27816 | 35366 | 59679 | 3336 | 209.814
| G&A (46%)* |  |  |  | 9170.2656 | 23710.7 | 13116.5136 | 14901.6816 | 24488.1 | 1554.8 |  | 100.97 | 0 | 0 |  |  | 87043.0308
| JLAB Total |  |  |  | 29105.6256 | 75255.7 | 41630.6736 | 47296.6416 | 77723.1 | 4934.8 |  | 320.47 | 0 | 0 |  |  | 276267.0108
| Total* | [15 empty] | 276267.0108
EE: Electrical Engineer
ET: Electronic Technician
AC: Associate engineer/designer/coordinator
CS: Computer Scientist
EF: Electronic Fabrication
EL: Electrician
* Subject to change

## EESICS
EESICS
Tasks |  | Labor - Hours
| Total Hrs | SR STAFF | ADMIN | SCIENTIST | COMP SCI | ENG-PW | ENG | ELEC DES | MECH DES | ELEC TECH | Mech Tech - PW | MECH TECH | SKLLD TRADE
Beam Position Monitors | 360 |  |  |  |  | 3 | 120 |  |  |  | 6 | 240 |  | let's imagine 17 stripline BPMs
Vacuum Valve Controls | 120 |  |  |  |  | 1 | 40 |  |  |  | 2 | 80 |  | 10 valves
Convectron Gauge | 140 |  |  |  |  | 1 | 40 |  |  |  | 2.5 | 100 |  | what is convectron gauge used for?
Cold Cathode Gauge | 96 |  |  |  |  | 0.8 | 32 |  |  |  | 1.6 | 64 |  | What is cold cathode gauge used for?
Viewer | 248 |  |  |  |  | 1 | 40 |  |  |  | 5.2 | 208 |  | 14 viewers
ION Pump | 320 |  |  |  |  | 3 | 120 |  |  |  | 5 | 200 |  | we have many many ion pumps available, and John H. will build his UHV ion pump supplies, but we need them cabled up
Insertable Pcup | 8 |  |  |  |  | 0 | 0 |  |  |  | 0.2 | 8 |  | 3 insertable cups
Aperature | 56 |  |  |  |  | 0.4 | 16 |  |  |  | 1 | 40 |  | 5 apertures
Insertable Cup | 64 |  |  |  |  | 0.4 | 16 |  |  |  | 1.2 | 48 |  | mentioned above, 3 insertable cups
Fast Valve | 48 |  |  |  |  | 0.2 | 8 |  |  |  | 1 | 40 |  | no fast valve, we can't afford it, and the beamline is too short to do much good
1/4 cryo | 0 |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
DP | 48 |  |  |  |  | 0.2 | 8 |  |  |  | 1 | 40
nA Cavity BPMs | 120 |  |  |  |  | 1 | 40 |  |  |  | 2 | 80 |  | We decided to NOT use the nA cavity BPMs
Harp | 8 |  |  |  |  | 0 | 0 |  |  |  | 0.2 | 8 |  | 2 harps
Total Hrs | 1636
[7 empty] | Labor/wk |  |  |  |  | Labor/wk |  | can you add BCM, and yao cavity?
FY15 Labor Total | 88.56 |  |  |  |  | 37.731 | 3.144 | FY15 |  |  | 50.829 | 1.759 | FY15
FY16 Labor Total | 90.113 |  |  |  |  | 38.3882 | 3.199 | FY16 |  |  | 51.7247 | 1.7898 | FY16
FTE | 0.92955 |  |  |  |  | 12 | 480 |  |  |  | 28.9 | 1156
FY16 Raise rate | 1.0175
Combined TOTAL
|  |  |  | 10 | valves |  |  | how many manual/pneumatic |  |  |  |  | how many 2.75" vs 4.5"?
|  |  |  | 14 | viewers
|  |  |  | 17 | ion pumps
|  |  |  | 16 | ion pump supplies
|  |  |  | 2 | differential pumps (these will have ion pumps too, epics readable?)
|  |  |  | 3 | dumps
|  |  |  | 3 | insertable cups
|  |  |  | 5 | apertures
|  |  |  | 6 | picommeters (reading 4 apertures plus default cup or dump, switch to go between cups and dumps)
|  |  |  | 17 | stripline BPMs
|  |  |  | 2 | harps
|  |  |  | 1 | yao cavity
|  |  |  | 1 | BCM cavity
|  |  |  | 1 | Brock cavity
YAG viewers could replace harps?
|  |  |  | 98 | Total

## EESRFS
UITF
| FTEs | SE/MN | EE/CS | ET | ED | PH | Total Weeks | Labor | Materials | Shipping | Travel | Total
Laser |  | 1.8 | 14.4 | 8.4 | 4 | 0 | 28.6 | 92480 | 52500 | 0 | 0 | 210221
Choppers |  | 1.6 | 17 | 13.2 | 6 | 0 | 37.8 | 119160 | 77000 | 0 | 0 | 284432
Buncher |  | 1.4 | 10 | 8.2 | 6 | 0 | 25.6 | 80560 | 12000 | 0 |  | 134212
Quarter |  | 6.2 | 29 | 34 | 16.4 | 0 | 85.6 | 267800 | 111000 | 0 | 0 | 549260
Total | 4.0364 | 11 | 70.4 | 63.8 | 32.4 | 0 | 177.6 | 560000 | 252500 | 0 | 0 | 1178125
FY15 AWP total |  | 53.301 | 220.31 | 126.755 | 67.879 |  |  | 468.245
FY15 Weekly labor rate w/ fringe |  | 4.846 | 3.129 | 1.987 | 2.095
FY16 AWP total |  | 54.2389 | 224.1365 | 128.9891 | 69.0659 |  |  | 476.4303
FY16 Weekly labor rate w/ fringe | 1.0175 | 4.9308 | 3.1838 | 2.0218 | 2.1317
Procurements:
[5 empty] | Supplies and Materials |  |  | 252.5
[7 empty] | Direct Total | 1197.1753
0
DRAFT Subject to Change

## EESDCP 4-22-15
EESDCP
Tasks |  | Labor - Hours
| Total Hrs | SR STAFF | ADMIN | SCIENTIST | COMP SCI | ELEC ENG | ELEC DES | MECH DES | ELEC TECH | MECH TECH | SKLLD TRADE
Pulling and terminating cables | 240 | [7 empty] | 240
HCO | 88 |  |  |  |  | 8 |  |  | 80
Spec/procure cable/lugs | 32 |  |  |  |  | 16 | 16
0
Spec/procure/build? 50A PSU | 0 |  |  |  |  | 24-120* | 16* |  | 80* |  |  | We will assume we need this, but Joe Grames might tell us later that he prefers to use CEBAF-style 5 MeV magnet, which runs on trim card, I believe
install and test 50A PSU | 80 |  |  |  |  | 40 |  |  | 40
0
procure 30+ 10A trim cards (turnkey?) | 64 |  |  |  |  | 40 | 24
test and calibrate 10A trim cards | 80 | [7 empty] | 80
0
0
Total Hrs
Hours | 584 |  |  |  |  | 104 | 40 | 0 | 440
PW | 14.6 |  |  |  |  | 2.6 | 1 | 0 | 11
FTEs | 0.33182
FY15 Weekly rate w/ fringe | [5 empty] | 3.26 | 2.28 |  | 1.9
FY15 Total Direct Labor $ | 31.657 |  |  |  |  | 8.476 | 2.28 |  | 20.901
FY16 Weekly rate w/ fringe | 1.0175 |  |  |  |  | 3.3171 | 2.3199 |  | 1.9333
FY16 Total Direct Labor $ | 32.21 |  |  |  |  | 8.6243 | 2.3199 |  | 21.2658
| Procurements |  |  |  |  | *build in house will save procurement $, but will take longer
|  |  | each | # to buy | total
| 32 trim cards |  | 3.5 | 32 | 112
| 32 trim cards |  | 3.5 | 0 | 0
| 2 50A/50V? PSU's |  | 10 | 2 | 20
| cables |  | 1.5 | 5 | 7.5 | ~70 feet average run? 60 channels = 4200' required, 5x1000' spools? $1.5/ft?
| lugs |  |  |  | 5
144.5
Parts count from Matt
Combined TOTAL
approx current
|  |  | 4 | skew quads |  | < 1 Amp
|  |  | 18 | corrector pairs |  | < 1 Amp |  | that's 36 independent current cards total, for the correctors
|  |  | 7 | solenoids |  | < 10 Amp
|  |  | 1 | 15 degree dipole |  | < 10 Amp |  | don't know if this is a "card" or stand alone supply
|  |  | 1 | ~ 30 degree dipole for spectrometer |  | ? |  | don't know if this is a "card" or stand alone supply
|  |  | 11 | quads |  | < 10 Amp
|  |  | 2 | dipoles |  | need independent ~ 50A current supplies

## EESSAF-ODH 4-22-15
Title | UITF ODH System | 2015-03-30
Funding FY | Fiscal year Funding
AWP | Associated AWP Plan
Deliverable | What is final product
Primary Customer | Who receives the benefit
Primary Contact(s) | Contact
Project Code(s) | Project Code | UITFBL
Project Manager(s) | Project Manager | Matt Poelker
SSG Principal | SSG Project Manager | Dan Sexton
Required Project Complete Date | 0
Start Date (Calculated) | 2015-07-01
End Date (Calculated) | 2015-10-30
G&A Rate (set to 0 if G&A not used) | 0%
Project Cost Summary |  |  |  |  | FTE
Labor Hours | 536 | hrs | 13.4 | person weeks | 0.30455
Labor $ | 26.962 |  | 26.962
Procurements and Expenses $ | 10666.5 |  | 10.6665
Subtotal | 10693.462 |  | 10.6665
G&A | 0 |  | 0
Total | 10693.462 |  | 10.6935
Support Costs
Labor Hours/yr | 0 | hrs/yr | 0 | person weeks/yr
Labor $/yr | #REF! |  | #REF!
Procurements and Expenses $/yr | 0 |  | 0
Subtotal/yr | #REF! |  | #REF!
G&A/yr | #REF! |  | #REF!
Total/yr | #REF! |  | #REF!
Project Start (RO) | 0 | RO = Start Date
[5 empty] | FY16 Total Labor w/ Fringe | 28.9837 |  |  |  |  | 8.1347 |  |  |  | 1.8017 |  | 12.1084 |  | 6.9389
[5 empty] | FY15 Total Labor w/ Fringe | 26.962 |  |  |  |  | 7.568 |  |  |  | 1.676 |  | 11.262 |  | 6.456
Note; This section is for non-recurring costs associated with completion of a project |  |  |  | 0 | Total Labor Hrs | 536 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 32 | 0 | 232 | 0 | 176 | 0 | 0 | 536 | Total Labor $ | #REF! | 10666.5 | 0 | 0 | Total Exp $/yr | 10666.5
[5 empty] | FY15 Labor Rate/week | [5 empty] | 3.153 |  |  |  | 2.095 |  | 1.942 |  | 1.467
[5 empty] | FY16 Labor Rate/week | 1.075 |  |  |  |  | 3.3895 |  |  |  | 2.2521 |  | 2.0877 |  | 1.577
Project Costs |  |  |  |  | Total Labor Wks | 13.4 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0.8 | 0 | 5.8 | 0 | 4.4 | 0 | 0 | 13.4 | Total Labor k$ | #REF! | 10.6665 | 0 | 0 | Total Exp k$/yr | 10.6665
Task ID | Tasks | Start Date | End Date | Duration, days | Predecessor |  | Labor - Hours | [17 empty] | Procurements and Expenses | [5 empty] | Notes
|  |  |  | 0 | Task ID(s) | Total Hrs | SR STAFF | ADMIN | SCIENTIST | COMP SCI | ELEC ENG | MECH ENG | PLANT ENG | OFFICE | ELEC DES | MECH DES | ELEC TECH | MECH TECH | SKLLD TRADE | STUDENT | Other | Total Hrs |  | Labor Cost | Procurements - $ | Expenses - $ | Travel - $ | Other - $ | Total Proc & Expenses | Tasks
0 | Management Oversight |  |  | 0 |  | 8 |  |  |  |  | 8 | [10 empty] | 8 |  | #REF! |  |  |  |  | 0 | Management Oversight
1 | Develop Architecture |  |  | 0 |  | 8 |  |  |  |  | 8 | [10 empty] | 8 |  | #REF! |  |  |  |  | 0 | Develop Architecture
2 | Change Control/ Design Review Process |  |  | 0 |  | 2 |  |  |  |  | 2 | [10 empty] | 2 |  | #REF! |  |  |  |  | 0 | Change Control/ Design Review Process
3 | Develop drawings |  |  | 0 |  | 32 |  |  |  |  | 8 |  |  |  | 16 |  | 8 |  |  |  |  | 32 |  | #REF! |  |  |  |  | 0 | Develop drawings
4 | Specify Components |  |  | 0 |  | 8 |  |  |  |  | 8 | [10 empty] | 8 |  | #REF! | 6665.5 |  |  |  | 6665.5 | Specify Components
5 | Process procurements |  |  | 0 |  | 16 |  |  |  |  | 8 | [5 empty] | 8 |  |  |  |  | 16 |  | #REF! |  |  |  |  | 0 | Process procurements
6 | Develop workplan / hazard analysis |  |  | 0 |  | 12 |  |  |  |  | 8 | [5 empty] | 4 |  |  |  |  | 12 |  | #REF! |  |  |  |  | 0 | Develop workplan / hazard analysis
7 | Remove existing hardware (if required) |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Remove existing hardware (if required)
8 | Install new hardware components |  |  | 0 |  | 80 | [10 empty] | 40 |  | 40 |  |  | 80 |  | #REF! |  |  |  |  | 0 | Install new hardware components
9 | Install new network components |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Install new network components
10 | Cable/fiber installation |  |  | 0 |  | 56 | [10 empty] | 40 |  | 16 |  |  | 56 |  | #REF! |  |  |  |  | 0 | Cable/fiber installation
11 | Conduit/tray installation |  |  | 0 |  | 120 | [10 empty] | 40 |  | 80 |  |  | 120 |  | #REF! | 4001 |  |  |  | 4001 | Conduit/tray installation
12 | Fabricate new chassis/interfaces/PCBs |  |  | 0 |  | 0 | [10 empty] | 0 |  |  |  |  | 0 |  | #REF! |  |  |  |  | 0 | Fabricate new chassis/interfaces/PCBs
13 | Rack installation / wiring |  |  | 0 |  | 80 | [10 empty] | 40 |  | 40 |  |  | 80 |  | #REF! |  |  |  |  | 0 | Rack installation / wiring
14 | Test integrity/continuity/QA |  |  | 0 |  | 40 |  |  |  |  | 8 | [5 empty] | 32 |  |  |  |  | 40 |  | #REF! |  |  |  |  | 0 | Test integrity/continuity/QA
15 | Develop logic spec |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Develop logic spec
16 | Develop logic |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Develop logic
17 | Develop test procedures |  |  | 0 |  | 10 |  |  |  |  | 10 | [10 empty] | 10 |  | #REF! |  |  |  |  | 0 | Develop test procedures
18 | Develop HMI |  |  | 0 |  | 16 | [10 empty] | 16 |  |  |  |  | 16 |  | #REF! |  |  |  |  | 0 | Develop HMI
19 | System test |  |  | 0 |  | 8 |  |  |  |  | 4 | [5 empty] | 4 |  |  |  |  | 8 |  | #REF! |  |  |  |  | 0 | System test
20 | System Certification |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | System Certification
21 | Final Documentation |  |  | 0 |  | 16 | [8 empty] | 16 | [6 empty] | 16 |  | #REF! |  |  |  |  | 0 | Final Documentation
22 | Training |  |  | 0 |  | 24 |  |  |  |  | 24 | [10 empty] | 24 |  | #REF! |  |  |  |  | 0 | Training
23 |  |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | 0
24 | Software???? | [28 empty] | Software????
25 | [29 empty] | 0
26 | [29 empty] | 0
27 | [29 empty] | 0
28
29
30
31
32
26 | To add lines - Copy this line and insert | 2009-09-30 | 2009-09-30 | 1 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | To add lines - Copy this line and insert
Note: This section is for incremental recurring costs anticipated as a result of this project |  |  |  |  | Total Labor Hrs/yr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Labor $/yr | #REF! | 0 | 0 | 0 | Total Exp $ | 0
Continuing Costs | Per Facility |  |  |  | Total Labor Wks/yr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Labor k$/yr | #REF! | 0 | 0 | 0 | Total Exp k$ | 0
Task ID | Tasks | Start Date | End Date | Duration, days | Predecessor |  | Labor - Hours | [17 empty] | Procurements and Expenses | [5 empty] | Notes
|  | 0 | 2011-09-30 | 29142 | Task ID(s) | Total Hrs | SR STAFF | ADMIN | SCIENTIST | COMP SCI | ELEC ENG | MECH ENG | PLANT ENG | OFFICE | ELEC DES | MECH DES | ELEC TECH | MECH TECH | SKLLD TRADE | STUDENT | Other | Total Hrs |  | Labor Cost | Procurements - $ | Expenses - $ | Travel - $ | Other - $ | Total Proc & Expenses | Tasks
1 | Management |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Management
2 | Planning |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Planning
3 | PM |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | PM
4 | Metrics/Tracking |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Metrics/Tracking
5 | Oversight |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Oversight
6 | Operations Training |  |  | 0 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | Operations Training
1 | To add lines - Copy this line and insert | 2010-08-01 | 2011-09-30 | 292 |  | 0 | [15 empty] | 0 |  | #REF! |  |  |  |  | 0 | To add lines - Copy this line and insert
[32 empty] | HOLIDAY | OBSERVED | DAY
FY11
[32 empty] | Thanksgiving Day | 2010-11-25 | Thursday
[32 empty] | Day After Thanksgiving | 2010-11-26 | Friday
[32 empty] | Christmas Eve | 2010-12-24 | Friday
[32 empty] | Christmas Day | 2010-12-27 | Monday
[32 empty] | Shutdown Day* | 2010-12-28 | Tuesday
[32 empty] | Shutdown Day* | 2010-12-29 | Wednesday
[32 empty] | Shutdown Day* | 2010-12-30 | Thursday
[32 empty] | New Year's Eve | 2010-12-30 | Friday
[32 empty] | New Year's Day | 2010-12-31 | Thursday
[32 empty] | MLK Day | 2011-01-17 | Monday
[32 empty] | President's Day | 2011-02-21 | Monday
[32 empty] | Memorial Day | 2011-05-30 | Monday
[32 empty] | Independence Day | 2011-07-04 | Monday
[32 empty] | Labor Day | 2011-09-05 | Monday
FY12
[32 empty] | Thanksgiving Day | 2011-11-24 | Thursday
[32 empty] | Day After Thanksgiving | 2011-11-25 | Friday
[32 empty] | Christmas Eve | 2011-12-23 | Friday
[32 empty] | Christmas Day | 2011-12-26 | Monday
[32 empty] | Shutdown Day* | 2011-12-27 | Tuesday
[32 empty] | Shutdown Day* | 2011-12-28 | Wednesday
[32 empty] | New Year's Eve | 2011-12-29 | Thursday
[32 empty] | New Year's Day | 2011-12-30 | Friday
[32 empty] | MLK Day | 2012-01-16 | Monday
[32 empty] | President's Day | 2012-02-20 | Monday
[32 empty] | Memorial Day | 2012-05-28 | Monday
[32 empty] | Independence Day | 2012-07-04 | Wednesday
Formulas:
Duration, days = NETWORKDAYS([UITFBL],[End Date],AS140:AS153)
UITFBL = MIN([UITFBL, row below]:C90)
End Date = MAX([End Date, row below]:D102)
Note on B43: See the Generic Activities List for suggested tasks
Workscope :
Define workscope. This is cut and pasted in to AWP worksheet.
Justificaiton/Drivers/Requirements:
Why is this project necessary? Thsi will eb cut and pasted in to AWP worksheet
Deliverables:
What is the final end product or outcome? This will be cut and pasted in to the AWP worksheet.

## EESSAF-PSS
EESSAF
Tasks |  | Labor - Hours
| Total Hrs | SR STAFF | ADMIN | SCIENTIST | COMP SCI | ENG | ELEC DES | MECH DES | ELEC TECH | MECH TECH | SKLLD TRADE
Management Oversight | 24 |  |  |  |  | 24
Develop Architecture | 56 |  |  |  |  | 56
Change Control/ Design Review Process | 80 |  |  |  |  | 80
Develop drawings | 224 |  |  |  |  | 56 | 48 |  | 120
Specify Components | 160 |  |  |  |  | 80 |  |  | 80
Process procurements | 64 |  |  |  |  | 16 |  |  | 48
Develop workplan / hazard analysis | 24 |  |  |  |  | 8 |  |  | 16
Remove existing hardware (if required) | 0
Install new hardware components | 456 | [7 empty] | 376 |  | 80
Install new network components | 32 | [7 empty] | 32
Cable/fiber installation | 240 | [7 empty] | 224 |  | 16
Conduit/tray installation | 240 | [7 empty] | 40 |  | 200
Fabricate new chassis/interfaces/PCBs | 230 | [7 empty] | 200 |  | 30
Rack installation / wiring | 120 | [7 empty] | 120
Test integrity/continuity/QA | 40 |  |  |  |  | 8 |  |  | 32
Develop logic spec | 80 |  |  |  |  | 80
Develop logic | 24 |  |  |  |  | 24
Develop test procedures | 80 |  |  |  |  | 80
Develop HMI | 160 |  |  |  |  | 80 |  |  | 80
System test | 136 |  |  |  |  | 40 |  |  | 96
System Certification | 32 |  |  |  |  | 16 |  |  | 16
Final Documentation | 200 |  |  |  |  | 64 | 72 |  | 64
Training | 24 |  |  |  |  | 24
Total Hrs | 2726 |  |  |  |  | 736 | 120 |  | 1544 |  | 326
Personweeks | 68.15 |  |  |  |  | 18.4 | 3 |  | 38.6 |  | 8.15
FTE | 1.5489 |  |  |  |  | 0.41818 | 0.068182 |  | 0.87727 |  | 0.18523
FY15 Labor Rate/week | [5 empty] | 3.153 | 2.095 |  | 1.942 |  | 1.467
FY16 Labor Rate/week | 1.0175 |  |  |  |  | 3.2082 | 2.1317 |  | 1.976 |  | 1.4927
FY16 Total Direct Labor with Fringe | 153.8638 |  |  |  |  | 59.0305 | 6.395 |  | 76.273 |  | 12.1653
FY15Total Direct Labor with Fringe | 151.285 |  |  |  |  | 58.019 | 6.285 |  | 74.949 |  | 12.032
Procurements | 35 | We already have CARMS and CARM controllers
Total Direct | 0

## MSCRYO
MSCRYO
Tasks |  | Labor - Hours
| Total Hrs | SR STAFF | ADMIN | SCIENTIST | ELEC ENG | MECH ENG | PROCESS ENG | MECH DES | ELEC TECH | MECH TECH | SKLLD TRADE
Cryo to 1/4 and HD Ice | 4680 |  |  |  | 120 | 600 | 40 | 800 | 720 | 2400
Total Hrs | 4680
PW | 117 |  |  |  |  | 15 | 1 | 20 | 18 | 60
$/week |  |  |  |  | 2.479 | 2.49 | 2.479 | 2.073 | 1.985 | 1.843
Total Labor $ | 235.016 |  |  |  | 7.438 | 37.347 | 2.479 | 41.467 | 35.727 | 110.558
Total Procurement $ | 48
Total Direct | 283.016
2.66 FTE
FY15 Scope:
[5 empty] | Provide LHe and controls to the 1/4 cryomodule at the upgrade injector test facility: 86.5 PW, or 2 FTE | [6 empty] | Plus some extra cost associated with heat exchanger in transfer can
FY16 Scope:
22.5 PW or .5 FTE
$42.5K procurements
Hookup HDICE
LABOR:
1.0175
| FY15 Weekly rate w/ fringe | FY16 Weekly rate w/ fringe | Resource Type | Org | Name | PW | FTEs | FY15 Total w/ Fringe | FY16 Total w/ Fringe
| 2.437 | 2.4796 | MD A/C | MSCRYO |  | 6.5 | 0.148 | 15.842 | 16.1177
| 2.49 | 2.5336 | ME II | MSCRYO |  | 4.5 | 0.102 | 11.207 | 11.4011
| 2.445 | 2.4878 | MT A/C | MSCRYO |  | 10 | 0.227 | 24.452 | 24.8779
| 1.24 | 1.2617 | MT A/C | MSCRYO |  | 54 | 1.227 | 66.934 | 68.1318
| 2.786 | 2.8348 | EE II | MSCRYO |  | 1.5 | 0.034 | 4.179 | 4.2521
| 1.972 | 2.0065 | ET Sr. | MSCRYO |  | 10 | 0.227 | 19.72 | 20.0651
[5 empty] | 86.5 | 1.965 | 1.965 | 142.334 | 144.8457
PROCUREMENTS:
|  |  |  | 1/4 CM transfer line |  |  |  | 48
[6 empty] | Direct Total | 49.965

## MSMECH
1.0175
FY15 LABOR $/PW | FY16 LABOR $/PW | Resource Type | Org | Name | PW | FTEs | FY15 AWP Total w/ Fringe | FY15 AWP Total w/ Fringe
2.148 | 2.1856 | MECH DES: Sr. Tech | MSMECH | Shaun Gregory | 6 | 0.13636 | 12.888 | 13.1135 | Shaun moves 3rd week of May to work on FRIB, replaced by Karl Smith per 5-6-15 email from Matt Poelker
3.697 | 3.7617 | ELEC ENG: Staff Eng III | MSMECH | Joe Gubeli | 11 | 0.25 | 40.672 | 41.3787
2.389 | 2.4308 | MECH DES: Assoc/Coord Design | MSMECH | Paul Hansen | 11 | 0.25 | 26.281 | 26.7389
3.435 | 3.4951 | MECH ENG: Staff Eng III | MSMECH | Tommy Hiatt | 11 | 0.25 | 37.783 | 38.4462
2.389 | 2.4308 | MECH DES: Assoc/Coord Design | MSMECH | Chuck Hutton | 11 | 0.25 | 26.281 | 26.7389
3.551 | 3.6131 | MECH ENG: Eng Support Mgr. | MSMECH | Dannie Machie | 11 | 0.25 | 39.062 | 39.7446
2.389 | 2.4308 | MECH DES: Assoc/Coord Design | MSMECH | Karl Smith | 5 | 0.11364 | 11.946 | 12.154
[5 empty] | 66 | 1.5 | 194.913 | 198.3148
PROCUREMENTS:
|  |  |  | Supplies and Materials |  |  | 0
[6 empty] | Direct Total | 194.913

## ACCCIS
CIS | [8 empty] | 1.0175
Tasks |  |  | Labor - WEEKS |  |  |  |  | FY15 Labor $/ | FY16 Labor $/ | Resource | FY15 AWP | FY16 AWP
| FTEs | Total Wks | Scientist 3 | EE3 | A/C2 |  | Name | Week | Week | Type | Total | Total
Build girders for keV beamline | 0.045455 | 2 |  |  | 2 |  | Phil Adderley | 2.708 | 2.7554 | ELEC TECH: Sen Assoc/Coord | 59.572 | 5.5108
Assemble keV beamline | 0.18182 | 8 |  |  | 8 |  | Phil Adderley | 2.708 | 2.7554 |  |  | 22.0431
Build girders for MeV beamline | 0.045455 | 2 |  |  | 2 |  | Phil Adderley | 2.708 | 2.7554 |  |  | 5.5108
Assemble MeV beamline | 0.18182 | 8 |  |  | 8 |  | Phil Adderley | 2.708 | 2.7554 |  |  | 22.0431
HV studies toward reliable 350kV gun | 0.27273 | 12 | 12 |  |  |  | Carlos Hernandez-Garcia | 3.482 | 3.5429 | SCI: Staff Sci III | 55.719 | 42.5152
Assemble 350kV gun and bakeout | 0.045455 | 2 |  |  | 2 |  | Phil Adderley | 2.708 | 2.7554 |  |  | 5.5108
Commission 400kV gun power supply | 0.045455 | 2 |  | 2 |  |  | John Hansknecht | 3.738 | 3.8034 | ELEC ENG: Staff Eng III | 44.854 | 7.6068
Commission gun at 350kV | 0.090909 | 4 | 4 |  |  |  | Carlos Hernandez-Garcia | 3.482 | 3.5429 |  |  | 14.1717
Drive laser in clean room | 0.090909 | 4 |  | 4 |  |  | John Hansknecht | 3.738 | 3.8034 |  |  | 15.2137
Deliver light to cave | 0.045455 | 2 |  | 2 |  |  | John Hansknecht | 3.738 | 3.8034 |  |  | 7.6068
construct laser table near beamline | 0.090909 | 4 |  | 4 |  |  | John Hansknecht | 3.738 | 3.8034 |  |  | 15.2137
350kV beam to cup upstream of 1/4 | 0.090909 | 4 | 4 |  |  |  | Joe Grames | 3.482 | 3.5429 | SCI: Staff Sci III | 62.684 | 14.1717
5MeV beam to cup upstream of HDIce | 0.090909 | 4 | 4 |  |  |  | Joe Grames | 3.482 | 3.5429 |  |  | 14.1717
Optics modeling | 0.22727 | 10 | 10 |  |  |  | Joe Grames | 3.482 | 3.5429 |  |  | 35.4294
[11 empty] | 222.829 | 226.7194
Total FTEs | 1.5455 | 68 | 34 | 12 | 22
Procurement costs
|  | needed | in-house | to purchase | unit cost | total cost
valves |  | 8 | 4 | 4 | 15 | 60
viewers |  | 14 | 6 | 8 | 2 | 16
ion pumps |  | 20 | 16 | 4 | 2 | 8
ion pump supplies |  | 20 | 20 |  | 4 | 4
differential pumps |  | 3 | 2 | 1 | 4 | 4
dumps |  | 3 | 2 | 1 | 4 | 4
insertable cups |  | 4 | 2 | 2 | 2 | 4
apertures |  | 5 | 3 | 2 | 2 | 4
picommeters (reading 4 apertures plus default cup or dump, switch to go between cups and dumps) |  | 6 | 4 | 2 | 3 | 6
stripline BPMs |  | 17 | 0 | 17 | 2 | 42.5
harps |  | 2 | 1 | 1 | 5 | 5
yao cavity |  | 1 | 1 | 0 |  | 0
BCM cavity |  | 1 | 1 | 0 |  | 0
YAG view screens |  | 4 | 0 | 4 | 1 | 4
Haimson coils |  | 20 | 8 | 12 | 2 | 24
quads |  | 12 | 0 | 12 | 6 | 72
dipoles |  | 3 | 1 | 2 | 12 | 24
80/20 structure | [5 empty] | 20
alignment cartridges |  | 12 | 3 | 9 | 0.2 | 1.8
machine shop jobs | [5 empty] | 40
gun manipultor |  | 1 | 0 | 1 | 3 | 3
NEG flange at Y chamber |  | 1 | 1 |  |  | 0
stuff for buncher | [5 empty] | 2
gun HV supply interface | [5 empty] | 2
gun SF6 tank | [5 empty] | 30
electronics rack bases | [5 empty] | 4
Gun NEG modules on half circle |  | 4 |  |  |  | 10
[6 empty] | 330.8 |  | 0
actuals as of 5-11-15 | [5 empty] | 51.034
381.834

## SRFOPS
LABOR:
1.0175
FY15 Weekly rate w/ fringe | FY15 Weekly rate w/ fringe | Resource Type | Org | Name | PW | FTEs | FY15 Total w/ Fringe | FY16 Total w/ Fringe
2.753 | 2.8012 | ELEC TECH/AC II | SRFOPS | John Fischer | 4 | 0.091 | 11.012 | 11.2047
[5 empty] | 4 | 0.091 | 11.012 | 11.2047
PROCUREMENTS:
|  |  |  | Supplies and Materials |  |  | 0
[6 empty] | Direct Total | 22.024

## OPSSFT
LABOR:
1.0175
FY15 Weekly Rate | FY16 Weekly Rate | Resource Type | Org | Name | PW | FTEs | FY15 Total w/ Fringe | FY16 Total w/ Fringe
2.34 | 2.3809 | ELEC TECH: A/C I | OPSADM | Brad Cumbia | 5 | 0.11364 | 11.699 | 11.9047
2.768 | 2.8164 | SCSC II | OPSADM | Adam Carpenter | 5 | 0.11364 | 13.841 | 14.0822
2.957 | 3.0087 | SCSC II | OPSSFT | George Lahti | 14.6 | 0.33182 | 33.65 | 43.9277
3.365 | 3.4239 | SCSC III | OPSSFT | Scott Higgins | 14.6 | 0.33182 | 29.573 | 49.9888
3.706 | 3.7709 | SCSC III | OPSAHL | Marie Keesee | 14.6 | 0.33182 | 37.055 | 55.0545
[5 empty] | 53.8 | 1.2227 | 125.818 | 174.9579
PROCUREMENTS:
|  |  |  | Supplies and Materials |  |  | 58
[6 empty] | Direct Total | 220.873
And for software, it's pretty straightforward:
86k$ procurements for network stuff
10 weeks labor for Brad Cumbia and Adam Carpenter to install the network stuff
30 weeks labor for software support (Scott Higgins, George Lahti, and Marie Kissee)
PROCUREMENTS:
|  | Network related procurements | unit price | number | total
|  | server for soft IOCs | 6 | 1 | 6
|  | fiefdom upgrade | 16 | 1 | 16
|  | network switcher, 48 channel | 3.5 | 2 | 7
|  | console server | 2 | 2 | 4
|  | UPS | 2.5 | 2 | 5
cross point switcher?
|  | fibers from com spigot |  |  | 5
|  | IOCs type 5100 | 3 | 5 | 15
|  | monitors in control room | free | 2 | 0
|  | VME crates | 8 | 5 | 0
58

## Facilities
| 1.0175 | LABOR:
FY15 | FY16
Weekly rate w/ fringe | Weekly rate w/ fringe |  | Resource Type | Org | Name | PW | FTEs | FY15 Total w/ Fringe | FY16 Total w/ Fringe
3.133 | 3.1878 | PLANT ENG | SEII | FMF | Thomas Renzo | 17 | 0.386 | 53.262 | 54.1931
3.866 | 3.9337 | PLANT ENG | SE III | FMF | Chrstine Snetter | 1 | 0.023 | 3.866 | 3.9337
3.642 | 3.7057 | ELEC ENG | SE III | FME | Paul Powers | 2 | 0.045 | 7.283 | 7.4115
2.131 | 2.1683 | ELEC ENG | SE I | FME | Jason Willoughby | 5 | 0.114 | 10.656 | 10.8415
3.188 | 3.2438 | MECH ENG | SE II | FMM |  | 6 | 0.136 | 19.131 | 19.4627
3.571 | 3.6335 | MECH ENG | SE III | FMFS | Dave Kausch | 3 | 0.068 | 10.713 | 10.9005
[6 empty] | 34 | 0.772 | 104.911 | 106.7429
|  | PROCUREMENTS: | [9 empty] | FY16
Plant Engr (FMF) - 16 PW
[5 empty] | Supplies and Materials |  |  | 300 |  |  |  | Electrical Engr (FME) - 7 PW
Mech Engr (FMM) - 8 PW
Mech Engr (FMFS) - 3 PW
[7 empty] | Direct Total | 404.911
[10 empty] | FY15 |  |  | procurements
[10 empty] | 8.2 weeks at 80% of year |  |  | 30.97 | remove concrete wall
[13 empty] | 15.6 | stair
[13 empty] | 4.2 | penetrations
50.77
[10 empty] | LOUGHBY, JASON | ELCENG | UITFBL | FME | 6039-001 (Fringe Labor) | 2 | 2 | 0.05
[10 empty] | RENZO, THOMAS C | PLTENG | UITFBL | FMF | 6039-001 (Fringe Labor) | 18 | 162 | 4.05
[10 empty] | KAUSCH, DAVID J | MECENG | UITFBL | FMFS | 6039-001 (Fringe Labor) | 0 | 6 | 0.16
[10 empty] | MINGA, TIMOTHY D | MECENG | UITFBL | FMFS | 6039-001 (Fringe Labor) | 0 | 16 | 0.4
[10 empty] | MEIRE, LEO T | MECENG | UITFBL | FMM | 6039-001 (Fringe Labor) | 4 | 33 | 0.83
[10 empty] | CLARK, DONALD W | SKLTRD | UITFBL | FMO | 6039-001 (Fringe Labor) | 0 | 17 | 0.43
[10 empty] | STANLEY, PHILLIP C | SKLTRD | UITFBL | FMO | 6039-001 (Fringe Labor) | 0 | 13 | 0.33
[10 empty] | RENZO, THOMAS C | PLTENG | UITFIN | FMF | 6039-001 (Fringe Labor) | 0 | 78 | 1.95
8.2

## Summary Sheet
[7 empty] | FY14 G&A | FY15 G&A | FY16 G&A
[7 empty] | 1.4538 | 1.49 | 1.513
DIRECT $
FY2014: |  |  | Direct |  |  |  | with G&A (loaded)
Org | System | FTEs | Labor | Proc | Total |  | Labor | Proc | Total |  | Notes
|  | 1.22 | 160.322 | 189.48 | 349.802 |  | 233.0817 | 274.2927 | 507.3744 |  | Actuals from PSR
FY2015:
Org | System | FTEs | Labor | Proc | Total |  | Labor | Proc | Total |  | Notes
MSSURV | Survey/Alignment | 0.50341 | 68.11 | 0 | 68.11 |  | 101.4839 | 0 | 101.4839
EESICS | Inst & Control | 0.92955 | 88.56 | 98 | 186.56 |  | 131.9544 | 146.02 | 277.9744 |  | Waiting on O. Garza
EESRFS | EESRFS | 4.0364 | 468.245 | 252.5 | 720.745 |  | 697.6851 | 373.5374 | 1071.2224 | only 1 >$50K known at this time - power supplies purchased in FY15 | Need to resolve labor discrepancy with rates C. Hovater is using - off by $100K
EESDCP | DC Power | 0.33182 | 31.657 | 144.5 | 176.157 |  | 47.1689 | 215.305 | 262.4739
EESSAF | PSS | 1.5489 | 151.285 | 35 | 186.285 |  | 225.4146 | 52.15 | 277.5646 |  | Waiting on H. Robertson
EESSAF | MPS |  | 0 | 0 | 0 |  | 0 | 0 | 0
EESSAF | ODH | 0.30455 | 26.962 | 10.6665 | 37.6285 |  | 40.1734 | 15.8931 | 56.0665
MSCRYO | Cryo | 1.965 | 142.334 | 48 | 190.334 |  | 212.0777 | 71.52 | 283.5977 |  | Waiting for an update from J. Creel concerning heat exchanger
MSMECH | Mech Design | 1.5 | 194.913 | 0 | 194.913 |  | 290.4204 | 0 | 290.4204
OPSSFT | Software & Control | 1.2227 | 125.818 | 58 | 183.818 |  | 187.4688 | 86.42 | 273.8888
SRFOPS | SRF Support | 0.091 | 11.012 | 0 | 11.012 |  | 16.4079 | 0 | 16.4079
ACCCIS | Gun Group | 1.5455 | 222.829 | 381.834 | 604.663 |  | 332.0152 | 568.9327 | 900.9479 |  | Currently not charging any labor to the project - AWP has actuals
FM | Facilities | 0.772 | 104.911 | 300 | 404.911 |  | 156.3174 | 447 | 603.3174 |  | Still waiting for estimates from vendors
| Total | 14.7507 | 1636.636 | 1328.5005 | 2965.1365 |  | 2438.5876 | 1976.7781 | 4415.3657
FY2016: | 1.75% raises for FY16 is included
Org | System | FTEs | Labor | Proc | Total |  | Labor | Proc | Total |  | Notes
MSSURV | Survey/Alignment |  | 0 | 0 | 0 |  | 0 | 0 | 0
EESICS | Inst & Control |  | 0 | 0 | 0 |  | 0 | 0 | 0
EESRFS | EESRFS |  | 0 | 0 | 0 |  | 0 | 0 | 0
EESDCP | DC Power |  | 0 | 0 | 0 |  | 0 | 0 | 0
EESSAF | PSS |  | 0 | 0 | 0 |  | 0 | 0 | 0
EESSAF | MPS |  | 0 | 0 | 0 |  | 0 | 0 | 0
EESSAF | ODH |  | 0 | 0 | 0 |  | 0 | 0 | 0
MSCRYO | Cryo | 0.5 | 62.4161 | 42.5 | 104.9161 |  | 94.4356 | 64.3025 | 158.7381 |  | .5 FTE plus 42.5K
MSMECH | Mech Design |  | 0 | 0 | 0 |  | 0 | 0 | 0
OPSSFT | Software & Control |  | 0 | 0 | 0 |  | 0 | 0 | 0
SRFOPS | SRF Support |  | 0 | 0 | 0 |  | 0 | 0 | 0
ACCCIS | Gun Group |  | 0 | 0 | 0 |  | 0 | 0 | 0
FM | Facilities |  | 0 | 0 | 0 |  | 0 | 0 | 0
| Total | 0.5 | 62.4161 | 42.5 | 104.9161 |  | 94.4356 | 64.3025 | 158.7381
Original Est. provided by Hari |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total
| FY14 | 3.67 | 462.537 | 478.951 | 941.488 |  | 682.705 | 671.232 | 1353.937 | 47.6%
| FY15 | 2.5 | 312.08 | 557.097 | 869.177 |  | 465 | 830.074 | 1295.074 | 49%
| FY16 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Total | 6.17 | 774.617 | 1036.048 | 1810.665 |  | 64.3025 | 1501.306 | 2649.011
Revised Est. |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total
| FY14 | 1.22 | 160.322 | 189.48 | 349.802 |  | 233.0817 | 274.2927 | 507.3744
| FY15 | 14.7507 | 1636.636 | 1328.5005 | 2965.1365 |  | 2438.5876 | 1976.7781 | 4415.3657
| FY16 | 0.5 | 62.4161 | 42.5 | 104.9161 |  | 94.4356 | 64.3025 | 158.7381
| Total | 16.4707 | 1859.3741 | 1560.4805 | 3419.8546 |  | 2766.1049 | 2315.3733 | 5081.4782
Dfference from original estimate |  | -10.3007 | -1084.7571 | -524.4325 | -1609.1896 | 0 | -2701.8024 | -814.0673 | -2432.4672
Legend
Waiting
Complete
Note on B27: Kelly Hanifan: use 1.75% for raises in FY16: - 3% divided by 12 months times 7 - raises start in March (7 mos thru Sep) - 0.03 divided by 12 = 0.0025 times 7 = 0.0175
Note on I46: Kelly Hanifan: HV Gun - only >$50K ($125 total for the gun)

## Summary Sheet-old
DIRECT $
FY2014:
Org | System | FTEs | Labor | Proc | Total | Notes
|  | 1.22 | 160.322 | 189.48 | 349.802 | Actuals from PSR
FY2015:
Org | System | FTEs | Labor | Proc | Total | Notes
MSSURV | Survey/Alignment | 0.50341 | 68.11 | 0 | 68.11
EESICS | Inst & Control | 0.92955 | 88.56 | 98 | 186.56 | Waiting on O. Garza
EESRFS | EESRFS | 4.0364 | 468.245 | 252.5 | 720.745 | Need to resolve labor discrepancy with rates C. Hovater is using - off by $100K
EESDCP | DC Power | 0.33182 | 31.657 | 144.5 | 176.157
EESSAF | PSS |  |  |  |  | Waiting on H. Robertson
EESSAF | MPS |  |  |  | 0
EESSAF | ODH | 0.30455 | 26.962 | 10.6665 | 37.6285
MSCRYO | Cryo | 1.965 | 1.965 | 48 | 49.965 | Waiting for an update from J. Creel concerning heat exchanger
MSMECH | Mech Design | 1.5 | 194.913 | 0 | 194.913
OPSSFT | Software & Control | 1.2227 | 37.055 | 58 | 95.055
SRFOPS | SRF Support | 0.091 | 37.055 | 0 | 37.055
ACCCIS | Gun Group | #REF! | #REF! | #REF! | #REF! | Currently not charging any labor to the project - AWP has actuals
FM | Facilities | 0.772 | 104.911 | 300 | 404.911 | Still waiting for estimates from vendors
| Total | #REF! | #REF! | #REF! | #REF!
FY2016: |  |  | 3% raises still needed for FY16
Org | System | FTEs | Labor | Proc | Total | Notes
MSSURV | Survey/Alignment |  | 0 | 0 | 0
EESICS | Inst & Control |  | 0 | 0 | 0
EESRFS | EESRFS |  | 0 | 0 | 0
EESDCP | DC Power |  | 0 | 0 | 0
EESSAF | PSS |  | 0 | 0 | 0
EESSAF | MPS |  | 0 | 0 | 0
EESSAF | ODH |  | 0 | 0 | 0
MSCRYO | Cryo | 0.5 | 62.4161 | 42.5 | 104.9161 | .5 FTE plus 42.5K
MSMECH | Mech Design |  | 0 | 0 | 0
OPSSFT | Software & Control |  | 0 | 0 | 0
SRFOPS | SRF Support |  | 0 | 0 | 0
ACCCIS | Gun Group |  | 0 | 0 | 0
FM | Facilities |  | 0 | 0 | 0
| Total | 0.5 | 62.4161 | 42.5 | 104.9161
Original Est. |  | FTEs | Labor | Proc | Total
| FY14 | 3.67 | 160.322 | 189.48 | 349.802
| FY15 | 2.5 | 312.08 | 557.097 | 869.177
| FY16 | 0 | 0 | 0 | 0
| Total | 6.17 | 42.5 | 746.577 | 1218.979
Revised Est. |  | FTEs | Labor | Proc | Total
| FY14 | 1.22 | 160.322 | 189.48 | 349.802
| FY15 | #REF! | #REF! | #REF! | #REF!
| FY16 | 0.5 | 62.4161 | 42.5 | 104.9161
| Total | #REF! | #REF! | #REF! | #REF!
Legend
Waiting
Complete