## Sheet1
| Duration | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI
(Days) | time axis 2021-07-23 to 2021-09-03
Swap Cryo CMTF > UITF | bar: 2021-07-23
Start HCO | bar: 2021-07-24 to 2021-07-30
Complete HCO | bar: 2021-07-24 to 2021-07-30
Beam Authorization | bar: 2021-07-30
Beamline Commissioning | 16 | bar: 2021-07-31 to 2021-08-15
Wastewater Experiment (2 weeks) | 14 | bar: 2021-08-16 to 2021-08-29
Source:
Gun HV conditioning/checkout | 7 | bar: 2021-07-31 to 2021-08-06
Cathode Activation | 1 | bar: 2021-08-07
Cathode Characterization (keV) | 1 | bar: 2021-08-08
EES-DC
Solenoid FSD Testing | 0.25 | bar: 2021-07-31
Solenoid Burn In | 6.75 | bar: 2021-08-01 to 2021-08-06
EES-RF
LLRF 3.0 Development | 7 | bar: 2021-07-31 to 2021-08-06
EES-IC
Fast Valve Closure Test | 0.1 | 2021-08-09: 0.1
BCM Calibration/Testing | 0.25 | 2021-08-10: 0.25
BLA/Current Clamp FSD Testing | 0.25 | 2021-08-10: 0.25
SSG
BLM Configuration/verification | 0.5 | 2021-08-09: 0.5
EH&S
Shielding Verification Test | 0.5 | 2021-08-11: 0.5
Experiment
Measure Laser Spots | 0.5 | 2021-08-07: 0.5
Current Lock Configuration | 0.1 | 2021-08-09: 0.1
Raster Verification | 0.1 | 2021-08-09: 0.1
Target Mapping Verification | 0.1 | 2021-08-09: 0.1
Radiation Dose Mapping Study | 0.5 | 2021-08-11: 0.5
keV Emittance Measurements | 2
Harp Based | 1 | bar: 2021-08-16
Viewer Based | 1 | bar: 2021-08-17
MeV Emittance Measurements | 2
Harp Based | 1 | bar: 2021-08-18
Viewer Based | 1 | bar: 2021-08-19
Energy Spread Characterization | 0.5 | 2021-08-20: 0.5
Energy Measurement (MeV line) | 0.5 | 2021-08-20: 0.5
Sample Ittadiation | 4 | bar: 2021-08-21 to 2021-08-24
Float / Harp & Viewer Tour | 1 | bar: 2021-08-25
keV Emittance Measurements | 1 | bar: 2021-08-26
MeV Emittance Measurements | 1 | bar: 2021-08-27
Float/Other Studies | bar: 2021-08-28 to 2021-08-29
UITF
keV Setup | 2 | bar: 2021-08-12 to 2021-08-13
MeV Setup | 2 | bar: 2021-08-14 to 2021-08-15
Bunchlength Monitoring | 0.5 | 2021-08-10: 0.5
Booster Charaterization
Shifts (Sum) | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1