## Slide 1: UITF: Booster and HDIce testing (3/17/2020)
Deliverables/Milestones
    Commission the QCM before installation at CEBAF 2021 (for Moller)
    Provide beam to HDIce for target tests (three or four run periods requested)
Staffing for FY2020
    FTEs: “Run0” (booster commissioning): Injector Group, Engineering HCO and support as needed, including Cryo to reconfigure CTF
    FTEs: “Runs1-3” (HDIce tests), request (3) fulltime Operators
    Skills :
      Facility Manager and Operators
      Cryo
      I&C
      DC power
      RF group
      Survey and Alignment
      Safety System Group
      Software, High Level Apps, Computer support
      Installation to remove/replace roof tiles
    When needed: now
Issues/Concerns that are/could affect on time delivery
    Approved UITF Operators (Kazimi and company) are busy at CEBAF
    Gun Group will be rebuilding CEBAF injector during SAD, not available to operate UITF for HDIce tests
    24/7 operations required
  DOE accelerator requirements are very formal, very strict
  Must close out (2) CATS items to obtain permission to Operate UITF (i.e., for HDIce runs)
  Covid-19
Recommended Mitigation:
  Take advantage of window of opportunity, a break in LCLS-2 CM testing at CMTF
  Operators available during SAD
  Poelker to close the 2 remaining CATS items by end April, ready to ask for permission to Operate and hope Site Office grants permission in timely manner

## Slide 2: UITF schedule, following productive meeting with Allison, Patrizia, Andy, Tony, Camille, Bob May, Steve Smith on 3/5/2020
(3/17/2020)
There’s a gap in LCLS-2 and CEBAF CM testing at CMTF, a perfect opportunity to perform Runs 0 - 3

## Slide 3
Noteworthy developments
(3/5/2020)
Buncher tests look good, we have numbers for phase and gradient, longitudinal waist at 2-cell cavity inside booster
Yao cavity tests have started, seems like a useful tool to set phases
Closed one CATS item - document procedures
Nearly finished closing out another CATS item: SAF162 UITF Operator is now a formal training, first training session scheduled for March 26
In good shape for Run0

## Slide 4: Preparing for Runs1, 2 and 3 (3/17/2020)
Still quite a lot of work to do
  Elevated beamline vacuum work, need vacuum from gun to HDIce dump
  HDIce computer interfaces
  Machine protection nodes related to HDIce
  ERR response must be filed
  Install 2nd Rowgowski coil for testing during Run0
  There is confusion about priority of UITF and HDIce tests as it relates to Medcon5

## Slide 5: UITF – Comments (3/17/2020)
ARR “post-start” findings
almost
This one does not need to be closed
Will work on this one now and immediately after Run0, with plan to distribute start up procedure ~ 1 week after commissioning run, ~ April 23. Then work with Bob to draft letter requesting permission to Operate, permission granted by May 7, that’s the plan