## Sheet1
KEY
COMPLETE
SCHEDULED
| Name | PSS | Goal | Status | Result or Useful Link
| 4-LLRF | INJ/NL | GSET/PSET @ 249/499 for 4 lasers | Complete | http://devweb.acc.jlab.org/CSUEApps/atlis/task/16999
| SRF @ 4K Ops | INJ/NL | Characterize capability for 50uA @ 18.5 MeV | Complete | https://logbooks.jlab.org/entry/3468680
| Tune mode generator | INJ | BS/VL/TU/CW w/ PC=OFF in CW + PSS cert | Complete | http://devweb.acc.jlab.org/CSUEApps/atlis/task/17296
| Brock bunch timing | INJ | Use Brock signal lock laser phase to 1497 MHz | Try again after "rough" phasing
| Kicker test | INJ | Drive Brock w/ HAWG, characterize kick | Receive, test, install HAWG … TBD
| PQB: spot size | INJ | Change size at PC/PC, evaluate PQB + life | APRIL 17-21 | https://wiki.jlab.org/ciswiki/index.php/PQB_Meeting_April_5,_2017
| Remove Gun3 | R | Remove Gun3, replace vacuum diag, bake | MAY 8-12 | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/17278
| Gun2 up to 150kV | INJ | Evaluate Gun2 for comparison: vac, emit, life | Week April 24 ? Or May 22 ?
| 200kV Gun | INJ/NL | Install gun/NEG, operate w/ Spellman @ 200kV | Priority job: June + July Priority
| PQB: 130kV v. 200kV | INJ | Compare position differences 130 v. 200 kV | July
| Resonant polarimeter | INJ | Install polarimete 500keV, detect P signal | TBD
| PQB: RTP | INJ | Evaluate RTP as polarization Pockels cell | TBD
| Test GaAsSb/AlGaAs | INJ/NL | Activate: a) QE vs. L, b) Pol, c) Lifetime, d) PQB | Period : 4/24 - 5/5 ???
| Test DBR | INJ/NL | Swap Gun2 photocathode | TBD
| Bubble Chamber | INJ/NL | Two week engineering run | AUGUST 7-17
| Mott Run III | INJ/NL | 4-energy study w/ gold | TBD