## Slide 1: UITF (1/21/2020)
Deliverables/Milestones
    Commission the QCM before installation at CEBAF 2021 (for Moller)
    Provide beam to HDIce for target tests (three or four run periods requested)
Staffing for FY2020
    FTEs: 1 FTE requested for operations and 0.5 FTE for Engineering support; RSRUIT
    FTEs: 2 FTEs requested to continue “building” UITF; ITFPTB
    Skills :
      Facility Manager and Operators
      I&C
      DC power
      RF group
      Survey and Alignment
      Safety System Group
      Software, High Level Apps, Computer support
      Installation to remove/replace roof tiles
    When needed: now
Issues/Concerns that are/could affect on time delivery
    UITF gets worked on “best effort” basis
    Approved UITF Operators are busy at CEBAF (LERF gun and laser)
  CTF can’t cool CMTF and UITF at same time, CMTF scheduled for LCLS testing through May, June. After LCLS2, CMTF will be needed for CEBAF cryomodule tests
  Key HDIce staff will retire soon, Postdoc leaving
  24/7 operations required
  DOE accelerator requirements are very formal, very strict
Recommended Mitigation:
  Prioritize HDIce over LCLS2 and CEBAF
  Hire dedicated Facility Manager and two Operators
  Upgrade the CTF refrigerator to provide more LHe capacity

## Slide 2: UITF “schedule”
HDIce run schedule
done
Buncher commissioning January
Booster commissioning when opportunity presents itself
After LCLS2 testing finished at CMTF, May/June 2020
HDIce tests cannot be performed contiguously: weeks-long breaks are required between runs
(1/21/2020)

## Slide 3
UITF today
Floating 200 keV beam through booster
Heating the buncher to hit resonance
Testing Wien Filter for 200 keV beam
Building walls
Commissioning Plan: 200 keV, 500 keV, 1 MeV, and 10 MeV beam delivered to two dumps
(1/21/2020)

## Slide 4: UITF – Comments (1/21/2020)
We postponed installation of booster until 2021
Fairly short to-do list (https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_January_3,_2020)
Buncher on resonance!
Trying to lock up at least three times per week to make beam
Week of Jan 27, dedicated week of operations to commission the buncher and the Yao cavity time-of-flight system, and all the other devices on the waist height beamline
Will install a second Ragowski coil near booster, so HDIce can test nA BPM before run 1
Prepare for possible 2 week gap in April when there is no LCLS II cryomodule inside CMTF – this could be run 0, booster commissioning
Suspect there will be lots of documentation required to begin run 1 (aka “operate” the UITF accelerator, beam to HDIce via elevated beamline)

## Slide 5: UITF – Comments (1/21/2020)
ARR “post-start” findings