## Schedule
Inj Commissioning and Restoration after SAD 2024
Prerequisites: HCO to ILD complete, simulated values of solenoids and warm RF ready for download, all lasers operable, on good QE spot, Gun HV at 200kV. Reference ATLis: https://tasklists.jlab.org/atlis/tasks/111504
| Week 0 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 09-Dec | Tues 10-Dec | Wed 11-Dec | Thurs 12-Dec | Fri 13-Dec | Sat 14-Dec | Sun 15-Dec
| Day/Swing Shift | HCO to FC2 | HCO to FC2 | HCO to FC2 | Completeing HCO to FC2 | Need Beam Authorization to 1D | Photocathode lifetime studies | Photocathode lifetime studies
[5 empty] | CIS Activate Wafer? | R30-4 gun eval
[5 empty] | CIS HCO Complete | Establish Tune Beam to FC1/1D |  | FX Optics Studies
[5 empty] | CIS identify good spot on wafer | Kicker Certification
[5 empty] | Laser frequencies set | R30-4 gun eval
|  | PSS Certifications | PSS Certifications | PSS Certifications | PSS Certifications
| Swing/Owl |  |  |  |  | Photocathode lifetime studies | Ops Inj Setup Procedures? | Ops Inj Setup Procedures
[7 empty] | Depends upon lifetime studies | Depends upon lifetime studies
Schedule can shift left or right
Max/Carlos: needs ~1hr to FC1, assistance from Carroll, Tom Powers: Preliminary R30-4 Gun Evaluation: https://tasklists.jlab.org/bslist/tasks/114405
Yan Set up beam to 1D for PSS Kicker Certification:
Max: Photocathode Lifetime Studies: https://tasklists.jlab.org/bslist/tasks/114440
Max: FX Optics and Orbit study after yoke modification: https://tasklists.jlab.org/bslist/tasks/109864
Ken: Test Procedure Gun to Pcup/1D: https://tasklists.jlab.org/bslist/tasks/113337
Ken: Test Procedure; Setting up Choppers 1 and 2: https://tasklists.jlab.org/bslist/tasks/113340
| Week 1 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 16-Dec | Tues 17-Dec | Wed 18-Dec | Thurs 19-Dec | Fri 20-Dec | Sat 21-Dec | Sun 22-Dec
| Day | HCO to ILD | HCO to ILD | HCO to ILD | HCO to ILD | Complete HCO to ILD
|  | NL Open? | NL Open? | NL Open? | NL Open? | NL Open | Winter Beak | Winter Beak
|  | Establish Tune Beam to FC1/1D | Establish Tune Beam to FC1/1D | Lock NL Swing Shift | Lock NL Swing Shift | CIS: Prep Injector for Winter Break
|  | Set up warm RF | Set up warm RF if needed | Characterize Wien Filter Optics | Cross Calibrate IYG0I02 and IHA0I02 |  |  | Turn on Inj Thurs Jan 2?
Possible BS to FC1
Restart Inj Commissioning Jan 6
| Swing/Owl | Early Injector Orbit Data up to Pcup | Thread beam through Booster and FC2 | Thread beam through Booster and FC2 | Thread beam through Booster and FC2
Booster Optics Measurements
Owl
|  | *Pcup to FC1 | *Pcup to FC1 | *Steer to FC2 | FX Optics Studies
|  |  | *Chopper 1&2 | *Chopper 1&2 | *Steer to FC2
Max: FX Optics and Orbit study after yoke modification: https://tasklists.jlab.org/bslist/tasks/109864
Alicia: Early Injector Orbit Data: https://tasklists.jlab.org/atlis/tasks/111605
Dennis: Characterize Wien Filter Optics: https://tasklists.jlab.org/bslist/tasks/107364
Dennis: Cross Calibrate IYG0I02 vs IHA0I02: https://tasklists.jlab.org/bslist/tasks/24275
Max: Booster Optics Measurements: https://tasklists.jlab.org/bslist/tasks/113860
*If time Permits:
Ken: Steer beam from Pcup to FC1: https://tasklists.jlab.org/bslist/tasks/113349
Ken: Chopper 1 and 2 Set up procedure: https://tasklists.jlab.org/bslist/tasks/113340
Ken: Steer beam from Gun to Pcup: https://tasklists.jlab.org/bslist/tasks/114416
Ken: Beam steer from FC2 to ILD: https://tasklists.jlab.org/bslist/tasks/113404
| Week 2 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 06-Jan | Tues 07-Jan | Wed 08-Jan | Thurs 09-Jan | Fri 10-Jan | Sat 11-Jan | Sun 12-Jan
| Day | Inj Commissioning FC2 | Inj Commissioning FC2 | Inj Commissioning FC2 | Inj Commissioning to 4D | Inj Commissioning to 4D | 5D Irradiation Commissioning | 5D Irradiation Commissioning
|  |  | Mott DAQ Check | Spin Rotator test at 200keV |  |  | MPT0L02 Optics Studies | Degrader Commissioning
Calibrate Wien (8hrs) Riad/Max
| Swing | Beam Studies FC1 | Beam Studies FC1 | Set Wien for Physics | Beam Studies FC2 | Beam Studies FC2 | BS up to FC2 | BS up to FC2
|  | Booster Optics Measurements |  | Beam Studies FC1 |  | Early Injector Orbit Data to FC2
| Owl | Beam Studies FC1 | Beam Studies FC1 | Beam Studies FC1 | Beam Studies FC2 | Beam Studies FC2
MPT0L02 Optics
|  |  | Characterize Wien Filter Optics | Cross Calibration of IYG0I02 vs IHA0I02 | Booster Optics Measurement -2D
|  | Ops Inj Training Prep | Ops Inj Training Prep | Ops Inj Training Prep | Ops Inj Training Prep | Ops Inj Training Prep | Ops Inj Training Prep | Ops Inj Training Prep
|  | Steer from Gun to Pcup | Steer from Gun to Pcup | Beam Steer to FC1 | Beam Steer to FC1 | Beam Steer to FC2
Max: Mott DAQ Upgrade Checks: https://tasklists.jlab.org/bslist/tasks/114409
Max/Riad: Calibrate the Wien:
Max: Spin Rorator Tests: https://tasklists.jlab.org/bslist/tasks/114355
Max: Booster Optics Measurements: https://tasklists.jlab.org/bslist/tasks/113860
Turner: Characterize Wien Filter Optics: https://tasklists.jlab.org/bslist/tasks/107364
Turner: Cross Calibrate IYG0I02 and IHA0I02
Turner: MPT0L02 Optics Characterization: https://tasklists.jlab.org/bslist/tasks/114280
Turner: Degrader Commissioning: https://tasklists.jlab.org/bslist/tasks/113987
Alicia: Early Injector Orbit Data to FC1: https://tasklists.jlab.org/atlis/tasks/111605
Alicia: Target Irradiation 5D Line Commissioning: https://tasklists.jlab.org/bslist/tasks/113763
Ken: Steer beam from Pcup to FC1: https://tasklists.jlab.org/bslist/tasks/113349
Ken: Chopper 1 and 2 Set up procedure: https://tasklists.jlab.org/bslist/tasks/113340
Ken: Steer beam from Gun to Pcup: https://tasklists.jlab.org/bslist/tasks/114416
Ken: Beam steer from FC2 to ILD: https://tasklists.jlab.org/bslist/tasks/113404
| Week 3 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 13-Jan | Tues 14-Jan | Wed 15-Jan | Thurs 16-Jan | Fri 17-Jan | Sat 18-Jan | Sun 19-Jan
| Day/Swing Shift | Inj Commissioning 4D | Inj Commissioning ILD | Inj Commissioning ILD | Inj Commissioning ILD | PQB Comprehensive Studies? | PQB Comprehensive Studies? | PQB Comprehensive Studies?
[6 empty] | PQB Transmission Check? | PQB Transmission Check? | PQB Transmission Check?
[5 empty] | Inj Match/CASA | Spin Cal and PQB ? | Spin Cal and PQB ? | Spin Cal and PQB ?
Check Transmission for high current
| Swing | Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD
|  |  | 5D Irradiation Studies | 5D Irradiation Studies | 5D Irradiation Studies | 5D Irradiation Studies | Early Injector Orbit Data to ILD | 5D Irradiation Studies
|  |  | Degrader Commis/ Studies | Degrader Commis/ Studies | Degrader Commis/ Studies | Degrader Commis/ Studies | Degrader Commis/ Studies | Degrader Commis/ Studies
[5 empty] | Multiwire Emittance Measurement | Multiwire Emittance Measurement | Multiwire Emittance Measurement | Multiwire Emittance Measurement
| Owl | 5D Irradiation Studies
Degrader Commissioning
*Ops Inj Training Prep
|  | Beam Steer to FC2 | *Ops Inj Training Prep | *Ops Inj Training Prep | *Ops Inj Training Prep | *Ops Inj Training Prep | *Ops Inj Training Prep | *Ops Inj Training Prep
|  | *review injector procedures with beam | Review Inj Procedures | Review Inj Procedures | steer to ILD | steer to ILD
Alicia: Early Injector Orbit Data to ILD: https://tasklists.jlab.org/atlis/tasks/111605
Alicia: Target Irrdiation 5D Line Commissioning: https://tasklists.jlab.org/bslist/tasks/113763
Turner: Degrader Commissioning: https://tasklists.jlab.org/bslist/tasks/113987
Turner: Degrader Beam Studies: https://tasklists.jlab.org/bslist/tasks/111105
Turner: Multiwire Emittance Measurements: https://tasklists.jlab.org/bslist/tasks/113343
Ken: Steer beam from Pcup to FC1: https://tasklists.jlab.org/bslist/tasks/113349
Ken: Chopper 1 and 2 Set up procedure: https://tasklists.jlab.org/bslist/tasks/113340
Ken: Steer beam from Gun to Pcup: https://tasklists.jlab.org/bslist/tasks/114416
Ken: Beam steer from FC2 to ILD: https://tasklists.jlab.org/bslist/tasks/113404
Caryn: Pre-Check on Transmission and Helicity Pickup to FC2: https://tasklists.jlab.org/bslist/tasks/113334
Caryn: PQB Comprehensive: https://tasklists.jlab.org/bslist/tasks/110921
| Week 4 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 20-Jan | Tues 21-Jan | Wed 22-Jan | Thurs 23-Jan | Fri 24-Jan | Sat 25-Jan | Sun 26-Jan
| Day |  | 5D Irradiation Studies | 5D Irradiation Studies | 5D Irradiation Studies | 5D Irradiation Studies
|  |  | Degrader Studies | Degrader Studies | Degrader Studies | Degrader Studies
|  | Hand over Inj to Ops | ORFP | ORFP | ORFP | ORFP | ORFP | ORFP
| Swing |  | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD
| Owl |  | *Ops Inj Training | *Ops Inj Training | *Ops Inj Training
|  |  | Steer to ILD | Steer to ILD | Steer to ILD
Alicia: Target Irrdiation 5D Line Commissioning: https://tasklists.jlab.org/bslist/tasks/113763
Turner: Degrader Commissioning: https://tasklists.jlab.org/bslist/tasks/113987
Turner: Degrader Beam Studies: https://tasklists.jlab.org/bslist/tasks/111105
Ken: Steer beam from Pcup to FC1: https://tasklists.jlab.org/bslist/tasks/113349
Ken: Chopper 1 and 2 Set up procedure: https://tasklists.jlab.org/bslist/tasks/113340
Ken: Steer beam from Gun to Pcup: https://tasklists.jlab.org/bslist/tasks/114416
Ken: Beam steer from FC2 to ILD: https://tasklists.jlab.org/bslist/tasks/113404
| Week 5 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 27-Jan | Tues 28-Jan | Wed 29-Jan | Thurs 30-Jan | Fri 31-Jan | Sat 01-Feb | Sun 02-Feb
| Day/Swing Shift | 5D Irradiation Studies | 5D Irradiation Studies | Beam to ILD prep to turn over Inj | Beam to ILD prep to turn over Inj | Beam to ILD prep to turn over Inj
|  | Degrader Studies | Degrader Studies
|  | ORFP | ORFP | ORFP | ORFP | ORFP | ORFP | ORFP
| Swing/Owl | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD | Beam Studies FC1/FC2/ILD
|  | Ops Inj Training | Ops Inj Training | Ops Inj Training | Ops Inj Training