## Sheet1
component |  | status | controls
layout |  | need ME design | n/a
dipole |  | exists (or new Lakshmi dipole) | exists
valve |  | exists | exists
H/V corrector #1 |  | exists | two trims
solenoids |  | FB/FB or FQ exists, choose | one or two trims
H/V corrector #2 |  | exists | two trims
Scattering chamber |  | exists | n/a
Lead dump |  | redesign | n/a
Target ladder | Linear actuator | have, inspect | n/a
| STAC5 | exists | need EPICS, control screen
| ladder | have, inspect
| 4 foils | check cabinet
| viewer | check cabinet
| camera | need | video channel
Detectors | (4) vac detector holders | have (2), need (2)
| (4) surface barrier | have (2 old), have (2 new)
| (4) collimator shields | need (4)
| (4) collimator holders | have (2), maybe (4?)
| (2) 50 collimators | use old?, make new?
| (2) 120 collimators | use old?, make new?
Vacuum | ion pump | need
| pump out port | have
| vacuum window | have
Dump | Fcup | can we re-use? | picoammeter
Girder |  | need to build/fabricate