## Slide 1
PQB Task | LEFT | RIGHT
Finalize Spin Rotators | 6/3: https://logbooks.jlab.org/entry/3684884 | 6/3: https://logbooks.jlab.org/entry/3684837
Injector Injector to ILD | 6/3: https://logbooks.jlab.org/entry/3684946 | 6/3: https://logbooks.jlab.org/entry/3684962
Initial PQB Check | 6/5: https://logbooks.jlab.org/entry/3685216 | 6/5: https://logbooks.jlab.org/entry/3684990
Final Injector to ILD | 6/12: https://logbooks.jlab.org/entry/3687751 | Reza estimates 8 hours
Position Damping to ILD | Estimate for this task is 4 hours, needs to be done for both LEFT and RIGHT http://opsweb.acc.jlab.org/CSUEApps/atlis/task/19273 | 
Position Damping to Hall A | Estimate for this task is 6 hours, needs to be done for both LEFT and RIGHT http://opsweb.acc.jlab.org/CSUEApps/atlis/task/19275 | 
Initial PQB Check to Hall A | Where in the Hall A commissioning sequence do we start focusing on PQB? | 
Spin Dance | Estimate for this task is 4 hours, once Moller polarimeter is ready for measurements. Estimate 4 hours injector turning if PQB is affected by change from expected angle -15.5 deg Do we repeat, another 4-8 hours for first change to right? | 
Final PQB Setup to Hall A | What are approximate thresholds for which intensity and position differences are not acceptable? | 
Anticipated Remaining PQB Setup and Checkout Tasks