Brock cavity install checklist

June 17:

- RF off for chopper, prebuncher (Marcy)

- HV off for Wien (Marcy) – LOTO the PS in ISB (John can help)

- Cycle valves 3x (Marcy)

- Downgrade magnets, BPMs, Aperture currents in HCO tool (Marcy, system experts)

- Remove valves from remote control (Phil)

- power magnets off (DC Power)

- remove quads from BPMs (DC Power) – please mark orientation before removing; quads can be taken off by removing 4 screws and then clamshells apart; then spacer clamps come off – please keep these together

- remove correctors from BPMs (DC Power) – helps if you mark orientation before removing, left/right, up/down, etc., clamshells apart, i.e. should need to undo any of the wiring harness – greatly simplifies putting back on.

- remove BMP, A1, A2 instrumentation (P. Francis) – Pete can undo all of BPM’s; for the A1/A2 not much to do except BNC cable; be sure to save/store copper hardware and  tee-zener

- Remove Wien HV cables (Marcy) – please keep track which is LEFT and RIGHT

- Remove viewer insertion cylinders (Phil)

- Remove Harp electronics (Phil)

- Remove A1, A2 water lines (Phil)

- Remove PSS kicker magnet (PSS)

June 18 – June 19:

- Survey and alignment setup (S&A)

- As found: IPM0I01, IPM0I01A, IFY0IA1, IWF1I04, flange upstream of valve VBV1I07 (S&A) – we don’t survey BPM’s because that info doesn’t get used anywhere; definitely good to know what Wien/downstream and 1I07/upgstream doesn’t get gronked;  if you want to survey something try MFQ0I01 – nice to know how close that is before/after

- Ion pumps off (Phil or Marcy)

- Verify valves closed (Marcy)

- Verify RF off for chopper (Marcy)

- Vent beamline at VIP0I1A (Phil, Marcy)

- Remove A1 cube, spoolpiece with PSS kicker (Phil, Marcy)

- Survey Wien faceplate with respect to flange (S&A)

- Take A1 cube to cleanroom (Phil or Marcy)

- Move hardware on A1 cube to new A1/Brock cube (Phil)

- Take A1/Brock cube to S&A lab for alignment (Phil)

- Align, determine if new spacers are needed (Phil) – remember – A1 was aligned last time to another aperture, so wouldn’t be surprised if different by aligning to closer Brock aperture;  unless the old apertures are dead on with Brock I would take the time and make 3 new spacers;  the smallest aperture is 2mm so 5% of that is 100um or ~4 mil.  Remember: PV experiments suffer due to A1 loss.  All to say…

- Destroy old spacers if necessary (Marcy)

Tuesday or Friday

- Connect Brock oscilloscope to network, verify software functionality through epics screens (Wes)

June 22-23:

- Continue/complete alignment of A1, Brock, Wien in survey lab (S&A, Phil)

- Install YAG viewer screens at ITV0I01 (required) ITV0I02 (optional)  (Phil and Marcy) – if John gets two done then good idea to do both; I’ve talked to John about making a 5mm x 5mm square centered on the YAG; makes sense to orient square so will be X/Y on viewport, but if not perfectly aligned OK.  Most important is to known distances between sides of the square.  I assume line width will be pretty small, but if possible mic or put under some microscope John knows about; the real physical distance between lines is the pixel calibration later on.; will factor into the uncertainty in beam size

- Remove RGA from injector beamline at VIP0I02

- Install Brock/A1

- Pumpdown

- Leak check

June 24:

- Survey and Alignment

- IPM0I01, IPM0I01A, IFY0IA1, IWF1I04, flange upstream of valve VBV1I07 (S&A)

- Adjust at VBV1I07 as needed/possible to get things back on centerline

June 25-28: bakeout

June 29-30:

- Bake down (Marcy, Phil)

- Leak check if beamline to pump cart

- Reconnect BPMs, Aperture current (Pete)

- Reconnect viewers (Tony Delacruz)

- Reconnect correctors, quads, solenoid (DC power)

- Reconnect viewer hardware, harp supports (Phil)

- Reconnect Wien HV cables (Marcy)

- Energize elements, remove LOTO when appropriate

- Check out elements, HCO tool, as they are reconnected (all)

- PSS reconnect PSS kicker (PSS)

- Move Brock scope to position, connect to Brock cavity

- Re-energize valves

July 1:

- Injector segment mode lockup

- Recover beam to FC1

- PSS kicker certification

- Beam on for Brock cavity tests (Matt Poelker)