## 200831
Week # | Week of | Components Due | AIPINJ Jobs | RSR Jobs | Groups | PSS | Sun | Mon | Tue | Wed | Thu | Fri | Sat
-4 | 2020-08-23 |  | BPM mapping #1, #2, #3 Survey Wien electrodes | Run CEBAF / HCO LERF
-3 | 2020-08-30 |  | Start assemble/align 2I components | bar: Mon
-2 | 2020-09-06 |  | Finish assemble/align 2I components | Run CEBAF / Run LERF |  | Mon: Lab Holiday
-1 | 2020-09-13 |  | Prep for Gun/2I jobs (hipot, bake equip)
1 | 2020-09-20 |  | HV test existing tee electrode and Wiens |  | Installation (crane) Ops (lock-ups) | PSS: 4 wks of INJ SEG
2 | 2020-09-27 |  | Replace electrode, rebuild 2I line |  | DC (remove magnets) I&C (remove BPM's) S&A (gun + 2I line)
3 | 2020-10-04 |  | Bake Gun2 and 2I line Assemble Y-chamber NEG | Repair FC1
4 | 2020-10-11 |  | HV test small shed electrode |  | Ops (lock-ups)
5 | 2020-10-18 |  | 1I-0I electronic & vacuum disconnects Laser outrigger table removal |  | DC, I&C, PSS (disconnects) Installation (girder removal) | PSS: 16 wks of no PSS (not counting break!)
6 | 2020-10-25 |  | 1I-0I removing components from tunnel | UHV repair may begin | Installation (girder removal)
7 | 2020-11-01 |  | Assemble Y-chamber in TL Disassemble/modify/clean Wiens Modify pedestals in tunnel ? |  | Machine shop (Wien) S&A/Install (new pedestals)
8 | 2020-11-08 |  | Install Y-chamber in tunnel Test magnetic assembly/map Wiens |  | S&A/Install (crane Y-chamber to tunnel, install, align)
9 | 2020-11-15 |  | Build/align A1/A2 in TL Test magnetic assembly/map Wiens
10 | 2020-11-22 |  | Build/align A1/A2 in TL Test electric assembly/HV Wiens
11 | 2020-11-29 |  | Build/align A1/A2 in TL Test electric assembly/HV Wiens" |  |  | Thu: Lab Holiday; Fri: Lab Holiday
12 | 2020-12-06 |  | Install A1/A2 in tunnel Build up Wien sub-assemblies
13 | 2020-12-13 |  | Bake A1/A2 in tunnel Build up Wien sub-assemblies
14 | 2020-12-20 |  | Float |  |  | Thu: Lab Holiday; Fri: Lab Holiday
15 | 2020-12-27 | [6 empty] | Shutdown Day | Shutdown Day | Shutdown Day | Lab Holiday | Lab Holiday
16 | 2020-01-03 | bar: PSS to Sun
17 | 2020-01-10 |  | Move or build Wiens girder in tunnel
18 | 2020-01-17 |  | Bake Y and Wien girder in tunnel
19 | 2020-01-24 |  | Reconnects of 2I/1I/0I regions
20 | 2020-01-31 |  | HCO of 2I/1I/0I regions | Add new Load chamber
21 | 2020-02-07 |  | HCO of 1I/0I regions
22 | 2020-02-14 |  | Float
23 | 2020-02-21 |  | Float
24 | 2020-02-28 |  | Commission Week #1 - Gun |  |  | PSS: 3 wks of INJ SEG BP Beam to FC#1
25 | 2020-03-07 |  | Commission Week #2 - Setup to chopper
26 | 2020-03-14 |  | Commission Week #3 - Setup to chopper
27 | 2020-03-28 |  | Commission Week #4 - Setup to FC2 |  |  | PSS: 3 wks of INJ/NL BP Beam to FC#2
28 | 2020-04-04 |  | Commission Week #5 - Wien/Spin
29 | 2020-04-11 |  | Commission Week #6 - Float
30 | 2020-04-18 |  | Float |  |  | PSS: 6 wks Float
31 | 2020-04-25 |  | Float
32 | 2020-05-02 |  | Float
33 | 2020-05-09 |  | Float
34 | 2020-05-16 |  | Float
35 | 2020-05-23 |  | Float
36 | 2020-05-30 |  | CEBAF HCO |  |  | PSS: Run CEBAF
37 | 2020-06-06 |  | CEBAF Restore
38 | 2020-06-13 |  | CEBAF Restore
39 | 2020-06-21 |  | CEBAF Physics starts

## 200910_Options
| Pros/Cons | Focus on HV gas conditioning tee and tee+shed Minimize dependence on S&A, Install Possibly wrap up PSS by end of Sep Defer the beamline work until mid-October | Focus on installing new cathode electrode Greater dependence on S&A, Install Needs PSS until mid-Oct Jump start vacuum work through Y
Date | Day | Strategy "A" | Strategy "B" | Comments
2020-09-21 | 1 | Install move DILO + PIG + Bake to tunnel Bypass the in-line NEG filters, bake line Add conditioning resistor | Install move DILO + PIG + Bake to tunnel Install move 2I and Y chamber to tunnel Bypass the in-line NEG filters, bake line Add conditioning resistor
2020-09-22 | 2 | Define laser launch + laser retroreflection Safe photocathodes + move dummy to cathode HV eval Wien filters | Define laser launch + laser retroreflection Safe photocathodes + move dummy to cathode HV eval Wien filters
2020-09-23 | 3 | HV eval + gas condition of tee | S&A as-found Gun2, 2I, … 2I and 1I disconnects
2020-09-24 | 4 | HV eval + gas condition of tee | Remove laser table Vent 1I, test gun valve for leaks Vent gun, blank and pump down
2020-09-25 | 5 | HV eval + gas condition of tee | Remove 2I and Y-chamber Install Y-chamber Drill and mount 2I solenoid
2020-09-26 | 6 | HV eval + gas condition of tee | Weekend
2020-09-27 | 7 | HV eval + gas condition of tee | Weekend
2020-09-28 | 8 | Breakpoint - 200 kV OK, then done w/ PSS | S&A install/align Y-chamber
2020-09-29 | 9 | S&A as-found of Gun2, 2I, … | Rework anode flange
2020-09-30 | 10 | Float | S&A install/align 2I beam pipe
2020-10-01 | 11 | Vent Gun2 S&A cathode for tee+shed Pump down Prep 2I line for bakeout | Vent Gun2 S&A cathode for tee+shed Pump down Prep 2I line for bakeout | Both plans are the same here
2020-10-02 | 12 | Leak check, setup and start bake | Leak check, setup and start bake
2020-10-03 | 13 | Bake | Bake
2020-10-04 | 14 | Bake | Bake
2020-10-05 | 15 | Bake | Bake
2020-10-06 | 16 | Bake | Bake
2020-10-07 | 17 | Ramp down, leak check | Ramp down, leak check
2020-10-08 | 18 | Re-assemble gun for HV tests | Re-assemble gun for HV tests
2020-10-09 | 19 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-10 | 20 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-11 | 21 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-12 | 22 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-13 | 23 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-14 | 24 | Breakpoint - Learn if tee+shed OK @ 200 kV | Breakpoint - Learn if tee+shed OK @ 200 kV
2020-10-15 | 25 | PSS expires 8am | PSS expires 8am
Formulas:
Date = [Date, row above]+1

## 200910
[5 empty] | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN
ID | R | Task | Start | End | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | 123 | INJ SEG PSS availabe | 2020-09-01 | 2020-10-15 | bar: SEP 1 to OCT 2; FEB 1 to JUN 4
2 | 1 | Gun - HV condition tee, test Wien to 15 kV | bar: SEP 3 to SEP 4
3 | 1 | Gun - Vent Gun, swap cathodes, bake, HV condition | bar: OCT 1 to OCT 2
4 | 1 | Gun - Install tee+shed, bake, HV condition | bar: OCT 1 to OCT 2
5 | 12 | Vac - Early opportunity to vent 1I (Y or Wien) for parts | bar: OCT 1 to OCT 2
6 | 123 | Vac - 2I, 1I, 0I laser box disconnects | bar: OCT 3
7 | 123 | Vac - Vent/remove 2I, 1I, 0I beam line | bar: OCT 4
8 | 1 | Vac - Complete rebuild of Y | bar: NOV 1
9 | 1 | Vac - Install/align beamline Gun, 2I, Y | bar: NOV 1 to NOV 2
10 | 1 | Region 1 (Gun, 2I) bake | bar: NOV 3 to NOV 4
11 | 1 | Reegion 1 reconnects | bar: DEC 1 to DEC 2
12 | 2 | Prebuncher - fab | bar: SEP 1 to OCT 4
13 | 2 | Prebuncher - testing | bar: NOV 1 to NOV 4
14 | 2 | Prebuncher - on girder | bar: DEC 1 to DEC 2
15 | 2 | FG solenoids on girder | bar: DEC 1 to DEC 2
16 | 2 | Wiens - Modify/clean Wien vacuum chamber | bar: NOV 1 to NOV 2
17 | 2 | Wiens - Assemble/map Wien magnet | bar: NOV 3 to NOV 4
18 | 2 | Wiens - Finalize electrodes | bar: DEC 1 to DEC 2
19 | 2 | Wiens - Complete S&A assembly | bar: DEC 3 to DEC 4
20 | 2 | Wiens - On girder | bar: JAN 1 to JAN 2
21 | 2 | Test Wien filter HV | bar: DEC 3 to DEC 4
22 | 2 | Wien cross - build new viewers | bar: DEC 2 to JAN 1
23 | 2 | Wien cross - quads arrive, QA | bar: JAN 1 to JAN 2
24 | 2 | Wien cross - add quads, weld flanges | bar: JAN 3 to JAN 4
25 | 2 | Wien cross - map quads | bar: FEB 1 to FEB 2
26 | 2 | Wien cross - final assembly | bar: FEB 3 to FEB 4
27 | 2 | Region 2 girder install/align | bar: MAR 1 to MAR 2
28 | 2 | Region 2 girder bake | bar: MAR 3 to MAR 4
29 | 2 | Region 2 reconnects | bar: APR 1 to APR 2
30 | 3 | A1/A2 - welded cubes ready/clean | bar: OCT 3 to OCT 4
31 | 3 | A1/A2 - MHD coils arrives | bar: NOV 1
32 | 3 | A1/A2 - MHD assembly/mapping | bar: NOV 2
33 | 3 | A1/A2 - vacuum aperture assembly & alignment | bar: NOV 3 to NOV 4
34 | 3 | A1/A2 - on girder | bar: DEC 1 to DEC 2
35 | 3 | A1/A2 - remaining girder assembly | bar: DEC 3 to DEC 4
36 | 3 | Region 3 girder - install to tunnel | bar: JAN 1 to JAN 3
37 | 3 | Region 3 girder - bake | bar: JAN 4 to FEB 1
38 | 3 | Region 3 reconnects | bar: FEB 2 to FEB 3
39 | 123 | Phase 1 HCO | bar: APR 3
40 | 123 | Commission Week #1 - Gun | bar: APR 4
41 | 123 | Commission Week #2 - Setup to chopper | bar: MAY 1
42 | 123 | Commission Week #3 - Setup to chopper | bar: MAY 2
43 | 123 | Commission Week #4 - Setup to FC2 | bar: MAY 3
44 | 123 | Commission Week #5 - Wien/Spin | bar: MAY 4
45 | 123 | CEBAF HCO | bar: JUN 1
46 | 123 | CEBAF Restore | bar: JUN 2
47 | 123 | CEBAF Restore | bar: JUN 3 to JUN 4