## Slide 1: UITF – Upgrade Injector Test Facility
Deliverables/Milestones
    Beam on HDIce by August 2016 (nA current level at ~ 10 MeV)
Staffing
    Critical Skills needed NOW: Facilities, Cryo including ODH assessment, Mechanical Design, Safety System Group for ODH, Ops Software
Update since last meeting
    Monthly meetings with Mont, on-going
    Cave1 north concrete wall demolition complete
    Accelerator design sufficiently complete to start building the keV beamline
    Shaun Gregory has started the MeV beamline design
    Cave1 cleared out, ready for Survey and Alignment
  Consensus achieved on entry/exit labyrinth from shielding point of view
  We realized we might have unwanted ODH2 conditions. Mat Wright now performing formal ODH assessment, which will include recommendations (?). Suspect we must revisit Cave2 ceiling design, to provide a passive escape path for helium gas
  Stairway to top of Cave1 – PR has been awarded
  Carlos and Don Bullard are back – they can focus on 350kV gun
  Continued progress on “stretch goals”: RF control modules, trim cards, quad magnets, BPMs (and staying within FY15 budget)

## Slide 2
Concrete demolition complete

## Slide 3
Cave 1 cleared out
in the queue for Survey and Alignment

## Slide 4
Ready to build the keV beamline
80/20 girder has been ordered, new gun table to straddle trench, 400kV gun HV power supply in house, waiting for SF6 tank which was evaluated by Tommy Hiatt, method identified to pressure-vessel certify the HV receptacle
Survey and Alignment to add monuments, they will tell us where to put the gun, the 80/20 stand, and the ¼ CM

## Slide 5: Shaun Gregory has started the MeV beamline design
(we think the MeV portion of accelerator will be easier to design than keV portion)

## Slide 6
Notes: Interior Page Design 2

## Slide 7
“Shed” triple-point protection
Doped insulator
SF6
R350 epoxy receptacle
Revisit one of our successful test configurations – polish the shed and test with actual gun electrode
Use a large doped insulator purchased by FEL: Danny Machie working on design

## Slide 8: UITF – Upgrade Injector Test Facility
To-do list for next 30 days
  Setup the electronics racks above Cave1
    Agree on layout, RadCon to approve it
    Installation Group (Neal Wilson and company) to build it
    Need a temporary stairway to access the top of Cave
    Provide electrical requirements to Facilities/Jason Willoughby
  Obtain the formal ODH assessment, use it to provide Tom Renzo information relevant to Cave2 ceiling design. Modifications to Cave1 ceiling required?
  Facilities should remove utilities on Control Room exterior wall (window air conditioner, fire, electric), so that Walter Kehlner can move more concrete block into position to erect the perimeter of Cave2
  Installation Group to install unistrut along east wall, for attaching utilities. Installation Group and Facilities to begin attaching utilities to this wall: LCW, GN2, compressed air, electric, lighting, fire suppression
  Move the ¼ CM into Cave1 or Cave2
  Apply high voltage to gun with shed electrode at FEL Gun Test Stand
  Need to make some headway on Bob May’s EHS&Q task list

## Slide 9
There’s enough LHe in UITF to completely displace all the air in the room. We don’t want the hassle of ODH2 conditions. Can’t rely on active ventilation, need adequate passive ventilation….

## Slide 10: Electronics Racks above Cave1
Fix the design
Finalize electrical requirements
Build it, populate the racks

## Slide 11: UITF – Upgrade Injector Test Facility
Issues/Concerns that could affect on-time delivery
  Can Cryo provide plumbing soon? Begin work on He recovery system for HDIce? Want to leave space for them to do their work but also want to start “filling up the cave” now
  Designers in short supply
  Can SSG provide the ODH and PSS systems on schedule?
  Facilities end-date February 2016 could delay ¼ CM commissioning, gun HV conditioning, and intentional beam generation
  Impact on CTF, a new LHe User
Recommended Mitigation
  Purchase contract designer
  We can use portable ODH monitoring system for ¼ CM commissioning
  Temporary shield wall and OSP could provide a means to commission ¼ CM, condition gun and perhaps make 350kV beam without a completed UITF concrete enclosure and PSS?
  Preble, K. Davis, Cryo Group have started conversation related to oversubscribed CTF. However, near term solution is likely a scheduling solution.
  Timing is good for Ops Software, provided we (mostly) duplicate existing CEBAF software controls