## Calendar
| SUN | MON | TUE | WED | THU | FRI | SAT
AUG | 9 | 10 | 11 | 12 | 13 | 14 | 15 | SCHEDULED
OWL
DAY |  | RA/Bubble | RA/Bubble | RA/Bubble |  |  |  | AVAILABLE
SWI |  | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble | IN/Mott 5756-4 | IN/Bubble
AUG | 16 | 17 | 18 | 19 | 20 | 21 | 22 | UNAVAILABLE
OWL
DAY
SWI |  | IN/GPT | IN/GPT | IN/GPT | IN/GPT | IN/GPT
AUG | 23 | 24 | 25 | 26 | 27 | 28 | 29
OWL
DAY
SWI |  | IN/GPT | IN/GPT | IN/GPT | IN/GPT | IN/GPT
AUG-SEP | 30 | 31 | 1 | 2 | 3 | 4 | 5
OWL
DAY
SWI
SEP | 6 | 7 | 8 | 9 | 10 | 11 | 12
OWL |  | Holiday
DAY |  | Holiday
SWI |  | Holiday
SEP | 13 | 14 | 15 | 16 | 17 | 18 | 19
OWL
DAY |  | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble
SWI |  | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble
SEP | 20 | 21 | 22 | 23 | 24 | 25 | 26
OWL
DAY |  | CRYO | CRYO | CRYO | CRYO | CRYO | CRYO
SWI |  | PSS | PSS | PSS | PSS | PSS | PSS
SEP-OCT | 27 | 28 | 29 | 30 | 1 | 2 | 3
OWL
DAY | CRYO | CRYO | CRYO | CRYO | CRYO | CRYO | CRYO
SWI | PSS | PSS | PSS | PSS | PSS | PSS
OCT | 4 | 5 | 6 | 7 | 8 | 9 | 10
OWL
DAY |  | HCO/CRYO | … | … | … | …
SWI
OCT | 11 | 12 | 13 | 14 | 15 | 16 | 17
OWL
DAY |  | HCO/CRYO | … | … | … | …
SWI
OCT | 18 | 19 | 20 | 21 | 22 | 23 | 24
OWL
DAY |  | HCO/CRYO | … | … | … | …
SWI
OCT-NOV | 25 | 26 | 27 | 28 | 29 | 30 | 1
OWL
DAY |  | RESTORE | RESTORE | RESTORE | RESTORE | RESTORE
SWI

## Tasks
ATLIS | Task | Contact | RA | INJSEG | INJ/NL | Term | Energy | Current | # shifts | Shift | Accesses | When? | Comment
| 5D beam line commissioning | Riad |  |  | x | FC2 | Up to max | 10 uA cw | 5 | SWING | maybe | 8/10-8/15 | Max gradient, momentum, optics
| Test SLSP-5756-4 | Joe/Riad |  |  | x | FC2 | 5 MeV | 2 uA cw | 1 | SWING | no | 8/14 | QE, analyzing power, polarization
| Radiate tungsten, then gallium | George/Pavel |  |  | x | FC2 | Max E | 10 uA cw | 1 | SWING | maybe | 8/10-8/15 | Changes rapid access when installed
15425 | GPT RF benchmarking | Injector group |  |  | x | FC2 | standard | Pulsed | 2 week | SWING | no | 8/17-8/28 | Save laser profile before/after
| Restore 3-laser + checkout | John/Matt/Shukui | x | [8 empty] | August | A=499, B=249, C=249
15326 | Test 250MHz phase shifter | Joe/Tomasz/John |  | x | x | FC1/FC2 | standard | 10 uA cw | 0.5 | DAY | no | Week 8/17 | Measure bleedthrough
| Bubble laser shutter | John/Riad | x | [5 empty] | 1 | DAY | yes | by Sep 14 | TLL=low=beam ON
| Bubble Commissioning | Riad |  |  | x | FC2 | 10 MeV | 10-100 uA | 1 week | DAY/SWING | maybe | 9/14-9/19 | Max current depends on thermal analysis
| Test Brock deconvolution | Wes/Mahmoud |  | x |  | FC1 | 130 keV | 10 uA cw | 0.5 | DAY | yes | Aug
| Prebuncher calibration | Fay/Joe |  | x |  | FC1 | 130 keV | 10-100 uA | 1 | DAY | no | Aug-Oct
| Compare Brock and model | Matt/Fay |  | x |  | FC1 | 130 keV | 100 uA cw | 1-3 | DAY | no | Aug-Oct | Prove Brock is useful tool
| Brock/Zener measurement | Matt |  | x |  | FC1 | 130 keV | 100 uA | 1-3 | DAY | likely | Aug-Oct
| YAG emittance measurement | Yan/Shukui |  | x |  | FC1 | 130 keV | 10 uA | 3 | DAY | likely | Aug-Oct | Work with Gubeli, compare against harp
CRYO RECONFIGURATION AND PSS CERTIFICATION FROM SEP 21 - OCT 3
| Gun2 suitcase swap | Marcy/Joe | x | [5 empty] | 6 | DAY | yes | Week 9/21 | During PSS commissioning
| Test Gun2 to 150kV | Joe |  | x |  |  |  |  | 1 | DAY | yes |  | Just before or after PSS commissioning
| 250/499 laser ready | EGG |  | x | x | FC1 | standard | 10 uA CW | 3 shift | DAY | maybe | October | Cables/attenuators, seed & IPG comm, IPG reset
| Commission new BCM0L02 receiver | Joe/Musson/Riad |  |  | x | FC2 | standard | 100 uA | 0.5 | DAY | yes | October | New electronics go in tunnel
| Bubble Commissioning | Riad |  |  | x | FC2 | 10 MeV | 100 uA | 1 week | DAY/SWING | limited ? | October | Request (not firm yet)
| Laser#4 @ 31 MHz | Hansknecht | x | [5 empty] | 1 day | DAY | no | mid-Sept | Digital gain switching laser #4 (only for Mott)
15065 | Mott Run II | Mott team |  |  | x | FC2 | 3-8 MeV | 10 uA | 3-4 days | 24/7 | no | October | Ideally have physics photocathode ready
| Test DBR | EGG | x | x | x | FC1/FC2 | standard | 1 mA /10 uA | 3 days | 24/7 | yes | October | QE, AP, P, emittance, lifetime
| Test Sb | EGG | x | x | x | FC1/FC2 | standard | 1 mA /10 uA | 3 days | 24/7 | yes | October | QE, AP, P, emittance, lifetime
| Test Brock as phase monitor | Joe/Curt |  | x |  | FC1 | 130 keV | 50 uA | 0.5 | DAY | yes | October | Can we use bunchlength 6GHz receiver?
| Activate photocathode for physics | EGG | x | [5 empty] | 1 | DAY | yes | Week 10/19 | SLSP-5247
| 3 beam injector restoration | EGG/INJ |  |  | x | FC2 | standard | 100 uA cw | 2 days | 24/7 | no | Week 10/26