## Sheet1
| Pros/Cons | Focus on HV gas conditioning tee and tee+shed Minimize dependence on S&A, Install Possibly wrap up PSS by end of Sep Defer the beamline work until mid-October | Focus on installing new cathode electrode Greater dependence on S&A, Install Needs PSS until mid-Oct Jump start vacuum work through Y
Date | Day | Strategy "A" | Strategy "B" | Comments
2020-09-21 | 1 | Install move DILO + PIG + Bake to tunnel Bypass the in-line NEG filters, bake line Add conditioning resistor | Install move DILO + PIG + Bake to tunnel Install move 2I and Y chamber to tunnel Bypass the in-line NEG filters, bake line Add conditioning resistor
2020-09-22 | 2 | Define laser launch + laser retroreflection Safe photocathodes + move dummy to cathode HV eval Wien filters | Define laser launch + laser retroreflection Safe photocathodes + move dummy to cathode HV eval Wien filters
2020-09-23 | 3 | HV eval + gas condition of tee | S&A as-found Gun2, 2I, … 2I and 1I disconnects
2020-09-24 | 4 | HV eval + gas condition of tee | Remove laser table Vent 1I, test gun valve for leaks Vent gun, blank and pump down
2020-09-25 | 5 | HV eval + gas condition of tee | Remove 2I and Y-chamber Install Y-chamber Drill and mount 2I solenoid
2020-09-26 | 6 | HV eval + gas condition of tee | Weekend
2020-09-27 | 7 | HV eval + gas condition of tee | Weekend
2020-09-28 | 8 | Breakpoint - 200 kV OK, then done w/ PSS | S&A install/align Y-chamber
2020-09-29 | 9 | S&A as-found of Gun2, 2I, … | Rework anode flange
2020-09-30 | 10 | Float | S&A install/align 2I beam pipe
2020-10-01 | 11 | Vent Gun2 S&A cathode for tee+shed Pump down Prep 2I line for bakeout | Vent Gun2 S&A cathode for tee+shed Pump down Prep 2I line for bakeout | Both plans are the same here
2020-10-02 | 12 | Leak check, setup and start bake | Leak check, setup and start bake
2020-10-03 | 13 | Bake | Bake
2020-10-04 | 14 | Bake | Bake
2020-10-05 | 15 | Bake | Bake
2020-10-06 | 16 | Bake | Bake
2020-10-07 | 17 | Ramp down, leak check | Ramp down, leak check
2020-10-08 | 18 | Re-assemble gun for HV tests | Re-assemble gun for HV tests
2020-10-09 | 19 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-10 | 20 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-11 | 21 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-12 | 22 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-13 | 23 | HV eval + gas condition of tee+shed | HV eval + gas condition of tee+shed
2020-10-14 | 24 | Breakpoint - Learn if tee+shed OK @ 200 kV | Breakpoint - Learn if tee+shed OK @ 200 kV
2020-10-15 | 25 | PSS expires 8am | PSS expires 8am
Formulas:
Date = [Date, row above]+1