## Sheet1
Quarter Year | 10 MeV Polarized e- Injector |  |  | 10 MeV Polarized e- Accumulator/Extractor |  |  | Polarized Positron Source
| Tasks | Procure | L | Tasks | Procure | Labor | Tasks | Procure | Labor
Oct-Dec 2016 | • Develop GPT simulation model of photogun and 10 MeV injector • Explore configurations at UITF and LERF |  |  | • Identify accumulator ring requirements • Explore linear optics designs • Develop preliminary linear optics design
Jan-Mar 2017 | • Perform GPT multivariate optimization of JLEIC and demo design parameters • Explore configurations at UITF and LERF • Finalize demo parameters (gun HV, laser rep rate, etc) • Model and simulation of diagnostics |  |  | • Conceptual design of the injection scheme • Specify injection scheme components and their parameters • Optimize the linear optics design for injection
Apr-Jun 2017 | • Test gun for operation at HV and with photocathode; e.g. HV condition UITF gun for >300 kV or explore high polarization photocathode at LERF • Order laser amplifer and hardware • Design and fab diagnostics |  |  | • Integrate injection system into the optics • Start beam dynamics simulations • Start considering instabilities
Jul-Sep 2017 | • Build and assemble laser • Commission gun for demo operation • Commission diagnostics |  |  | • Start beam injection simulations • Consider spin dynamics • Start beam dynamics simulations • Explore extraction options
Oct-Dec 2017 | • Beam tests & model benchmarking at gun votlage • Full demo parameters and beam power at gun voltage |  |  | • Downselection of the extraction system • Study misalignments • Design and simulate orbit correction system
Jan-Mar 2018 | • Beam tests and model benchmarking at 10 MeV • Full demo parameters for injection into figure-8 accumulator at allowed beam power |  |  | • Beam dynamics simulations with nonlinear field components and/or element field maps • Complete injection simulations and determine its performance
Apr-Jun 2018 | • Complete data analysis, conclusions, present findings |  |  | • Complete spin tracking simulations and specify spin control requirements • Identify potential instabilities and their mitigatin techniques • Start extraction simulations
Jul-Sep 2018 | • Summarize findings for pre-condeptual design report |  |  | • Start-to-end simulation • Specify parameters of all components
Oct-Dec 2018 | None |  |  | • Identify engineering tasks • Complete conceptual design report
Jan-Mar 2019 | None |  |  | • Comlete a cost estimate • Design a potentially simplified proof of principle experiment
Apr-Jun 2019 | None |  |  | • Simulate the proof-of-principle experiment • Cost the experiment
Jul-Sep 2019 | None |  |  | • Present findings • Prepare a proposal for the experimental test
Note on C4: Microsoft Office User: Eliminate?