## Slide 1: Status of Upgraded Injector Test Facility (UITF)
Matt Poelker
Status of UITF and dependence on CTF LHe (charge #1, 7, 9)
UITF goals: CEBAF injector, QCM tests, HDIce
Status of RadCon assessment, ARR, ASE, other approvals
Status of beam hardware & software control
Modes/Staff for providing beam
HDIce @ UITF – Experimental Readiness Review
November 19, 2019

## Slide 2: UITF is a 10 MeV spin-polarized electron accelerator
the UITF accelerator is built, ready to use….
(HV processing the gun now, buncher not yet commissioned, we have not made MeV beam yet)
Q. 1

## Slide 3: keV beamline commissioned*, RF applied to cold “Booster”, no MeV beam yet
* we are presently restoring operation of the photogun, cathode electrode was moved to CEBAF during SAD

## Slide 4: MeV beam….the accelerator
Run 0
Run 1
Design, construction, songsheets, software, everything is cabled up waiting for hot check out….

## Slide 5
“Standard” tools available at UITF, just like at CEBAF
Low duty factor modes of operation: Viewer Limited and Tune Mode
Viewers, BPMs, harps, current monitoring
Spectrometers, Yao cavity, and Brock bunchlength monitor
Ditherer to center beam in solenoids and quads
Elegant to predict device settings
Archiver, save/restore, twiddle save
Frame grabber, viewer image fitting tool, StepNGraph
Machine protection (FSD), chime
…
The elevated beamline is “normal”, no anticipated problems putting beam on the viewer and Faraday Cup upstream of the IBC

## Slide 6: Unique aspect of HDIce testing: low current CW, ~ 1 nA
After threading normal viewer-limited and tune-mode beam (100 nA ave current) to last viewer, we will:
insert the chopper slit to obtain nA CW beam at Faraday cup in front of IBC. Chopper slit current (i.e., beam that is dumped) serves as good gun current monitor
use viewers in CW mode as current monitors, one viewer in front, two dump viewers behind IBC. Viewer image intensity cross-calibrated against Faraday cup. Downstream viewer provides real-time current and position monitoring
apertures with proper holes prevent dumping beam on cell walls
if there's an earth’s-field bucking magnet between apertures, it will be interlocked
radiation monitors at apertures in front of IBC, and behind IBC. Beam trips OFF when radiation levels exceed nominal good readings
Rogowski coil (we hope) provides real-time beam position and current monitoring at nA current, it will serve as go/no go indicator, with fsd interlock to trip OFF beam
solenoid magnet will also be interlocked via fsd
Q. 5
Features that protect HDIce

## Slide 7: Test the Booster before installing at CEBAF in 2020
Our new “booster”:
2 cell capture section + 7 cell cavity,
should provide 10 MeV beam and introduce no x/y coupling, allow better matching, more adiabatic damping
Increase gun voltage and Wien filters for 200 kV operation to suppress space-charge effects and improve parity quality beam
Locate Wien filters (energy filters) upstream of pre-buncher cavity and install quadrupoles to better compensate astigmatism
Increase aperture of chopper and beam line solenoids to suppress existing astigmatism and improve parity quality beam
Install new SRF booster that eliminates warm-rf capture cavity, RF deflection and x/y coupling
“Booster” - sometimes we say QCM, or ¼ CM

## Slide 8: Test the spin-polarized target “HDIce”

## Slide 9: Past Reviews of UITF
Review #1: UITF Operations Review, aka “will it work?” March 18, 2016
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_March_18,_2016
Review #2: UITF Safety Review, May 10, 2016
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_May_10,_2016
Review #2.5: PSS BCM review *, October 21, 2016
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_October_21,_2016
Review #3: Conduct of Operations Review, April 24, 2019
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_April_24,_2019
Shielding Design Package, June 2019, JLAB-TN-18-020
Accelerator Readiness Review: June 26-28, 2019
  https://www.jlab.org/indico/event/322/timetable/#20190626
* the PSS BCM, once deemed necessary now deemed optional, following detailed shielding assessment
Q. 1

## Slide 10: Official Documentation
https://wiki.jlab.org/ciswiki/index.php/UITF_Official_Documents
https://www.jlab.org/eshq/ProgramDocs
These documents were approved by Lab Leadership and TJSO
Q. 1

## Slide 11: CATS items following ARR
Q. 1
all prestart findings have been addressed

## Slide 12: Post Start Findings of ARR – these should not impact timely HDIce testing
Q. 1
Post-start Findings will need to be addressed after Commissioning:

## Slide 13: Official Documentation
https://wiki.jlab.org/ciswiki/index.php/UITF_Safety_Documents
Q. 1

## Slide 14: Augmenting Cave2 Shielding
helium vent – used to maintain ODH0, ODH1 status

## Slide 15: Radiation Shielding Assessment and Commissioning Plan
https://wiki.jlab.org/ciswiki/index.php/UITF_Official_Documents
https://wiki.jlab.org/ciswiki/index.php/UITF_Safety_Documents
Shielding is adequate for 100 uA CW beam
Q. 9

## Slide 16
Table 1 of the UITF ARR Plan, presented to ARR Review Committee June 26-28, 2019
Q. 9

## Slide 17
Commissioning process “break points”, verify shielding is adequate
BLM locations (ILMM401, 601 and 701)
Good locations for spill tests:
proximity to control room and labyrinth
Q. 9

## Slide 18: MeV beam….the accelerator
Run 0
Run 1

## Slide 19: Note, we already tested Booster with RF at UITF (no beam acceleration)
Maximum beam energy at UITF?
16 MV/m x 0.7m = 11.2 MeV
(7-cell cavity effective length 0.7 m)
QCM commissioning results at UITF
 | Cavity 7 (2-cell) | Cavity 8 (7- cell)
QextFPC | 6.2E+06 | 9.9E+06
QextFP | 2.9E+12 | 2.3E+12
Emax (MV/m) | 16.5 | 18.0
Emaxop (MV/m) (1 Hour run) | 16.0 | 18.0
Limit | Quench | Forward Pwr
FE onset (MV/m) | 11.5 | 16.0
RF heat load at typical operating gradients | 9.5E+09 (< 1W at 6 MV/m) | 1.2E+10 (~12 W at 6 MV/m)
Static heat load | 20 W | 

## Slide 20: UITF “schedule”
HDIce proposed run schedule
done
waiting for permission
Buncher commissioning December
Booster commissioning January
January, February, March, April, May?
Q. 7

## Slide 21: UITF “schedule”
Task | Comment
Restore 200 kV beam operation (photogun bakeout, HV conditioning, activate photocathode) | Gun HV conditioning now
Commission the 200 kV buncher cavity | Having trouble hitting resonance
Obtain permission from TJSO to commission the "waist-height" accelerator | EH&S approval, Andrei to ask Stuart to ask TJSO
Set a date for commissioning "waist-height" beamline (Run #0) | hard to do without having permission to commission
coordinate with Cryo and SRF, u-tube swap at CTF, booster cool down | 
Engineering gets two weeks notice for HCO | 
HDIce completes work inside enclosure: magnet, dump, halo counter installation | now through…..
administrative tasks: beam authorization, shift plans, coordinate control room staffing approved operators | 
Commission the Booster | estimate one week of beam, no access to the enclosure
Obtain permission to operate UITF accelerator to test HDIce, another round of signatures | Is this time consuming?
Set a date for commissioning the elevated beamline (Run #1) | 
installation work, HDIce specific controls and diagnostics | 
Engineering gets two weeks notice for HCO | 
accelerator checks: beam size, energy spread, stability | 
HDIce specific checks: ragowski coil BPM calibration, raster magnets, fsd functionality, current calibration | 
Remove Booster and install at CEBAF | May-20
Install CEBAF 1/4 CM | 
Q. 7

## Slide 22: CTF Schedule
December 2019, send beam through warm booster, commission the buncher
Jan 2-9/20 commission cold booster and waist height accelerator
Opportunities for LHe, per schedule above:
Jan 31-Feb 16/20 (17 days = 4 d switch-overs + 13 d UITF OPS)
Mar 7-16/20 (10 days = 4 d switch-overs + 6 d UITF OPS)
Apr 11-May 5/20 (25 days = 4 d switch-overs + 21 d UITF OPS)
CTF is broken now, CM20 moved to LERF for testing, no plans for CMTF tests through 2019
Q. 7

## Slide 23: Approved UITF Operators (underlined names)
Gun Group (Center for Injectors and Sources)
Scientists: J. Grames, C. Hernandez-Garcia, M. A. Mamun, M. Poelker, R. Suleiman, M. Stutzman and S. Zhang
Technical staff: P. Adderley, B. Bullard, (plus replacement for John Hansknecht)
Graduate Students: G. Palacios, S. Wijiethunga, J. Yoskovitz
Injector Group
Scientists: R. Kazimi, Y. Wang, A. Hofler
24/7 operations seems required - there is insufficient staffing to support 24/7 operations
Q. 6

## Slide 24: UITF – Summary (a slide presented at JLAAC and P&C Meeting)
Testing the “booster” and HDIce target remain high priority tasks, now with “deadline” May 2020
Project started 2014…..now the Accelerator is built with three MeV beam destinations, waiting for permission to commission
Conduct of Operations Review, Shielding Design Package, and Accelerator Readiness Review
UOD, ASE and updated FSAD
Commissioning Plan and a number of OSPs
While working towards MeV operations, we have been using UITF as a Gun Test Stand:
  Tested a number of cathode electrodes, and two gun designs
  Modified Wien filter to operate at +/-20kV per plate, for 200 keV beam
  Assisted visiting scholar Max Herbert, testing LiCsNF3:GaAs, does lithium prolong operating lifetime?
  Installed the non-invasive resonant polarimeter from sbir-partner Electrodynamic, beam tests soon
When booster leaves UITF for CEBAF May 2020, we will install a traditional ¼ CM, and then we need 350 kV photogun (this is an R&D project for us)
Held Workshop on Uses of UITF
Nb3Sn coated cavities inside ¼ CM, waste water treatment, fast kicking, bubble chamber astrophysics experiment, PEPPo….all these topics represent potential R&D for UITF

## Slide 25: UITF – Summary (~ slide presented at JLAAC and P&C Meeting)
Future challenges:
  The Gun and Injector Groups (nominally, the people we originally imagined operating UITF) need to focus on the CEBAF injector upgrade, scheduled to start May 2020, ~ five months from now
  After Booster commissioning, HDice needs a minimum of three (preferably four) two-week run periods BEFORE the Booster is removed in May of 2020
  Formality of DOE requirements….suggests fulltime Facility Manager and Operations staffing required
  Liquid helium: the CTF refrigerator at building 58 cannot provide sufficient LHe to operate Vertical Test Area, Cryomodule Test Facility and UITF simultaneously
Q.6, Q.7

## Slide 26: What would be a good outcome of this ERR (Poelker opinion)
Recommendation for Operations to become more involved, especially in terms of admin tasks and beam delivery to support 24/7 operations
More help from Physics to push the approval process along
More help from Leadership, Accelerator, Engineering, Facilities and Physics to push for a CTF upgrade, to provide more LHe capactiy

## Slide 27
Back Up Slides

## Slide 28: Uses of UITF: workshop on December 12, 2018
Application | Beam Energy | Beam Current | Experiment Duration | Notes | Presenter
Commission QCM for CEBAF | 6 MeV, but prefer up to 10 MeV | up to 100 uA | three or four 1-week long tests | tests complete before long shutdown of 2020, when QCM to be installed at CEBAF | R. Kazimi
Commission HDIce for CEBAF | ~ 8 MeV | up to 100 nA for tuning, 0.25 to 5 nA for production | four or five run periods, two-weeks long each | target provides transverse polarization required for 3 A-rated Hall B experiments | A. Sandorfi
Manufacturing polarized targets for CEBAF via DNP | 10 to 18 MeV | 1 to 10 uA | hours, days | likely some R&D to determine optimum polarizing conditions | C. Keith
Bubble Chamber astrophysics | 4 - 10 MeV | 0.01 to 100 uA | 3 weeks, ~ 3 runs/year | UITF better location than CEBAF injector, when CEBAF shutdowns are short | R. Suleiman
MeV parity violation experiment | 10 MeV | milliamps preferred, will reduce experiment duration | months to years | requires polarized electron beam, transmission geometry offers advantages | R. Carlini
Testing Nb3Sn-coated cavities | determining the beam energy of test cavity is point of test | up to 100 uA | as many tests as possible | Nb3Sn cavities require only 4K Helium | G. Eremeev
Wastewater treatment | 2- 10 MeV | 100 uA | imagine week-long test durations over three years | together with local partners | G. Ciovati
Polarized positron source | 5 - 10 MeV | up to 100 uA | staged tests, likely many required, 1-week long duration | requires polarized electron beam | J. Grames
EIC: fast kicker tests | 5 - 10 MeV | up to 100 uA | two 1-week long tests | together with sbir-partner | H. Wang
EIC: testing high bunch charge | 5 - 10 MeV | up to 100 uA | two 1-week long tests | requires polarized electron beam | J. Grames and J. Guo
https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_December_12,_2018