## Sheet1
Quarter Year | 10 MeV Polarized e- Injector |  | 10 MeV Polarized e- Accumulator/Extractor |  | Polarized Positron Source
| Tasks | Procure | Tasks | Procure | Tasks | Procure
Oct-Dec 2016 | • Develop GPT simulation model of photogun and 10 MeV injector • Explore configurations at UITF and LERF |  | • Identify accumulator ring requirements • Explore linear optics designs • Develop preliminary linear optics design |  | • Identify electron beam parameter space at target • Identify typical 5MeV input acceptance at CEBAF
Jan-Mar 2017 | • Perform GPT multivariate optimization of JLEIC and demo design parameters • Explore configurations at UITF and LERF • Finalize demo parameters (gun HV, laser rep rate, etc) • Model and simulation of diagnostics |  | • Conceptual design of the injection scheme • Specify injection scheme components and their parameters • Optimize the linear optics design for injection |  | • Simulate and compare positron distributions from W and Pb/Bi targets • Develop preliminary model of target and collection
Apr-Jun 2017 | • Test gun for operation at HV and with photocathode; e.g. HV condition UITF gun for >300 kV or explore high polarization photocathode at LERF • Order laser amplifer and hardware • Design and fab diagnostics |  | • Integrate injection system into the optics • Start beam dynamics simulations • Start considering instabilities |  | • Start simulating collection by solenoid, AMD, quad to identify most promising method * Explore solenoid, AMD options we have access to
Jul-Sep 2017 | • Build and assemble laser • Commission gun for demo operation • Commission diagnostics |  | • Start beam injection simulations • Consider spin dynamics • Start beam dynamics simulations • Explore extraction options • Hire a postdoc |  | • Determine optimum target thicknes • Study sensitivity to input electron beam parameters • Get a new hire involved
Oct-Dec 2017 | • Beam tests & model benchmarking at gun votlage • Full demo parameters and beam power at gun voltage |  | • Downselection of the extraction system • Study misalignments • Design and simulate orbit correction system |  | • Integrate beam/target/collection • Compare collection options and downselect • Begin a start-to-end simulation
Jan-Mar 2018 | • Beam tests and model benchmarking at 10 MeV • Full demo parameters for injection into figure-8 accumulator at allowed beam power |  | • Beam dynamics simulations with nonlinear field components and/or element field maps • Complete injection simulations and determine its performance |  | • Optimize the selected collection system • Dowselect target, collection, shielding
Apr-Jun 2018 | • Complete data analysis, conclusions, present findings |  | • Complete spin tracking simulations and specify spin control requirements • Identify potential instabilities and their mitigatin techniques • Start extraction simulations |  | • Identify diagnostic components, capitalize on PEPPo, Mag Cooler • Explore supressing e- drive beam, backgrounds * Simulate management of beam, shielding
Jul-Sep 2018 | • Summarize findings for pre-condeptual design report |  | • Start-to-end simulation • Specify parameters of all components |  | • Design/simulation new diagnostic (RF, slit) • Identify engineering tasks
Oct-Dec 2018 | None |  | • Identify engineering tasks • Complete conceptual design report |  | • Complete conceptual design report • Comlete a cost estimate
Jan-Mar 2019 | None |  | • Comlete a cost estimate • Design a potentially simplified proof of principle experiment |  | • Design a potentially simplified proof of principle experiment • Simulate the proof-of-principle experiment
Apr-Jun 2019 | None |  | • Simulate the proof-of-principle experiment • Cost the experiment |  | • Cost the experiment • Prepare a proposal for the experimental test
Jul-Sep 2019 | None |  | • Present findings • Prepare a proposal for the experimental test |  | • Present findings
Note on C4: Microsoft Office User: Eliminate?