## Slide 1: 2023 Objectives & Milestones
Lab management is developing an N year profile for LERF e+ source, Ce+BAF 12 GeV, Energy Upgrade
If we say N=1 is 2023 then we have some homework…
  January 31st – first estimate of scope/resource/schedule for LERF e+ source (Y1, Y2, …)
    Carlos – polarized e- source (photogun, Wien filter, drive laser, HV systems)
    Reza – electron injector (warm and cold beamlines – everything except SRF)
    Tony/Curt – e- SRF linac/rf power (QCM repair, C75) and low current e+ SRF (C100)
    Silviu – High power e+ source target (vacuum integration, water-cooled spinning target)
    Probir – NC/SC e+ source magnets (solenoid capture magnet, linac capture magnet)
    Bob/Curt – Capture linac/rf power (NC/SC linac, klystrons)
    Yves – Transport beam lines (layout magnet count/type, coordinate with Fanglei spin rotator)
    Joe – Eng resources (RCG, SSG, DC, RF, I&C, OPS, VAC) and circling back with everyone
  Ce+BAF WG – start-to-end conceptual design and feasability report
    Apr 1 – IPAC’23 contributions status of R&D development
    Jun 1 – distribute outline and writing assignments
    Sep 1 – first drafts due at +3 months
    Dec 1 – final material due at +6 months