## Rev 0 & 1
NOW |  | AIPINJ |  |  |  | Alicia's Review |  | Grames status (Aug 17 2020)
Region | Name | Region | Component | At same "Z"/Co-located | Name | Your name column! (Max Reuse) | Ideally for 2I elements | FINAL LIST | INSTALL STATUS
Region 0 | VIP2I01A | Region 0 | Ion pump | x | VIP2I01A |  |  | VIP2I01A | Exists in tunnel
| VIP2I01B |  | Ion pump | x | VIP2I01B |  |  | VIP2I01B | Exists in tunnel
| VIP2I01C |  | Ion pump | x | VIP2I01C |  |  | VIP2I01C | Exists in tunnel
| ILL2I01DCANO |  | Gun anode | x | ILL2I01DCANO |  |  | ILL2I01DCANO | Ready to install
| VIP2I01 |  | Gun pump | x | VIP2I01 |  |  | VIP2I01 | Exists in tunnel
VIP3I01
VBV3I02
Region 1 | MBH2I01H | Region 1 | Cor-H | x | MBH2I01H |  | MBH2I00H | MBH2I00H | Exists in tunnel
| MBH2I01V |  | Cor-V |  | MBH2I01V |  | MBH2I00V | MBH2I00V | Exists in tunnel
| IPM2I01 |  | BPM |  | IPM2I01 |  | IPM2I00 | IPM2I00 | Musson mapping
| MBH2I02H |  | Cor-H | x | MBH2I02H |  | MBH2I00AH | MBH2I00AH | Exists in tunnel
| MBH2I02V |  | Cor-V |  | MBH2I02V |  | MBH2I00AV | MBH2I00AV | Exists in tunnel
| MFH2I01 |  | BPM |  | IPM2I02 |  | IPM2I00A | IPM2I00A | Musson mapping
| MBH2I03H |  | Solenoid | x | MFX2I01 | MFX2I03 | MFX2I01 | MFX2I01 | NEG coating
| MBH2I03V |  | Cor-H | x |  | MBH2I03H | MBH2I01H | MBH2I01H | Need BH-H
| IPM2I02 |  | Cor-V |  |  | MBH2I03V | MBH2I01V | MBH2I01V | Need BH-V
| VBV2I02 |  | Cor-H | x | MBH2I03H | MBH2I03AH | MBH2I01AH | MBH2I01AH | Exists in tunnel
|  |  | Cor-V |  | MBH2I03V | MBH2I03AV | MBH2I01AV | MBH2I01AV | Exists in tunnel
|  |  | BPM |  | IPM2I03 | IPM2I03A | IPM2I01A | IPM2I01A | Musson mapping
|  |  | Valve | x | VBV2I02V (*ending V typo?) | VBV2I03 | VDV2I01A | VBV2I01A | Exists in tunnel
Region 2 | ITV2I02 | Region 2 | Viewer | x | ITV2I02 | ITV2I03 | ITV2I01 | ITV2I01 | Rework top hat & shield in new Y-chamber
| VIP1I01 |  | Ion pump | x | VIP1I01 |  |  | VIP1I01 | Exists in tunnel
| MDS1I01 |  | 15 dipole | x | MDT1I02 | MDR1I02 |  | MDR1I02 | Milhous is winding now
| ITV1I02 |  | Viewer | x | ITV1I02 |  |  | ITV1I02 | Rework top hat & shield in new Y-chamber
| VIP1I02 |  | Ion pump | x | VIP1I02 |  |  | VIP1I02 | Exists in tunnel
| IPM1I02 |  | Cor-H | x | MBH1I02H |  |  | MBH1I02H | Exists in tunnel
| MBH1I02H |  | Cor-V |  | MBH1I02V |  |  | MBH1I02V | Exists in tunnel
| MBH1I02V |  | BPM |  | IPM1I02 |  |  | IPM1I02 | Exists in tunnel
| MFB1I02 |  | Solenoid | x | MFX1I02 | MFX1I03 |  | MFX1I03 | Mapping completed, ready for alignment
Region 3 | MHB1I03H | Region 3 | Cor-H | x | MBH1I03H |  |  | MBH1I03H | Exists in tunnel
| MHB1I03V |  | Cor-V |  | MBH1I03V |  |  | MBH1I03V | Exists in tunnel
|  |  | BPM |  | IPM1I03 |  |  | IPM1I03 | Exists in tunnel
| MQW1I03 |  | Wien quad | x | MQW1I03 |  |  | MQW1I03 | In design phase
| ITV1I03 |  | Viewer |  | ITV1I03 |  |  | ITV1I03 | Rework top hat? Or use as is???
| VIP1I03 |  | Ion pump |  | VIP1I03 |  |  | VIP1I03 | Exists in tunnel
| MWF1I04 |  | Vert. Wien | x | MWF1I04 |  |  | MWF1I04 | In testing phase
| MQW1I04 |  | Wien quad | x | MQW1I04 |  |  | MQW1I04 | In design phase
| ITV1I04 |  | Viewer |  | ITV1I04 |  |  | ITV1I04 | Rework top hat? Or use as is???
| VIP1I04 |  | Ion pump |  | VIP1I04 |  |  | VIP1I04 | Exists in tunnel
| MBH1I04H |  | Cor-H | x | MBH1I04H |  |  | MBH1I04H | Exists in tunnel
| MBH1I04V |  | Cor-V |  | MBH1I04V |  |  | MBH1I04V | Exists in tunnel
| IPM1I04 |  | BPM |  | IPM1I04 |  |  | IPM1I04 | Exists in tunnel
| MFG1I04A |  | Solenoid | x | MFG1I04A |  |  | MFG1I04A | Exists in tunnel
| MFG1I04B |  | Solenoid | x | MFG1I04B |  |  | MFG1I04B | Exists in tunnel
| MHB1I05H |  | Cor-H | x | MHB1I05H |  |  | MHB1I05H | Exists in tunnel
| MHB1I05V |  | Cor-V |  | MHB1I05V |  |  | MHB1I05V | Exists in tunnel
|  |  | IPM |  | IPM1I05 |  |  | IPM1I05 | Exists in tunnel
| VDP1I05 |  | Wien quad | x | MQW1I05 |  |  | MQW1I05 | In design phase
| VIP1I05 |  | Viewer |  | ITV1I05 |  |  | ITV1I05 | Rework top hat? Or use as is???
| RIN1I05 |  | Ion pump |  | VIP1I05 |  |  | VIP1I05 | Exists in tunnel
|  |  | Hor. Wien | x | MWF1I06 |  |  | MWF1I06 | In testing phase
|  |  | Wien quad | x | MQW1I06 |  |  | MQW1I06 | In design phase
| IHA1I06 |  | Viewer |  | ITV1I06 |  |  | ITV1I06 | Rework top hat? Or use as is???
| IPM1I06 |  | Ion pump |  | VIP1I06 |  |  | VIP1I06 | Exists in tunnel
| MBH1I06H |  | Prebuncher | x | RIN1I06 |  |  | RIN1I06 | In fabrication phase
| MBH1I06V |  | Cor-H | x | MBH1I07H |  |  | MBH1I07H | Exists in tunnel
| IFY1I07 |  | Cor-V |  | MBH1I07V |  |  | MBH1I07V | Exists in tunnel
| ITV1I07 |  | BPM |  | IPM1I07 |  |  | IPM1I07 | Exists in tunnel
VIP1I07
Region 4 | VBV1I07 | Region 4 | Valve | x | VBV1I07 |  |  | VBV1I07 | Exists in tunnel
| MFQ0I01 |  | Diff pump | x | VDP0I01 |  |  | VDP0I01 | Install new NEGs
| MBH0I01H |  | Ion pump | x | VIP0I01 |  |  | VIP0I01 | Exists in tunnel
| MBH0I01V |  | Solenoid | x | MFX0I01 |  |  | MFX0I01 | ETI delivery on schedule
| MQU0I01 |  | Cor-H | x | MBH0I01H |  |  | MBH0I01H | Exists in tunnel
| IPM0I01 |  | Cor-V |  | MBH0I01V |  |  | MBH0I01V | Exists in tunnel
| SBK0I01 |  | BPM |  | IPM0I01 |  |  | IPM0I01 | Exists in tunnel
| IPM0I01A |  | Viewer | x | ITV0I01 |  |  | ITV0I01 | Rework top hat? Or use as is???
| VIP0I01 |  | Pcup |  | IFY0I01 |  |  | IFY0I01 | Exists in tunnel
| ITV0I01 |  | Ion pump |  | VIP0I01A |  |  | VIP0I01A | Exists in tunnel
| MQW0I01A |  | A1 aperture | x | IFY0IA1 |  |  | IFY0IA1 | Cubes on hand, to be machined
| IFY0I01 |  | Ion pump |  | VIP0I01B |  |  | VIP0I01B | Exists in tunnel
| MHD0I01AH |  | Cor-H |  | MHD0I01AH |  |  | MHD0I01AH | New coil design, waiting on bids
| MHD0I01AV |  | Cor-V |  | MHD0I01AV |  |  | MHD0I01AV | New coil design, waiting on bids
| ICB0I01 |  | Cor-H | x | MBH0I01BH |  |  | MBH0I01BH | Exists in tunnel
| MWF0I02 |  | Cor-V |  | MBH0I01BV |  |  | MBH0I01BV | Exists in tunnel
| IPM0I02 |  | BPM |  | IPM0I01A | IPM0I01B |  | IPM0I01B | Exists in tunnel
| MQU0I02 |  | PSS Kicker | x | SBK0I01 |  |  | SBK0I01 | Finish kicker design, bid and fabricate
| MBH0I02H |  | Valve | x | VBV0I02 |  |  | VBV0I02 | New gate value here
| MBH0I02V |  | Viewer | x | ITV0I02 |  |  | ITV0I02 | Rework top hat? Or use as is???
| ITV0I02 |  | Harp |  | IHA0I02 |  |  | IHA0I02 | Exists in tunnel
| IHA0I02 |  | A2 aperture | x | IFY0I02 (* typo?) | IFY0IA2 |  | IFY0IA2 | Cubes on hand, to be machined
| IFY0IA2 |  | Ion pump |  | VIP0I02 |  |  | VIP0I02 | Exists in tunnel
| VIP0I02 |  | Cor-H |  | MHD0I02H |  |  | MHD0I02H | New coil design, waiting on bids
| IPM0I02A |  | Cor-V |  | MHD0I02V |  |  | MHD0I02V | New coil design, waiting on bids
MBH0I02AH
MBH0I02AV
MQU0I02A
VBV0I02

## Rev 2
Color Codes for Boxes
Name exists (I think) | Done, exists, ready to use
New name | In process, good plan, not missing something
Still in design phase, missing parts, undecided
Grames status (Aug 17 2020)
FINAL LIST | STATUS
VIP2I01A | Exists in tunnel
VIP2I01B | Exists in tunnel
VIP2I01C | Exists in tunnel
ILL2I01DCANO | Ready to install
VIP2I01 | Exists in tunnel
MBH2I00H | Exists in tunnel
MBH2I00V | Exists in tunnel
IPM2I00 | Musson mapping
MBH2I00AH | Exists in tunnel
MBH2I00AV | Exists in tunnel
IPM2I00A | Musson mapping
MFX2I01 | NEG coating
MBH2I01H | Need BH-H
MBH2I01V | Need BH-V
MBH2I01AH | Exists in tunnel
MBH2I01AV | Exists in tunnel
IPM2I01A | Musson mapping
VBV2I01A | Exists in tunnel
ITV2I01 | Rework top hat & shield in new Y-chamber | garage ready for tack welding
VIP1I01 | Exists in tunnel | VNEG1I01 | I don't know if we want to note these on the songsheets.
MDR1I02 | Milhous is winding now
ITV1I02 | Rework top hat & shield in new Y-chamber | garage ready for tack welding
VIP1I02 | Exists in tunnel | VNEG1I02
MBH1I02H | Exists in tunnel
MBH1I02V | Exists in tunnel
IPM1I02 | Exists in tunnel
MFX1I03 | Mapping completed, ready for alignment
MBH1I03H | Exists in tunnel
MBH1I03V | Exists in tunnel
IPM1I03 | Exists in tunnel
MQW1I03 | In design phase
ITV1I03 | Rework top hat? Or use as is??? | replace bellows, determine if we need new tophat/flag
VIP1I03 | Exists in tunnel | VNEG1I03
MWF1I04 | In testing phase
MQW1I04 | In design phase
ITV1I04 | Rework top hat? Or use as is??? | replace bellows, determine if we need new tophat/flag
VIP1I04 | Exists in tunnel | VNEG1I04
MBH1I04H | Exists in tunnel
MBH1I04V | Exists in tunnel
IPM1I04 | Exists in tunnel
MFG1I04A | Exists in tunnel
MFG1I04B | Exists in tunnel
MHB1I05H | Exists in tunnel
MHB1I05V | Exists in tunnel
IPM1I05 | Exists in tunnel
MQW1I05 | In design phase
ITV1I05 | Rework top hat? Or use as is??? | replace bellows, determine if we need new tophat/flag
VIP1I05 | Exists in tunnel | VNEG1I05
MWF1I06 | In testing phase
MQW1I06 | In design phase
ITV1I06 | Rework top hat? Or use as is??? | replace bellows, determine if we need new tophat/flag
VIP1I06 | Exists in tunnel | VNEG1I06
RIN1I06 | In fabrication phase
MBH1I07H | Exists in tunnel
MBH1I07V | Exists in tunnel
IPM1I07 | Exists in tunnel
VBV1I07 | Exists in tunnel
VDP0I01 | Install new NEGs: Agreed to leave these intact, install all 4 new ones at y chamber
VIP0I01 | Exists in tunnel | the ion pump from VDP1I05 needs to be cleaned
MFX0I01 | ETI delivery on schedule
MBH0I01H | Exists in tunnel
MBH0I01V | Exists in tunnel
IPM0I01 | Exists in tunnel
ITV0I01 | Rework top hat? Or use as is??? | replace bellows, determine if we need new tophat/flag
IFY0I01 | Exists in tunnel
VIP0I01A | Exists in tunnel
IFY0IA1 | Cubes on hand, to be machined
VIP0I01B | Exists in tunnel | VNEG0I08B
MHD0I01AH | New coil design, waiting on bids
MHD0I01AV | New coil design, waiting on bids
MBH0I01BH | Exists in tunnel
MBH0I01BV | Exists in tunnel
IPM0I01B | Exists in tunnel
SBK0I01 | Finish kicker design, bid and fabricate
VBV0I02 | New gate value here
ITV0I02 | Rework top hat? Or use as is??? | replace bellows, determine if we need new tophat/flag
IHA0I02 | Exists in tunnel
IFY0IA2 | Cubes on hand, to be machined
VIP0I02 | Exists in tunnel | VNEG0I02
MHD0I02H | New coil design, waiting on bids
MHD0I02V | New coil design, waiting on bids

## Rev 3
Color Codes for Boxes
| Name exists (I think) | Done, exists, ready to use
| New name | In process, good plan, not missing something
| This box means same location | Still in design phase, missing parts, undecided
Reviewed by Grames, Hofler, Turner, Stutzman (Aug 17 2020)
REGION | NAME | STATUS
0 | VIP2I01A | Exists in tunnel
| VIP2I01B | Exists in tunnel
| VIP2I01C | Exists in tunnel
| ILL2I01DCANO | Ready to install
| VIP2I01 | Exists in tunnel
1 | MBH2I00H | Exists in tunnel
| MBH2I00V | Exists in tunnel
| IPM2I00 | Musson mapping
| MBH2I00AH | Exists in tunnel
| MBH2I00AV | Exists in tunnel
| IPM2I00A | Musson mapping
| MFX2I01 | NEG coating
| MBH2I01H | Need BH-H
| MBH2I01V | Need BH-V
| MBH2I01AH | Exists in tunnel
| MBH2I01AV | Exists in tunnel
| IPM2I01A | Musson mapping
| VBV2I01A | Exists in tunnel
2 | ITV2I01 | garage ready for tack welding
| VIP1I01 | Exists in tunnel
| VNG1I01 | Build up new NEG's on Y-chamber flange
| MDR1I02 | Milhous is winding now
| ITV1I02 | garage ready for tack welding
| VIP1I02 | Exists in tunnel
| VNG1I02 | New NEG on pump
| MBH1I02H | Exists in tunnel
| MBH1I02V | Exists in tunnel
| IPM1I02 | Exists in tunnel
| MFX1I03 | Mapping completed, ready for alignment
3 | MBH1I03H | Exists in tunnel
| MBH1I03V | Exists in tunnel
| IPM1I03 | Exists in tunnel
| MQW1I03 | In design phase
| ITV1I03 | replace bellows, determine if we need new tophat/flag
| VIP1I03 | Exists in tunnel
| VNG1I03 | Add new capaciTorr
| MWF1I04 | In testing phase
| MQW1I04 | In design phase
| ITV1I04 | replace bellows, determine if we need new tophat/flag
| VIP1I04 | Exists in tunnel
| VNG1I03 | Add new capaciTorr
| MBH1I04H | Exists in tunnel
| MBH1I04V | Exists in tunnel
| IPM1I04 | Exists in tunnel
| MFG1I04A | Exists in tunnel
| MFG1I04B | Exists in tunnel
| MHB1I05H | Exists in tunnel
| MHB1I05V | Exists in tunnel
| IPM1I05 | Exists in tunnel
| MQW1I05 | In design phase
| ITV1I05 | replace bellows, determine if we need new tophat/flag
| VIP1I05 | Exists in tunnel
| VNG1I05 | Add new capaciTorr
| MWF1I06 | In testing phase
| MQW1I06 | In design phase
| ITV1I06 | replace bellows, determine if we need new tophat/flag
| VIP1I06 | Exists in tunnel
| VNG1I06 | Add new capaciTorr
| RIN1I06 | In fabrication phase
| MBH1I07H | Exists in tunnel
| MBH1I07V | Exists in tunnel
| IPM1I07 | Exists in tunnel
4 | VBV1I07 | Exists in tunnel
| VDP0I01 | Leave NEG intact
| VIP0I01 | the ion pump from VDP1I05 needs to be cleaned
| MFX0I01 | ETI delivery on schedule
| MBH0I01H | Exists in tunnel
| MBH0I01V | Exists in tunnel
| IPM0I01 | Exists in tunnel
| ITV0I01 | replace bellows, determine if we need new tophat/flag
| IFY0I01 | Exists in tunnel
| VIP0I01A | Exists in tunnel
| IFY0IA1 | Cubes on hand, to be machined
| VIP0I01B | Exists in tunnel
| MHD0I01AH | New coil design, waiting on bids
| MHD0I01AV | New coil design, waiting on bids
| MBH0I01BH | Exists in tunnel
| MBH0I01BV | Exists in tunnel
| IPM0I01B | Exists in tunnel
| SBK0I01 | Finish kicker design, bid and fabricate
| VBV0I02 | New gate value here
| ITV0I02 | replace bellows, determine if we need new tophat/flag
| IHA0I02 | Exists in tunnel
| IFY0IA2 | Cubes on hand, to be machined
| VIP0I02 | Exists in tunnel
| VNG0I02 | Add NEG
| MHD0I02H | New coil design, waiting on bids
| MHD0I02V | New coil design, waiting on bids

## Rev 4
Color Codes for Boxes
| Name exists (I think) | Done, exists, ready to use
| New name | In process, good plan, not missing something
| This box means same location | Still in design phase, missing parts, undecided
Reviewed by Grames, Hofler, Turner, Stutzman (Aug 17 2020)
REGION | NAME | STATUS
0 | VIP2I01A | Exists in tunnel
| VIP2I01B | Exists in tunnel
| VIP2I01C | Exists in tunnel
| ILL2I01DCANO | Ready to install
| VIP2I01 | Exists in tunnel
1 | MBH2I00H | Exists in tunnel
| MBH2I00V | Exists in tunnel
| IPM2I00 | Musson mapping
| MBH2I00AH | Exists in tunnel
| MBH2I00AV | Exists in tunnel
| IPM2I00A | Musson mapping
| MFX2I01 | NEG coating
| MBH2I01H | Need BH-H
| MBH2I01V | Need BH-V
| MBH2I01AH | Exists in tunnel
| MBH2I01AV | Exists in tunnel
| IPM2I01A | Musson mapping
| VBV2I01A | Exists in tunnel
2 | ITV2I01 | garage ready for tack welding
| VIP1I01 | Exists in tunnel
| VGP1I01 | Build up new NEG's on Y-chamber flange
| MDR1I02 | Milhous is winding now
| ITV1I02 | garage ready for tack welding
| VIP1I02 | Exists in tunnel
| VGP1I02 | New NEG on pump
| MBH1I02H | Exists in tunnel
| MBH1I02V | Exists in tunnel
| IPM1I02 | Exists in tunnel
| MFX1I03 | Mapping completed, ready for alignment
3 | MBH1I03H | Exists in tunnel
| MBH1I03V | Exists in tunnel
| IPM1I03 | Exists in tunnel
| MQW1I03 | In design phase
| ITV1I03 | replace bellows, determine if we need new tophat/flag
| VIP1I03 | Exists in tunnel
| VGP1I03 | Add new capaciTorr
| MWF1I04 | In testing phase
| MQW1I04 | In design phase
| ITV1I04 | replace bellows, determine if we need new tophat/flag
| VIP1I04 | Exists in tunnel
| VGP1I03 | Add new capaciTorr
| MBH1I04H | Exists in tunnel
| MBH1I04V | Exists in tunnel
| IPM1I04 | Exists in tunnel
| MFG1I04A | Exists in tunnel
| MFG1I04B | Exists in tunnel
| MHB1I05H | Exists in tunnel
| MHB1I05V | Exists in tunnel
| IPM1I05 | Exists in tunnel
| MQW1I05 | In design phase
| ITV1I05 | replace bellows, determine if we need new tophat/flag
| VIP1I05 | Exists in tunnel
| VGP1I05 | Add new capaciTorr
| MWF1I06 | In testing phase
| MQW1I06 | In design phase
| ITV1I06 | replace bellows, determine if we need new tophat/flag
| VIP1I06 | Exists in tunnel
| VGP1I06 | Add new capaciTorr
| RIN1I06 | In fabrication phase
| MBH1I07H | Exists in tunnel
| MBH1I07V | Exists in tunnel
| IPM1I07 | Exists in tunnel
4 | VBV1I07 | Exists in tunnel
| VDP0I01 | Leave NEG intact
| VIP0I01 | the ion pump from VDP1I05 needs to be cleaned
| MFX0I01 | ETI delivery on schedule
| MBH0I01H | Exists in tunnel
| MBH0I01V | Exists in tunnel
| IPM0I01 | Exists in tunnel
| ITV0I01 | replace bellows, determine if we need new tophat/flag
| IFY0I01 | Exists in tunnel
| VIP0I01A | Exists in tunnel
| IFY0IA1 | Cubes on hand, to be machined
| VIP0I01B | Exists in tunnel
| MHD0I01AH | New coil design, waiting on bids
| MHD0I01AV | New coil design, waiting on bids
| MBH0I01BH | Exists in tunnel
| MBH0I01BV | Exists in tunnel
| IPM0I01B | Exists in tunnel
| SBK0I01 | Finish kicker design, bid and fabricate
| VBV0I02 | New gate value here
| ITV0I02 | replace bellows, determine if we need new tophat/flag
| IHA0I02 | Exists in tunnel
| IFY0IA2 | Cubes on hand, to be machined
| VIP0I02 | Exists in tunnel
| VGP0I02 | Add NEG
| MHD0I02H | New coil design, waiting on bids
| MHD0I02V | New coil design, waiting on bids

## Rev 5
Color Codes for Boxes
| Name exists (I think) | Done, exists, ready to use | Layout updated
| New name | In process, good plan, not missing something
| This box means same location | Still in design phase, missing parts, undecided
| Reviewed by Grames, Hofler, Turner, Stutzman (Aug 17 2020) |  | Changes reflect edits by Machie, Stutzman, Hofler (Aug 27 2020)
REGION | NAME | STATUS | Changes from Rev 4 to 5
0 | VIP2I01A | Exists in tunnel
| VIP2I01B | Exists in tunnel
| VIP2I01C | Exists in tunnel
| ILL2I01DCANO | Ready to install
| VIP2I01 | Exists in tunnel
1 | MBH2I00H | Exists in tunnel
| MBH2I00V | Exists in tunnel
| IPM2I00 | BPM #1 wire fixed, re-map | Status updated
| MBH2I00AH | Exists in tunnel
| MBH2I00AV | Exists in tunnel
| IPM2I00A | BPM #2 mapped OK, re-map larger Y-direction | Status updated
| MFX2I01 | Magnet mapped, pipe NEG coated | Status updated
| MBH2I01H | BH-H on-hand | Status updated
| MBH2I01V | BH-V on-hand | Status updated
| MBH2I01AH | Exists in tunnel
| MBH2I01AV | Exists in tunnel
| IPM2I01A | BPM #3 wire fiixed, re-map | Status updated
| VBV2I01A | Exists in tunnel
2 | ITV2I01 | Garages tacked welded, Phil needs parts to rebuild | Status updated
| VRV1I01 | From tunnel or on-hand | Added right angle valve
| VIP1I01 | Exists in tunnel
| VGP1I01 | Build up new NEG's on Y-chamber flange | Comment: Call all 4 by one name, like a DP can
| MDR1I02 | 1st winding not met spec, Milhous re-winding now | Status updated
| ITV1I02 | Garages tacked welded, Phil needs parts to rebuild | Status updated
| VIP1I02 | Exists in tunnel
| VGP1I02 | New NEG on pump | Correct eliminate VGP1I02
| MBH1I02H | Exists in tunnel
| MBH1I02V | Exists in tunnel
| IPM1I02 | Exists in tunnel
| MFX1I03 | Mapping completed, ready for alignment | Status updated
3 | MBH1I03H | Exists in tunnel
| MBH1I03V | Exists in tunnel
| IPM1I03 | Exists in tunnel
| MQW1I03 | Initial designs done, ~2 wks to complete/bid | Status updated
| ITV1I03 | replace bellows, determine if we need new tophat/flag
| VIP1I03 | Exists in tunnel
| VGP1I03 | Add new capaciTorr
| MWF1I04 (vertical) | Test tunnel electrodes, design spares | Status updated
| MQW1I04 | Initial designs done, ~2 wks to complete/bid | Status updated
| ITV1I04 | replace bellows, determine if we need new tophat/flag | Status updated
| VIP1I04 | Exists in tunnel
| VGP1I04 | Add new capaciTorr | Corrected VGP1I03 => VGP1I04
| MBH1I04H | Exists in tunnel
| MBH1I04V | Exists in tunnel
| IPM1I04 | Exists in tunnel
| MFG1I04A | Exists in tunnel
| MFG1I04B | Exists in tunnel
| MBH1I05H | Exists in tunnel | Corrected "HB" => "BH"
| MHB1I05V | Exists in tunnel | Corrected "HB" => "BH"
| IPM1I05 | Exists in tunnel
| MQW1I05 | Initial designs done, ~2 wks to complete/bid | Status updated
| ITV1I05 | replace bellows, determine if we need new tophat/flag
| VIP1I05 | Exists in tunnel
| VGP1I05 | Add new capaciTorr
| MWF1I06 (horizontal) | Test tunnel electrodes, design spares | Status updated
| MQW1I06 | Initial designs done, ~2 wks to complete/bid | Status updated
| ITV1I06 | missing this viewer assembly, ordering chromox screen | Status updated
| VIP1I06 | Exists in tunnel
| VRV1I06 | From tunnel or on-hand | Added right angle valve
| VGP1I06 | Add new capaciTorr
| RIN1I06 (pre-buncher) | >50% complete, iterating skim cuts, then braze | Status updated
| MBH1I07H | Exists in tunnel
| MBH1I07V | Exists in tunnel
| IPM1I07 | Exists in tunnel
4 | VBV1I07 | Exists in tunnel
| VDP0I01 | Leave NEG intact
| VIP0I01 | the ion pump from VDP1I05 needs to be cleaned
| VRV0I01 | From tunnel or on-hand | Added right angle valve
| MFX0I01 | ETI delivery on schedule, additional vee blocks ordered | Status updated
| MBH0I01H | Exists in tunnel
| MBH0I01V | Exists in tunnel
| IPM0I01 | Exists in tunnel
| ITV0I01 | Garages tacked welded, Phil needs parts to rebuild | Status updated
| IFY0I01 | Exists in tunnel
| VIP0I01A | Exists in tunnel
| VGP0I01A | Add capictorr | Added getter pump
| IFY0IA1 | Cubes to shop for fiducials and tube weld | Status updated
| VIP0I01A | Exists in tunnel | Should be VIP0I01A, not VIP0I01B
| MHD0I01AH | Coils ordered, assembly parts final design/order | Status updated
| MHD0I01AV | Coils ordered, assembly parts final design/order | Status updated
| MBH0I01BH | Exists in tunnel
| MBH0I01BV | Exists in tunnel
| IPM0I01B | Exists in tunnel
| SBK0I01 | Finish kicker design, bid and fabricate
| VBV0I02 | New gate value here
| ITV0I02 | Garages tacked welded, Phil needs parts to rebuild | Status updated
| IHA0I02 | Exists in tunnel
| IFY0IA2 | Cubes to shop for fiducials and tube weld | Status updated
| VIP0I02 | Exists in tunnel
| VRV0I02 | On-hand right angle valve | Added right angle valve
| VGP0I02 | Add NEG
| MHD0I02H | Coils ordered, assembly parts final design/order | Status updated
| MHD0I02V | Coils ordered, assembly parts final design/order | Status updated