## cold quarter
ALL Procurements Direct Dollars
October | November | December | January | February | March | April | May | June | July | August
ALL Procurements Direct Dollars October: Facilities: electric Cave1; ALL Procurements Direct Dollars November: Facilities: network; ALL Procurements Direct Dollars December: Facilities: structural; ALL Procurements Direct Dollars January: Facilities: electric Cave2; ALL Procurements Direct Dollars February: Facilities: Fire; ALL Procurements Direct Dollars March: Facilities: Paint, Mech, Gate | Just electricity, nothing else |  |  | 109k$ includes 20% extra for unanticipated Jlab overhead
ALL Procurements Direct Dollars October: Procurement: 109k$; ALL Procurements Direct Dollars November: Procurement: 23k$; ALL Procurements Direct Dollars December: Procurement: 94k$; ALL Procurements Direct Dollars January: Procurement: 50k$; ALL Procurements Direct Dollars February: Procurement: 10k$; ALL Procurements Direct Dollars March: Procurement: 19k$ | Just Cave1, top of Cave1 and control room |  |  | 23k$ in November is for communications (18k$) and stuff we forgot
ALL Procurements Direct Dollars October: Labor EE: 2 PW; ALL Procurements Direct Dollars November: Labor EE: 2 PW; ALL Procurements Direct Dollars December: Labor; ALL Procurements Direct Dollars January: Labor; ALL Procurements Direct Dollars February: Labor; ALL Procurements Direct Dollars March: Labor: | Cave2 electricity will cost more later
ALL Procurements Direct Dollars October: Cryo - Controls; ALL Procurements Direct Dollars November: Cryo - Controls; ALL Procurements Direct Dollars December: Cryo - Controls; ALL Procurements Direct Dollars January: Cryo - Controls | Procurements for controls per Buddy Carlton 18k$, used to be 44k$, we must have ordered stuff in FY15
Procurement: 18k$ for controls | Procurement: 0k$ | Procurement | Procurement
ALL Procurements Direct Dollars October: Labor EE: 2PW; ALL Procurements Direct Dollars November: Labor EE: 2PW; ALL Procurements Direct Dollars December: Labor EE: 0.5PW; ALL Procurements Direct Dollars January: Labor EE: 0.5PW | PR358479 in queue, 2.8k$, waiting for signature, could be 16 wks delivery
Labor ET: 2PW | Labor ET: 4PW | Labor ET: 2PW | Labor ET: 1PW
ALL Procurements Direct Dollars October: Cryo - Design and Plumbing; ALL Procurements Direct Dollars November: Cryo - Design and Plumbing; ALL Procurements Direct Dollars December: Cryo - Design and Plumbing; ALL Procurements Direct Dollars January: Cryo - Design and Plumbing; ALL Procurements Direct Dollars February: Cryo - Design and Plumbing | After this, there will be additional work for HDIce, which we are still pondering the path forward
ALL Procurements Direct Dollars October: Procurement: 20k$; ALL Procurements Direct Dollars November: Procurement: 20k$; ALL Procurements Direct Dollars December: Procurement: 10k$; ALL Procurements Direct Dollars January: Procurement: 0k$; ALL Procurements Direct Dollars February: Procurement: 0k$ | i.e., there are different ways we can cool the HDIce target: buying Lhe, creating our own fill station, or attaching directly to CTF
Labor ME: 3 PW | Labor ME: 2 PW | Labor ME: 1 PW | Labor ME: 2 PW | Labor ME: 0 PW
Labor MD: 5 PW | Labor MD: 3 PW | Labor MD: 1 PW | Labor MD: 0 PW | Labor MD: 0 PW
Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW
|  |  |  | Cryo - HDIce | Cryo - HDIce | Cryo - HDIce | Cryo - HDIce
|  |  |  | Procurement | Procurement | Procurement | Procurement
|  |  |  | Labor | Labor | Labor | Labor
[11 empty] | Installation Group tasks: |  | Ricky Taylor, Bern Johnson, Neil Wilson
ALL Procurements Direct Dollars November: Installation Group; ALL Procurements Direct Dollars December: Installation Group; ALL Procurements Direct Dollars January: Installation Group; ALL Procurements Direct Dollars February: Installation Group; ALL Procurements Direct Dollars March: Installation Group; ALL Procurements Direct Dollars April: waveguides, girders, cable trays | November: | attach rad shielding plates above and below penetrations, cable trays
ALL Procurements Direct Dollars November: Procurement: 3k$; ALL Procurements Direct Dollars December: Procurement: 3k$; ALL Procurements Direct Dollars January: Procurement: 13k$; ALL Procurements Direct Dollars February: Procurement: 3k$; ALL Procurements Direct Dollars March: Procurement: 3k$; ALL Procurements Direct Dollars April: LCW, compressed air, | December: | SSG conduit for ODH and PSS, sheet metal on rack sides
ALL Procurements Direct Dollars November: Labor Mech Tech: 3 PW; ALL Procurements Direct Dollars December: Labor Mech Tech: 3 PW; ALL Procurements Direct Dollars January: Labor Mech Tech: 3 PW; ALL Procurements Direct Dollars February: Labor Mech Tech: 3 PW; ALL Procurements Direct Dollars March: Labor Mech Tech: 3 PW | January: | Finish railings above cave
cable trays…
| Ops Network and Controls | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Network and Controls:
| Procurement: 32.5k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | (5) VME IOCs @ 3500/ea - $17,500
| Labor: 5 PW (Brad Cumbia) | Labor CSci: 5 PW | Labor CSci: 5 PW | Labor CSci: 5 PW | Labor CSci: 5 PW | Labor CSci: 5 PW | Labor CSci: 5 PW | Labor CSci: 5 PW | Labor CSci: 5 PW | Labor CSci: 5 PW | (1) Network Switch Line Cards $15,000
ALL Procurements Direct Dollars November: High Power RF; ALL Procurements Direct Dollars December: High Power RF; ALL Procurements Direct Dollars January: High Power RF; ALL Procurements Direct Dollars February: High Power RF | Master oscillator |  | (we will borrow an MO from somewhere) |  | straight waveguide: TBD
ALL Procurements Direct Dollars November: Machine shop: 5k$; ALL Procurements Direct Dollars December: Procurement: 15k$ waveguides; ALL Procurements Direct Dollars January: Procurement; ALL Procurements Direct Dollars February: Procurement | Two LL rf control boards |  |  |  | flex: 4 x 1.5k ea = 6k
ALL Procurements Direct Dollars November: Procurement: 5k$ HPA controller; ALL Procurements Direct Dollars December: Labor EE: 2 PW; ALL Procurements Direct Dollars January: Labor EE: 2 PW; ALL Procurements Direct Dollars February: Labor EE: 2 PW | klystrons installed in racks |  |  |  | directional couplers: 2 x 1.5k = 3k
ALL Procurements Direct Dollars November: Labor EE: 2 PW; ALL Procurements Direct Dollars December: Labor ET: 2PW; ALL Procurements Direct Dollars January: Labor ET: 2PW; ALL Procurements Direct Dollars February: Labor ET: 2PW | controls hardware |  |  |  | sweeps/miters; TBD
ALL Procurements Direct Dollars November: Labor ET: 2PW | waveguides (also requires MD support to layout) |  |  |  | gaskets, hangers, hardware
ALL Procurements Direct Dollars November: Labor MD: 2 PW |  |  |  |  | HPA controller: $5k
Labor for two channels of RF
Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF |  |  | Kevin to build the HP klystron rack and controls.
Procurement: 5 k | Procurement: 5 k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k
Labor ET: 2 PW | Labor ET: 4 PW | Labor ET: 4 PW | Labor ET: 4 PW | Labor ET: 4 PW | Labor ET: 4 PW | Labor ET: 4 PW | Labor ET: 4 PW | Labor ET: 4 PW
ALL Procurements Direct Dollars November: SSG: ODH; ALL Procurements Direct Dollars December: SSG: ODH; ALL Procurements Direct Dollars January: SSG: ODH | ODH 14 PW
ALL Procurements Direct Dollars November: Procurement: 2k$ (tube PR); ALL Procurements Direct Dollars December: Procurement: 0k$; ALL Procurements Direct Dollars January: Procurement: 0k$ | 2k$ procurement total, the PR in queue waiting to be signed
ALL Procurements Direct Dollars November: Labor: 0 PW; ALL Procurements Direct Dollars December: Labor: 7 PW; ALL Procurements Direct Dollars January: Labor: 7 PW | Neil to help with installation
ALL Procurements Direct Dollars January: SSG: PSS; ALL Procurements Direct Dollars February: SSG: PSS | PSS 68 PW, original estimate |  |  | Henry said he can't get to PSS till January
ALL Procurements Direct Dollars January: Procurement: 35k$; ALL Procurements Direct Dollars February: Procurement: 0k$ | 35k$ procurement
ALL Procurements Direct Dollars January: Labor: 10 PW; ALL Procurements Direct Dollars February: Labor: 10 PW | Neil to help with installation
|  |  | Design: finish keV | Design: finish keV | Design: MeV beamline | Design: MeV beamline | Design: MeV beamline | Design: MeV beamline
|  |  | Labor: 4 PW | Labor: 4 PW | Labor: 4 PW | Labor: 4 PW | Labor: 4 PW | Labor: 4 PW
|  |  | I&C: valves | I&C: valves | I&C: valves | I&C: valves | I&C: valves | I&C: valves | I&C: valves
|  |  | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement
|  |  | Labor | Labor | Labor | Labor | Labor | Labor | Labor
|  |  | I&C: Viewers | I&C: Viewers | I&C: Viewers | I&C: Viewers | I&C: Viewers | I&C: Viewers | I&C: Viewers
|  |  | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement
|  |  | Labor | Labor | Labor | Labor | Labor | Labor | Labor
October | November | December | January | February | March | April | May | June | July | August
|  |  | I&C: BPMs | I&C: BPMs | I&C: BPMs | I&C: BPMs | I&C: BPMs | I&C: BPMs | I&C: BPMs
|  |  | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement
|  |  | Labor | Labor | Labor | Labor | Labor | Labor | Labor
|  |  | I&C: SCAM | I&C: SCAM | I&C: SCAM | I&C: SCAM | I&C: SCAM
|  |  | Procurement | Procurement | Procurement | Procurement | Procurement
|  |  | Labor | Labor | Labor | Labor | Labor
|  |  | DC Power | DC Power | DC Power | DC Power | DC Power | DC Power | DC Power
|  |  | Procurements | Procurements | Procurements | Procurements | Procurements | Procurements | Procurements
|  |  | Labor | Labor | Labor | Labor | Labor | Labor | Labor
Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS
Procurement | Procurement | Procurement | build keV beamline | build keV beamline | build keV beamline | build keV beamline | build keV beamline | build MeV beamline | build MeV beamline | build MeV beamline
Labor | Labor | Labor | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement | Procurement
|  |  | Labor | Labor | Labor | Labor | Labor | Labor | Labor | Labor
| Magnet measurement | Magnet measurement | Magnet measurement | Magnet measurement
| Labor | Labor | Labor | Labor