## Slide 1: CPS Engineering Status March 25, 2022
Steven Lassiter

## Slide 2
1. Prototyping development
2. CPS magnet coils updates
3. FLEUNT licensing issues at JLAB
4. W block shipments / remaining job list / updates

## Slide 3: CPS Prototype
Parts in JLAB’s Machine shop being fabricated

## Slide 4: Prototype Base Cooling Element Redesigned

## Slide 5: CPS Magnet Coils
Just received latest updated drawing from TOKIN on single wound coils.
Bert is updating 3D model – See JT model

## Slide 6: CPS Coils Cooling Calcuations

## Slide 7: CPS Magnet JT

## Slide 8: FLEUNT Modeling
Todd Coates was able to obtain 5 additional temporary licenses of FLEUNT until the end of April.
BUT upgrades to the ANSYS license file, (new date stamp on the main file) resulted in the temp license files not working any more, (older date stamp). He is working on getting them re-issued.
Amy has been able to work on a simplified model on a very limited basis. See her report.

## Slide 9
280 W blocks out of 440 have been delivered from ELMET
Job List and considerations
  Finish magnet design and drawings for procurement
  Prototype testing
  Shielding layout in CAD – both internal and external
  External W Shielding in boxes for ease of handling
  Raster layout
  Radiator design
  Beamlines with Be windows
  N2 purge within magnet to reduce corrosive gases
  Absorber final design
Sandesh of the Magnet support group is also working on cooling calculations for the prototype and absorber using FLEUNT, independent review.
LCW cooling of the Absorber and coils is likely as the heating load is 30kW. Still waiting on Radcon’s approval.