## Feuil1
Time | serial Tasks | Name | Time and Pax | // tasks | // tasks | // tasks | // tasks | // tasks | // tasks | // tasks | // tasks | Total people
|  |  |  | 33 | 62 | 63 | 64 | 65 | 66 | 70 | 71
|  |  |  | Wrapping 1080 crystals | connecting T° sensors | assembly 1080 PMts + base | assembly 1080 kapton on PMts | assembly 1080 PMts in their individual support | assembly fibers + front cables on PCB on a table | Additionnal sensors connecting | Gas connecting
|  | Task reference :see ppt mounting procedure |  | 33: wrapping ready
before our arrival ?
needs 5 ' / crystal to wrapp
if reflective sheet preliminary folded
12 days @ 2 (without folding)
Day 1 administration
Day 2 dismounting | 1 | Opening wood box | 1 h @ 3 | 63: 1'/ PMt @1
| 2 | Remove black plastic plates | 2 h @ 3 | 63: 9h @2
| 3 | Removing 30 PCB protections | 1 h @ 2 | [8 empty] | 6 | bar: 63
| 4 | Removing 30 PCB | 2 h @ 2 | bar: 63
| 5 | Removing bottom wood base | 0,5 h @ 2 | bar: 63
| 6 | Lift box and pull down on Jlab frame | 2 h @ 4 | bar: 63
Day 3 dismounting | 7 | Removing 1080 PMt supports from box | 4 h @ 2 | 66: 90 ' / pcb/people
| 8 | Removing 2 scintillators | 0,5 h @ 2 | 66: 30 PCB
| 9 | disconnecting copper tubes | 0,5h @ 2 | 66: 5 PCB / day/ people
| 10 | disconnecting copper tubes |  | 66: 10 PCB/day @ 2 (3 days)
| 11 | removing reinforcement arms | [9 empty] | 5 to 6 | bar: 66
| 12 | Removing false plastic shielding | 1 h @ 2 | bar: 66
| 13 | Removing front reinforcement plate | 1 h @ 3 | bar: 66
| 14 | Removing Top aluminum plate | bar: 66
| 15 | Removing threaded rods and fixing nuts | 1 h @ 3 | bar: 66
Day 4 dismounting and start mounting | 16 | Removing calorimeter support from box |  | 64: 1'/PMt @ 2
| 17 | Removing 4 copper plates |  | 64: 18 h @ 2
| 18 | Removing front PE plate | bar: 64; 66
| 19 | Removing front frame | 3 h @ 3 | [8 empty] | 6 to 7 | bar: 64; 66
| 20 | Removing screws under base plate | 1 h @ 3 | bar: 64; 66
| 21 | Mounting Bottom iron shielding plate | bar: 64; 66
| 22 | Mounting front frame | 1,5 h @ 3 | bar: 64; 66
| 23 | Mounting bottom tubes and tight test | 2 h @ 2 | bar: 64; 66
| 24 | Mounting calorimeter support in the box | 2 h @ 3 | bar: 64; 66
Day 5 mounting frame crystals | 25 | Mounting bottom foam | 2 h @ 2 | bar: 64; 66
| 26 | Mounting vertical Mu metal plates | 1 h @ 2 | bar: 64; 66
| 27 | Mounting bottom cooling plate | [9 empty] | 6 | bar: 64; 66
| 28 | slide bottom H 1,5mm Mu metal | 0,5 h @ 2 | bar: 64; 66
| 29 | Re connect bottom right tubes | 0,5 h @ 2 | bar: 64; 66
| 30 | slide vertical carbon plates | 2 h @ 2 | bar: 64; 66
| 31 | slide 1st H carbon plates and adjustment shims | bar: 64; 66
| 32 | preliminary mounting reinforcement arms | bar: 64; 66
Days 6 Stacking 135 crystals | 34 | inserting stop plastic part | 6'/crystal /people | bar: 64
| 35 | inserting 1st crystal with its wrapping | 2 peoples mounting | bar: 64
| 36 | adjust backward height of crystal | 7 h /day | bar: 64
| 37 | adjust front height of crystal | 135 crystal/day @2 | bar: 64
| 38 | insert 1st raw (step 34 to 37) | 3 +3/4 raws/day | bar: 64
| 39 | slide carbon H plate | +2 peoples help mounting | bar: 64
| 40 | insert 1st 0,5 mm Mu metal | [9 empty] | 6 | bar: 64
| 41 | insert front plastic part with reflective sheet | bar: 64
| 42 | insert layer front plastic part with reflective sheet | bar: 64
| 43 | Stack crystal raws until raw 29 (tasks 34 to 42) | bar: 64
| 44 | Stack crystal raws until raw 29 (tasks 34 to 42) | bar: 64
| 45 | mounting top aluminum frame | bar: 64
| 46 | Stacking the 6 last raws | bar: 64
| 47 | remove right side rods | bar: 64
Days 7 Stacking 135 crystals | 34 to 41 |  | 7 h @ 4 | 65: 5h @ 2 | 6
Days 8 Stacking 135 crystals | 34 to 41 |  | 7 h @ 4 | 71: 7 h @ 2 | 6
Days 9 Stacking 135 crystals | 34 to 41 |  | 7 h @ 4 | [8 empty] | 4
Days 10 Stacking 135 crystals | 34 to 41 |  | 7 h @4 | [8 empty] | 4
Days 11 Stacking 135 crystals | 34 to 41 |  | 7 h @ 4 | [8 empty] | 4
Days 12 Stacking 135 crystals | 34 to 41 |  | 7 h @ 4 | [8 empty] | 4
Days 13 Stacking 135 crystals | 34 to 41 |  | 7 h @ 4 | [8 empty] | 4
Day 14 mounting cooling and foam | 48 | mounting vertical right copper plate | 2 h @ 3
| 49 | mounting right side rods with spacers
| 50 | mounting vertical left copper plate
| 51 | mounting corner to fix top copper plate
| 52 | mountind Top copper plate
| 53 | mounting foam around copper plates | 1 h @ 3 | [8 empty] | 4
| 54 | mounting the 2 vertical shielding plates | 1 h @ 2
| 55 | mounting the top shielding plate
| 56 | mounting arms and spacers 2 mm | 1 h @ 2
| 57 | connecting all copper tubes and tightness test | 4 h @ 4
Day 15 finalising front calo | 58 | mounting front PE plate with sensors | 1 h @ 2
| 59 | mounting front PE plate with sensors
| 60 | mounting front foam | 1 h @ 2 | [8 empty] | 3
| 61 | mounting Top aluminum plate with connectors and cables | 1 h @ 3
Day 16 monting PMt | 67 | mounting 1080 PMt assembly on support plate |  | 62: 4 h @ 2
| 68 | mounting 1080 PMt assembly on support plate | [9 empty] | 4 | bar: 62
| 69 | mounting 1080 PMt assembly on support plate | 7 h @ 2 | bar: 62
Day 17 monting PMt | 67 to 69 |  | 7 h @ 2 | [8 empty] | 2
Day 18 monting PMt | 67 to 69 |  | 7 h @ 2 | [8 empty] | 2
Day 19 mounting and connection 2 PCB in box | 72 | mounting first left PCB |  | 70: 4 h @ 2
| 73 | connecting fiber and front cables on PMt support | bar: 70
| 74 | connecting LED flat cables | bar: 70
| 75 | connecting anode cables to the top plate | 3,75 h/pcb @ 1 Max at a time | [8 empty] | 4 | bar: 70
| 76 | mounting of all pcb (tasks 72 to 75)x30 | 2 PCB /day @ 1 alone in the box | bar: 70
| 77 | close the box | 2 h @ 3 | bar: 70
Day 20 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 21 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 22 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 23 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 24 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 25 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 26 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 27 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 28 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 29 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 30 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 31 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 32 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2
Day 33 mounting and connection 2 PCB in box | 72 to 75 | [10 empty] | 2