## Slide 1: Draft HPS Run Plan
March 30, 2015

## Slide 2: Beamline Setup
Set Up Beam to Alcove * Good scans on upstream harps, good halo rates, upstream BPMs calibrated * 4mm SVT Collimator in; SVT fully retracted * Bring centered beam to dump. Good spot on screen at x=+5mm; y=-5mm * Good scans on 2H02, low halo rates * Downstream BPMs calibrated. Beware excessive motions during calibration * Turn Chicane on * SVT Wire Scan. Move beam to desired spot x,y with upstream movers. * Record BPMs and Magnets and Harp Scans * Establish Orbit Locks * Mike/Arne provide operator procedure

## Slide 3: Trigger Studies
Conditions: Can proceed if good beams are established to Hall B dump and beams are stable. Can proceed before bpms are calibrated and orbit locks are on, if beams are good and calibration is delayed.
Online trigger diagnostics ready
With Trigger Expert on shift, take ALLTrig data for 1hr at 50 nA
Analyze data. Trigger OK? Rates? Report at 3 o’clock meeting.
When to take individual runs?

## Slide 4: Beam Stability Studies
Conditions: Need bpms calibrated and orbit locks on.
Confirm diagnostics ready and data being recorded.
Need bpm diagnostics available to look for beam motion at 2H02
With Expert, run beam stability studies at 2H02 harp on 1mm wire * 4 hours running on top wire * 4 hours running on bottom wire
Can this running be used for trigger studies with individual triggers?

## Slide 5: SVT Commissioning
Conditions for moving SVT in: 1) Need beam stability studies to confirm no fast beam motion in trip 2) Need orbit locks on 3) Need beam trip diagnostics and procedures: SVT procedures for recovery from beam trip MCC procedures for recovery from beam trip BPM display to show beam position ok
Studies in Out position with SVT expert. Could get started before full stability studies with an attempt to time in with SVT in out position 1)Time in at <10nA on 4 um target (assumes 2.2 GeV) 2)Take sample data and begin offline analysis
When have met conditions above, proceed with SVT commissioning plan. SVT expert should be on hand.
SVT commissioning ends with data runs at several “in” positions—to be decided as we see what backgrounds and performance are like.

## Slide 6: Data Taking
Take data in final SVT commissioning steps * use 3 mm collimator * Fully protected Si (1.5 mm from beams)
Check occupancies and trigger rates with full system Get more experience with beam trips Performance OK? Try full current
Safe to move in? * Check beam trips history? Any beam motion? * Handle occupancy and rates? * Feeling lucky?

## Slide 7: Priorities
Beams * Good beams to tagger * Beams to alcove * If people are available, bpm calibration and orbit locks Do this as soon as people are available * If people not available, set up chicane and target studies and then Essential Trigger studies Time in SVT in out position
When have bpms calibrated and orbit locks on * Get MCC procedures for setup * Beam Stability Studies
When have beam stability studies and SVT diagnostics available proceed with SVT commissioning
Take data. This is final stage of SVT commissioning.