## Installation
KLONG CPS Installation
| Days | # | # | FTE | FTE | FTE | FTE | FTE
Task | Duration | Eng | Tech | Eng | Tech | Facilities | S&A | EES
Remove old equipment
Crates | 5 | 0.1 | 3 | 0.002 | 0.06
microscope | 3 | 0.1 | 3 | 0.0012 | 0.036
store cables | 5 | 0 | 2 | 0 | 0.04
Permanent magnet (and store it) | 2 | 0.1 | 3 | 0.0008 | 0.024
Hodoscope | 3 | 0.1 | 2 | 0.0012 | 0.024
Beamline | 5 | 0.2 | 3 | 0.004 | 0.06
Install CPS
Install Concrete Base | 10 | 0.1 | 1 | 0.004 | 0.04 | 0.12
Install rails | 4 | 0.3 | 3 | 0.0048 | 0.048 |  | 0.008
Install support structure | 10 | 0.3 | 3 | 0.012 | 0.12 |  | 0.016
Install magnet and test | 10 | 0.2 | 3 | 0.008 | 0.12
Install Power Supply | 5 | 0.1 | 3 | 0.002 | 0.06 |  |  | 0.06
Survey and alignment | 2 | 0.2 | 1 | 0.0016 | 0.008 |  | 0.008
Install/test radiator | 4 | 0.3 | 2 | 0.0048 | 0.032 |  | 0.01
Install partial shielding | 20 | 0.2 | 4 | 0.016 | 0.32
Enclose removable shielding box and align | 10 | 0.2 | 3 | 0.008 | 0.12 |  | 0.016
Test Magnets | 5 | 0.2 | 2 | 0.004 | 0.04
Survey and Alignment intermediate step | 2 | 0.2 | 1 | 0.0016 | 0.008 |  | 0.008
Install remaining shielding | 20 | 0.2 | 4 | 0.016 | 0.32
Install/test cooling system | 10 | 0.4 | 3 | 0.016 | 0.12
Install Perm Magnet | 4 | 0.2 | 3 | 0.0032 | 0.048 |  | 0.008
Install beamline & windows | 5 | 0.2 | 3 | 0.004 | 0.06
Install New Girder | 3 | 0.1 | 3 | 0.0012 | 0.036 |  | 0.008
Setup and test controls | 20 | 0.1 | 1 | 0.008 | 0.08
Final Survey | 3 | 0.1 | 1 | 0.0012 | 0.012 |  | 0.016
Totals | 170 |  |  | 0.1256 | 1.836 | 0.12 | 0.098 | 0.06
Duration in months | 8.5
Techs required for duration (ave) | 2.592
Eng required for duration (ave) | 0.17732
Designer support | 0.2
Techs with overhead for safety and training | 3.1104

## Design and procure
KLONG CPS Design
| Days | # | # | FTE | FTE | FTE | FTE
Task | Duration | Eng | Des | Eng | Des | Facilities | S&A
Design new beamline
Beamline layout | 10 | 0.1 | 1 | 0.004 | 0.04
Perm Magnet setup | 2 | 0.1 | 1 | 0.0008 | 0.008
Vacuum pump setup | 2 | 0.1 | 1 | 0.0008 | 0.008
Final Beamline drawings | 25 | 0.2 | 1 | 0.02 | 0.1
Component procurement | 200 | 0.05 | 0.05 | 0.04 | 0.04
Design CPS
Design Concrete Base | 30 | 0.2 | 1 | 0.024 | 0.12 | 0.12
Design rails | 15 | 0.3 | 1 | 0.018 | 0.06
Design support structure/strongback | 25 | 0.4 | 1 | 0.04 | 0.1
Design adjustment system | 25 | 0.1 | 1 | 0.01 | 0.1
Design magnets | 65 | 0.5 | 1 | 0.13 | 0.26
Procure Magnets and Power Supplies | 250 | 0.1 | 0.1 | 0.1 | 0.1
Design radiator | 25 | 0.1 | 1 | 0.01 | 0.1
Design shielding | 120 | 0.2 | 1 | 0.096 | 0.48
Design containment box | 30 | 0.3 | 1 | 0.036 | 0.12
Test Magnets | 5 | 0.2 | 2 | 0.004 | 0.04
Design alignment system | 45 | 0.2 | 1 | 0.036 | 0.18
Design cooling system | 30 | 0.4 | 1 | 0.048 | 0.12
Procure all shileding components | 200 | 0.1 | 0.05 | 0.08 | 0.04
Procure rails, strongback and cooling | 200 | 0.1 | 0.05 | 0.08 | 0.04
Procure radiator components | 80 | 0.1 | 0.05 | 0.032 | 0.016
Installation Drawings | 40 | 0.1 | 1 | 0.016 | 0.16
Totals | 494 |  |  | 0.8256 | 2.232 | 0.12
Duration in months | 24.7
Des required for duration (ave) | 1.0844
Eng required for duration (ave) | 0.4011

## Pavel Material 75
Klong Compact Photon Source - Pavel 75 material
Component | qty | Lbs | Kg | cost ea $ | Fab cost $ | Total cost $ |  | cost $/lb | cost/kg
Copper absorber | 1 | 1916 | 869.864 | 33000 | 0 | 33000 | as manufactured in 2 sections | 17.2234 | 37.8914 | based old Quote from manufacturer
WCu absorbers | 138.32 | 3458 | 1569.932 | 1500 |  | 207480 | small blocks (25 lbs ea) | 60 | 132 | based on 4 year old quote for tungsten x a factor 0f 1.2
Lead Bricks (painted) | 2220.4231 | 57731 | 26209.874 | 62 | 2000 | 139666.2308 | 2x4x8 inch^3 bricks (26 lbs ea) | 2.4193 | 5.3224 | based on quote from last year
borated poly sheets | 89.4813 | 14317 | 6499.918 | 800 | 35792.5 | 107377.5 | 1"x48"x96" (160 lbs ea) | 7.5 | 16.5 | based on quote from last year
Iron core | 1 | 3370 | 1529.98 | 16850 | 10000 | 26850 | machined in several pieces | 7.9674 | 17.5282 | based on current material costs and machining
Iron shield | 1 | 27555 | 12509.97 | 137775 | 10000 | 147775 | machined in several pieces | 5.3629 | 11.7984 | based on current material costs and machining
Barite concrete (CPS and beamline) | 893.926 | 55132 | 25029.928 | 42 | 10000 | 47544.892 | 28kg blocks 4x8x16" | 0.86238 | 1.8972 | based on material cost and guess at what it would take to fabricate | $190/ft^3
Adjustment components | 3 |  |  | 2800 |  | 8400
Support Structure | 1 | 2000 |  | 30000 |  | 30000
Lifting box (radiation containment portion) | 1 |  |  | 14000 |  | 14000
Rail System | 1 |  |  | 4000 |  | 4000
Water Cooling System | 1 |  |  | 5000 |  | 5000
Beamline Plus girder and windows | 1 |  |  | 15000 |  | 15000
Radiator (3 position remotely) | 1 |  |  | 15000 |  | 15000 |  |  |  | Magnet 1.0; Cu 1.45; WCu 0.23; FeCore 1.56; Pb 40.39; FeShield 17.56; BariteCPS 29.92; B.Poly 5.2 --> CPStot 97.31 .
Magnet | 1 | 2202.65 | 1000.0031 | 110000 |  | 110000 | estimate from Everson Tesla
Power Supply | 1 |  |  | 200000 |  | 200000
Machining of shielding components | 1 |  |  | 15000 |  | 15000
Concrete pier | 1 |  |  | 20000 |  | 20000
Temperature sensors and wires | 20 |  |  | 200 |  | 4000
Vacuum Pump and controllers | 1 |  |  | 20000 |  | 20000
PLC modules and shielding | 5 |  |  | 1500 |  | 7500
Total Materials |  | 167681.65 | 75219.4691 |  |  | 1177593.6228
[6 empty] | 819693.6228 | Total for just absorber, magnet and shielding