## Sheet1
| 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
CPS
Hall C Conceptual Design | bar: 2019 Q1 to 2019 Q4
Hall D Conceptual Design | bar: 2019 Q1 to 2021 Q1
Electron Beamline Optimization
Shielding Optimization
Hall D Engineering Design | bar: 2021 Q2 to 2022 Q2
Acquiring Funding & Material | bar: 2021 Q2 to 2022 Q4
Hall D Construction | bar: 2022 Q3 to 2023 Q4
KPT
Conceptual Design | bar: 2019 Q1 to 2020 Q2
Engineering Design | bar: 2020 Q4 to 2021 Q4
Construction | bar: 2022 Q1 to 2022 Q4
Installation in collimator alcove | bar: 2022 Q4 to 2023 Q1
KFM
Conceptual Design | bar: 2020 Q1 to 2020 Q4
Acquiring Funding & Material for Prototypes | bar: 2020 Q1; 2020 Q3; 2021 Q4
Prototyping | bar: 2021 Q4 to 2022 Q1
Acquiring Funding & Material | bar: 2020 Q4 to 2021 Q4
Construction | bar: 2021 Q4 to 2023 Q1
Delivery from UK to Jlab | bar: 2022 Q4; 2023 Q2
Installation in exp hall | bar: 2023 Q1 to 2023 Q4
CryoTarget
Installation in GlueX detector | bar: 2022 Q4 to 2023 Q1
Time for Beam development
Acquiring high power injector laser amplifiers | bar: 2022 Q1 to 2022 Q3
Gain switching development | bar: 2022 Q2 to 2022 Q4
Bench testing and integration | bar: 2023 Q1 to 2023 Q2
CEBAF deployment and testing, gun ramp-up | bar: 2023 Q3 to 2023 Q4