## Installation
KLONG CPS Installation
| Days | # | # | FTE | FTE | FTE | FTE
Task | Duration | Eng | Tech | Eng | Tech | Facilities | S&A
Remove old equipment
Crates | 5 | 0.1 | 3 | 0.002 | 0.06
microscope | 3 | 0.1 | 3 | 0.0012 | 0.036
Hodoscope | 3 | 0.1 | 2 | 0.0012 | 0.024
Beamline | 5 | 0.2 | 3 | 0.004 | 0.06
Install CPS
Install Concrete Base | 10 | 0.1 | 1 | 0.004 | 0.04 | 0.12
Install rails | 4 | 0.3 | 3 | 0.0048 | 0.048 |  | 0.008
Install support structure | 10 | 0.3 | 3 | 0.012 | 0.12 |  | 0.016
Install magnets | 10 | 0.2 | 3 | 0.008 | 0.12
Install Power Supplies | 5 | 0.1 | 3 | 0.002 | 0.06
Survey and alignment | 2 | 0.2 | 1 | 0.0016 | 0.008 |  | 0.008
Install radiator | 2 | 0.3 | 2 | 0.0024 | 0.016
Install partial shielding | 20 | 0.2 | 4 | 0.016 | 0.32
Test Magnets | 5 | 0.2 | 2 | 0.004 | 0.04
Survey and Alignment | 2 | 0.2 | 1 | 0.0016 | 0.008 |  | 0.008
Install remaining shielding | 20 | 0.2 | 4 | 0.016 | 0.32
Install cooling system | 10 | 0.4 | 3 | 0.016 | 0.12
Install Perm Magnet | 4 | 0.2 | 3 | 0.0032 | 0.048 |  | 0.008
Install beamline & windows | 5 | 0.2 | 3 | 0.004 | 0.06
Install New Girder | 3 | 0.1 | 3 | 0.0012 | 0.036 |  | 0.008
Final Survey | 2 | 0.1 | 1 | 0.0008 | 0.008 |  | 0.008
Totals | 130 |  |  | 0.106 | 1.552 | 0.12 | 0.064
Duration in months | 6.5
Techs required for duration (ave) | 2.8652
Eng required for duration (ave) | 0.19569
Techs with overhead for safety and training | 3.4383

## Material
Klong Compact Photon Source
Component | qty | Lbs | cost ea $ | Fab cost $ | Total cost $ |  | cost $/lb
Copper absorber | 4 | 250 | 2900 | 0 | 11600 | as manufactured in 4 sections | 46.4 | Quote from manufacturer
Tungsten absorbers | 406.12 | 10153 | 1400 |  | 568568 | small blocks (25 lbs ea) | 56 | based on 4 year old quote x a factor 0f 1.2
Lead Bricks | 4408.1154 | 114611 | 52 | 2000 | 231222 | 2x4x8 inch^3 bricks (26 lbs ea) | 2.0175 | based on quote from last year
borated poly sheets | 6.7938 | 1087 | 800 | 2717.5 | 8152.5 | 1"x48"x96" (160 lbs ea) | 7.5 | based on quote from last year
Adjustment components | 3 |  | 2800 |  | 8400
Support Structure | 1 |  | 30000 |  | 30000
Rail System | 1 |  | 4000 |  | 4000
Water Cooling System | 1 |  | 5000 |  | 5000
Beamline Plus girder | 1 |  | 10000 |  | 10000
Radiator (3 position remotely) | 1 |  | 15000 |  | 15000
Magnet | 2 |  | 88000 |  | 176000 | estimate from Everson Tesla
Power Supply | 1 |  | 100000 |  | 100000
Machining of shielding components | 1 |  | 15000 |  | 15000
Concrete pier | 1 |  | 20000 |  | 20000
Temperature sensors and wires | 20 |  | 200 |  | 4000
Vacuum Pump and controllers | 1 |  | 20000 |  | 20000
PLC modules and shielding | 5 |  | 1500 |  | 7500
Total Materials |  |  |  |  | 1234442.5

## Design and procure
KLONG CPS Design
| Days | # | # | FTE | FTE | FTE | FTE
Task | Duration | Eng | Des | Eng | Des | Facilities | S&A
Design new beamline
Beamline layout | 10 | 0.1 | 1 | 0.004 | 0.04
Perm Magnet setup | 2 | 0.1 | 1 | 0.0008 | 0.008
Vacuum pump setup | 2 | 0.1 | 1 | 0.0008 | 0.008
Final Beamline drawings | 25 | 0.2 | 1 | 0.02 | 0.1
Component procurement | 200 | 0.05 | 0.05 | 0.04 | 0.04
Design CPS
Design Concrete Base | 30 | 0.2 | 1 | 0.024 | 0.12 | 0.12
Design rails | 15 | 0.3 | 1 | 0.018 | 0.06
Design support structure/strongback | 25 | 0.4 | 1 | 0.04 | 0.1
Design adjustment system | 25 | 0.1 | 1 | 0.01 | 0.1
Design magnets | 65 | 0.4 | 1 | 0.104 | 0.26
Procure Magnets and Power Supplies | 250 | 0.1 | 0.1 | 0.1 | 0.1
Design radiator | 25 | 0.1 | 1 | 0.01 | 0.1
Design shielding | 120 | 0.2 | 1 | 0.096 | 0.48
Test Magnets | 5 | 0.2 | 2 | 0.004 | 0.04
Design alignment system | 45 | 0.2 | 1 | 0.036 | 0.18
Design cooling system | 30 | 0.4 | 1 | 0.048 | 0.12
Procure all shileding components | 200 | 0.1 | 0.05 | 0.08 | 0.04
Procure rails, strongback and cooling | 200 | 0.1 | 0.05 | 0.08 | 0.04
Procure radiator components | 80 | 0.1 | 0.05 | 0.032 | 0.016
Installation Drawings | 40 | 0.1 | 1 | 0.016 | 0.16
Totals | 424 |  |  | 0.7636 | 2.112 | 0.12
Duration in months | 21.2
Des required for duration (ave) | 1.1955
Eng required for duration (ave) | 0.43223

## Pavel Material
Klong Compact Photon Source - Pavel
Component | qty | Lbs | Kg | cost ea $ | Fab cost $ | Total cost $ |  | cost $/lb | cost/kg
Copper absorber | 1 | 3194 | 1450.076 | 33000 | 0 | 33000 | as manufactured in 2 sections | 10.3319 | 22.7301 | based old Quote from manufacturer
WCu absorbers | 20.4 | 510 | 231.54 | 1400 |  | 28560 | small blocks (25 lbs ea) | 56 | 123.2 | based on 4 year old quote for tungsten x a factor 0f 1.2
Lead Bricks | 3421.7308 | 88965 | 40390.11 | 52 | 2000 | 179930 | 2x4x8 inch^3 bricks (26 lbs ea) | 2.0225 | 4.4495 | based on quote from last year
borated poly sheets | 71.5875 | 11454 | 5200.116 | 800 | 28635 | 85905 | 1"x48"x96" (160 lbs ea) | 7.5 | 16.5 | based on quote from last year
Iron core | 1 | 3436 | 1559.944 | 17180 | 0 | 17180 | machined in several pieces | 5 | 11 | based on current material costs and machining
Iron shield | 1 | 38678 | 17559.812 | 193390 | 0 | 193390 | machined in several pieces | 5 | 11 | based on current material costs and machining
Barite concrete (CPS and beamline) | 2045.7078 | 126167 | 57279.818 | 10 | 10000 | 30457.0779 | 28kg blocks 4x8x16" | 0.2414 | 0.53109 | based on material cost and guess at what it would take to fabricate
Adjustment components | 3 |  |  | 2800 |  | 8400
Support Structure | 1 |  |  | 30000 |  | 30000
Rail System | 1 |  |  | 4000 |  | 4000
Water Cooling System | 1 |  |  | 5000 |  | 5000
Beamline Plus girder | 1 |  |  | 10000 |  | 10000
Radiator (3 position remotely) | 1 |  |  | 15000 |  | 15000 |  |  |  | Magnet 1.0; Cu 1.45; WCu 0.23; FeCore 1.56; Pb 40.39; FeShield 17.56; BariteCPS 29.92; B.Poly 5.2 --> CPStot 97.31 .
Magnet | 1 | 2202.65 | 1000.0031 | 110000 |  | 110000 | estimate from Everson Tesla
Power Supply | 1 |  |  | 100000 |  | 100000
Machining of shielding components | 1 |  |  | 15000 |  | 15000
Concrete pier | 1 |  |  | 20000 |  | 20000
Temperature sensors and wires | 20 |  |  | 200 |  | 4000
Vacuum Pump and controllers | 1 |  |  | 20000 |  | 20000
PLC modules and shielding | 5 |  |  | 1500 |  | 7500
Total Materials |  | 274606.65 | 124671.4191 |  |  | 917322.0779
[6 empty] | 678422.0779 | Total for just absorber, magnet and shielding

## Vitaly Material
Klong Compact Photon Source -Vitaly
Component | qty | Lbs | Kg | cost ea $ | Fab cost $ | Total cost $ |  | cost $/lb | cost/kg
Copper absorber | 1 | 6388 | 2900.152 | 66000 | 0 | 66000 | as manufactured in 2 sections | 10.3319 | 22.7301 | based old Quote from manufacturer
WCu absorbers N/A
Lead Bricks | 4185.0231 | 108810.6 | 49400.0124 | 52 | 2000 | 219621.2 | 2x4x8 inch^3 bricks (26 lbs ea) | 2.0184 | 4.4404 | based on quote from last year
borated poly sheets | 33.0413 | 5286.6 | 2400.1164 | 800 | 13216.5 | 39649.5 | 1"x48"x96" (160 lbs ea) | 7.5 | 16.5 | based on quote from last year
Iron core | 1 | 25771 | 11700.034 | 128855 | 0 | 128855 | machined in several pieces | 5 | 11 | based on current material costs and machining
Iron Shield N/A
Beamline Borated Concrete | 250 | 15418.5 | 6999.999 | 10 | 10000 | 12500 | 28kg blocks 4x8x16" | 0.81071 | 1.7836 | based on material cost and guess at what it would take to fabricate
Adjustment components | 3 |  |  | 2800 |  | 8400
Support Structure | 1 |  |  | 30000 |  | 30000
Rail System | 1 |  |  | 4000 |  | 4000
Water Cooling System | 1 |  |  | 5000 |  | 5000
Beamline Plus girder | 1 |  |  | 10000 |  | 10000
Radiator (3 position remotely) | 1 |  |  | 15000 |  | 15000
Magnet | 2 | 4405.3 | 2000.0062 | 88000 |  | 176000 | estimate from Everson Tesla
Power Supply | 1 |  |  | 100000 |  | 100000
Machining of shielding components | 1 |  |  | 15000 |  | 15000
Concrete pier | 1 |  |  | 20000 |  | 20000
Temperature sensors and wires | 20 |  |  | 200 |  | 4000
Vacuum Pump and controllers | 1 |  |  | 20000 |  | 20000
PLC modules and shielding | 5 |  |  | 1500 |  | 7500
Total Materials |  | 166080 | 75400.32 |  |  | 881525.7
[6 empty] | 642625.7 | Total for just absorber, magnet and shielding