Minutes from Wed. 10/11/2017 Scheduling meeting:
Clean room was moved to LERF vault 10/10/17
CM FL02 upstream end prepared for Vacuum work 10/12/17
Work on securing cryomodule vacuum will continue over the next weeks, followed by the move of the C20 from zone 4 to zone 2. This will then be re-connected to cryo & RF system
Kevin & Wes to visit SLAC 10/17-19/17
PSS certification scheduled for 10/30/17
Cryomodule move of FL02 & FL03 scheduled for 11/2/17
Cooldown of the LERF transferlines, the quarter & zone 2 will be after the CHL trip scheduled for week of November 12???